## Sheet1
Concrete Solutions - Requests For Information
No | Requested By | Question | Response
1 | University of Washington | The concrete division's scope of work includes the foundation of the tower. Please confirm that earthwork for the foundation is included in the scope. | All structural excavation and backfill required to complete the tower foundations is part of the concrete package.
2 | Montana Tech | 1) $/Manhour units on the Safety Recognition Plan. Does this mean the cost of safety equipment per the hours it will be used on the project? If not, what does this entail? 2) What time does "night" start where written permission from the client is needed for work? | 1) Sundt Construction implements a safety recognition program on all jobs designed to celebrate the successes of job safety performance. The $/MH units refers to the total unit price of the overall program you will implement in relation to the total manhours required for the Project. 2) "Night" work starts at 10PM.
3 | Oregon State | In Reference to page S141-3, does the scope of work cover all structural concrete on the sheet or does the scope end at the match line located above grid line 13.9? | The Structural Concrete package for this competition includes ONLY the Hotel Tower. For the sake of uniformity, Gridlines 14 and Q have columns that represent the limits of construction. The slab on grade incorporates these columns and then terminates.
4 | Oregon State | Are there CAD files available for this project that could be picked up on a flash drive? | No CAD files are available for this Project.
5 | Arizona State | Pertaining to Jobsite Footprint: Is fencing and access control provided by the GC? Is the area to include all scope specific needs (i.e. lay down yard, parking, etc.) Are we to treat the footprint as having no existing impeding structures? | Fencing and access control is provided by the GC. Contractor labor force parking is provided outside of the tower area, all other scope specific needs can be located within. All existing structures presenting an impediment to the Concrete Scope will have been removed prior to work starting.
6 | Arizona State | In regards to safety, I do not see a template for the Safety Recognition Plan. Do we create this document as we see fit? | Yes. See previously answered RFI.
7 | Arizona State | Are we able to know the region of work? We ask so that we may better plan our pours and safety considerations pertaining to the climate. | This project takes place in the Southwest US, in a desert climate.
8 | Montana Tech | Terminology wise, are the Caisson Footings the same as the drilled piers? This is in reference to Exhibit B asking for drilled piers and the location of drilled piers are not identified on the drawings. | Drilled piers / caissons can be used interchangably for the sake of this competition.
9 | Sac State | It is understood self-perform deliverables are fifty points. Please provide a point breakdown self-perform deliverables due tonight by eight p.m? | There is no point breakdown for each deliverable. The three deliverables required will be scored as a 50 point lump sum.
10 | Sac State | Please provide power point presentation from todays meeting that was at seven am in Southern Pacific AGB. | Please see attached RFI 10 PDF Response.
11 | Cal Poly - SLO | Please provide Sundt’s site specific Emergency Action Plan. Specifically, please provide location of emergency assembly points and evacuation plan, emergency contact information and protocol, personnel responsible for man counts, locations for emergency shutoffs in the case of a critical operation, and locations for eye wash stations and first aid if provided by Sundt. | The Building Group will meet with all subcontractors on the job prior to mobilization to develop the EAP document. For the sake of this exercise, disregard.
12 | Cal Poly - SLO | Please clarify T.O.S elevation at the bottom of the elevator pit. | Please reference Contract Documents (Shown in Arch & Struct)
13 | Cal Poly - SLO | Please provide the geo-tech soil report. | Provided during Partnering Meeting.
14 | Cal Poly - Pomona | 1. Please confirm that all soil is non expansive. Also, please a geo technical soils report if available. 2. Please confirm the CMU work expect CMU foundational work is not part of our scope of work. 3. 4' cassion that are pier caps are 6000 PSI per detail 227, but specs calls out 4000 psi for foundation and cassion. Please clarify. 4. Please provide the amount of time required for SOG and decks to reach 80% of its compression stress. | 1. Please refer to Geotechnical Report provided during Partnering Meeting. 2. A third-party subcontractor has provided pricing for this scope. Coordinate all activities with regard to your Project schedule. 3. Please refer to Sheet S007 and all General Structural Notes. 4. Please refer to General Structural Notes.
15 | Cal Poly - SLO | Please provide a site fencing and access points layout per G.C.’s logistics plan. | Please refer to RFI 015 response.
16 | Cal Poly - Pomona | Please provide a full section view of the escalator and elevator pits. | Please refer to provided Contract Documents. (See RFI 12)
17 | Cal Poly - Pomona | Please provide sheet S205 and S206 - elevation views for the concrete shear walls. | Please refer to RFI 017 response.
18 | Montana Tech | Are we using the pump pour rates given on the redimix subcontractors, or do we assume our own pour rates? | The placing rates for concrete vary based on multiple factors including the form system used, how it is configured, and the scope of concrete placed in the pour shift.
19 | Virginia Tech | Should demobilization be included in our schedule? Specifically with the crane chosen for the work?? Or will any cranes or site equipment remain for other trades on the project? Please advise. | During construction of this Project, the Sundt Building Group carried the crane rental because several other scopes required it's availability, namely structural steel. For the purpose of this exercise, the crane is to be assumed as needed ONLY for structural concrete. Plan accordingly.
20 | Montana Tech | Is it possible to obtain a variance from the Client to perform work at night? | In order to request a variance from the Owner, please prepare a noise abatement plan, and detail the scope of work requested and the working hours desired.