CBU Kugel Fountain Project

Equipment room:

Sump pit Design from Rick engineering?

Remove reservoir water.

Remove reservoir.

Remove pump, filter, and equipment skid.

Install sump pit for new Reservoir.

Install new Reservoir.

Install new pump, filter, and piping. (Collins Plumbing and AJ Kirkwood Electric)

Kugel removal date?

Demo concrete adjacent to kugel.

Excavate under base to disconnect piping.

Cut threaded rods, make ready for existing Kugel to be removed.

Remove existing Kugel. Move to maintenance yard. (Corovan)

Test existing piping. Check existing foundation for reuse.

Reuse piping or replace.

Reuse foundation or replace

New Kugel arrival date?

Install new Kugel:

Move Kugel into position, set and shim to level. (Corovan)

Connect piping.

Start up equipment/Kugel, test/adjust

Backfill underground piping and foundation

Pour back flatwork.