Project: App-Side Down

List of Estimate Changes:

- Fire Alarm:

  - Initial estimate: missing fire alarm rough-in.

  - Final Estimate: Include fire alarm rough in take-off. Value: <$165,000>

- A/V Sub:

  - Initial estimate: AV was excluded in the scope letter as directed in RFI responses.  Sub costs included in subcontracts.

  - Final Estimate: Delete sub costs

Value: $98,172

- Coring:

  - Initial estimate- Coring cost included in subcontracts and then doubled up in the body of the estimate.

  - Final estimate- Delete coring from the body of the estimate.

Value: $30,000

- Quoted Material:

| Initial Estimate | Final Estimate |
| --- | --- |
| Distribution: Square D - $31,457 | Distribution: Eaton - $36,510 |
| Lighting: Wesco - $310,278 | Lighting: CED - $328,861.30 |
| Lighting Control: Plug - $30,000 | Lighting Control: CED - $40,872 |

- Overtime:

  - Initial estimate OT- None included.

  - Final estimate OT-250 hours of Foreman time and a half, and 420 of Journeyman time and a half.

Value:  <$82,500>

- Direct Labor

  - Initial estimate Crew Mix- (1) Foreman only

  - Final Estimate Crew Mix- (1) Foreman (2) Journeyman and (1) Apprentice

  - Initial estimate Rates- Local 6

  - Final Estimate Rates- Local 617

Value: $105,000

- Sales tax:

  - Initial estimate: 8% sales tax

  - Final estimate: 8.5% sales tax.

Value:  <$300>