## HOJ Design Deviations Tracker
Historic Cost Delta Matrix
Item Number | Issue | Area | Discipline | Scoping Document Requirements | Proposed Scope | Priority (High, Medium, Low) | Subcontractor Cost (does not include mark-up) | Responsible Party | Sheet | Comment By | Date sent to ACMP | Correspondence / RFI | Addressed by ACMP | Reason | Resolution or Decision
Exterior items
Example | New copper cap flashing. | HOJ | Historic | Scoping Documents do not contain a requirement to add cap flashing to the existing copper roof. | This unforeseen work is necessary per the observation in the WJE report. May be able to replace only damaged portions, but not recommended. | Medium | 104011 | DPW
1 | Façade cleaning with less aggressive, non-damaging product/method. | HOJ | Historic | Scoping Documents call for the use of Prosoco Sure Klean for granite and terra cotta. | For cleaning exterior surfaces, the Design-Build specs call for less aggressive methods than were in the original scoping documents. This has the potential to cause a cost increase in the required cleaning for all exterior surfaces. |  |  |  |  | HH | 2012-06-20 |  | Cleaning to 100% may be desired by County, but it violates Standards, which recommend 85%. County should direct us NOT to follow standards. Use of less aggressive cleaning may be able to get to 85% without adding cost, especially if less aggressive cleaners do not require masking, containment, or special clean-up. | Preservation, Damage | Additional Mock-ups to be performed. Design team to identify 3 producs to be used and outline a specific mock-up procedure for each product.
2 | Cleaning/Restoration of the Exterior Metal Window Grilles between the upper and lower copper roof. | HOJ | Historic | Restoration of the metal grilles between the upper and lower copper roof is not addressed in Scoping. Major repair or replacement of metal grilles could be seen as an unforeseen condition. | Recommend clean and coat in place to prevent further deterioration. Inform DPW that water can come into the building through these openings but the openings may be necessary so as not to trap moisture. |  |  |  | HA-301-304 | RS | 2012-06-20 |  | Clean and coat in place to prevent further deterioration is acceptable. DPW should be informaed that water can come into the building through these openings but the openings may be necessary so as not to trap moisture. Suggest closing off the floor openings in this space to prevent water migration into the building. | Preservation Practice, Weatherproofing | Grilles to be cleaned and coated in-place. Clark to request a breakout price during with bid.
3 | Repair chipped light court brick and exterior granite as necessary | HOJ | Historic | Scoping Documents do not address chipped bricks or granite outside of those areas known to be replaced. | Recommend use helifix anchors to make repairs as necessary. Small chips to be ignored. DB team to provide parameters for bidders regarding size of spall to be repaired. Estimated quantity to be provided by DB team. |  |  |  | HA-309 | HH | 2012-06-20 |  | scoping is silent. Chipped off pieces could be ignored; pieces that will fall off may be adhered, but a poor long-term solution. Cost? |  | WJE to provide size perameters and Estimated Qty. BL&A to revise detail.
4 | Replace light court brick where bars were removed. | HOJ | Historic | Scoping Documents do not address the replacement of brick where metal bars were removed. | Repair of this brick is impractical. DB documents call for replacement of units where bars were removed from upper floors instead of patching. |  |  |  | HA-308 | HH | 2012-06-20 |  | Glazed brick can not be patched, replacement is necessary. Cost? |  | Bricks are to be replaced.
5 | Structural integrity of the existing copper roof anchorage/attachment. | HOJ | Historic | Scoping Documents do not contain a requirement to demonstrate/test the structural integrity of the copper roof. | Note in specifications to have roof repair/clean contractor to call to the owners attention any signs of deterioration or structural weakness, but no investigation. |  |  |  | HA-210 | HH | 2012-06-20 |  | Note in specifications to have roof repair/clean contractor to call to the owners attention any signs of deterioration or structural weakness, but no investigation. | Hazard, Deterioration, waterproofing | WJE to perform futher analysis/investigation during construction.
6 | Remove, fabricate and install new terra cotta pieces. | HOJ | Historic | Scoping Documents call for the placement of stainless steel rods to secure the balustrade, but does not address the need to replace significant amounts of damaged terra cotta. | Recommend removal, fabrication and installation of approximately 42 full and 16 half deteriorated balusters w/ new terra cotta. Remove and reinstall 250 lintel and jamb terra cotta pieces. Fabricate 100 lintel and jamb terra cotta pieces. Clark to request a breakout price from the bidders for this scope of work. |  |  |  | HA-210 | HH | 2012-06-20 |  | See WJE report. Unforeseen condition? This is an estimate baed on 10% typically observed damaged. Falling Hazard can not be ignored. Stainless steel pins called for by scoping are not necessary, credit to offset cost? | Hazard, Preservation | Note is to remain in the Documents. Clark to request a breakout from bidders as well as unit pricing. WJE to create a replacement detail.
7 | Perform dutchman repairs on granite |  |  | Scoping Documents do not indicate the numerous holes in the grante that will require repair. | Most of the holes can be patched and filled. This is included in base bid. Until a complete investigation is performed, we assumed additional 100 dutchman repairs for holes that require this type of correction.
8 | Provide Different Interior and Exterior Paint on Historic Windows | HOJ | Historic | Scoping Documents do not call of separate paint colors of the interior vs. the exterior of the windows. | Recommend that an interior and exterior paint color be used. |  |  |  | HA-214 | HH | 2012-06-20 |  | Glazing replacement can be removed. Caulking glass in place is not recommended, replace deteriorated putty instead. Faux Finish can be an Add and only in a few locations. Only the Jail floors windows that must be operable for smoke need to be refurbished. | Waterproofing, Preservation | Perimeter of windows to receive sealant at perimeter of frame; Use putty in leiu of sealant at each pane of glass - loose and deteriorated glazing putty to be removed and replaced with new glazing putty (hardened putty to be left in place); Remove from documents all requirements for corrosion converter (unless specified period of time has elapsed), gaskets, faux finish, repair of cables/pulleys/counter weights, removal of all glazing stops, glazing, etc.
9 | Caulk and seal all upward facing joints | HOJ | Historic | Scoping Documents call for 20% joint repointing for all exterior granite and terra cotta joints. No sealant is required beyond typical grouted joints. | Added backer rod, caulk and seal for all upward facing joints as well as all bullnose to ashlar joints. This is beyond the specified 20% repointing and adds a sealant requirement for these specific joints. |  |  |  | HA-200 and 210 | HH | 2012-06-20 |  | Is the additional cost for caulk intstead of mortar, or for 80%, or? | Waterproofing, Preservation | Remove this note from the documents. Clark will request Add/Alternate from bidders.
10 | Repoint 50% of all granite and terra cotta joints | HOJ | Historic | Scoping Documents call for 20% joint repointing for all exterior granite and terra cotta joints. | County request to price 50% repointing based on WJE recommendation to repoint entire façade |  |  |  | HA-200 | HH | 2012-06-20 |  | County wants to have 20,50, and 100% priced. Adjust documents to make this clear? | Waterproofing, Preservation | Remove this note from the documents. Per County direction, Bidders will provide pricing for 20%, 50%, 100% repointing.
11 | Repoint 100% of all granite and terra cotta joints |  |  | Scoping Documents call for 20% joint repointing for all exterior granite and terra cotta joints. | County request to price 100% repointing based on WJE recommendation to repoint entire façade
Interior Items
1 | Perform investigation of Broadway Entrance "sagging" |  |  | Scoping Documents do not address any repairs required at the Broadway entrance | Recommend performing an investigation to determine the cause of the sagging. Additional costs may be necessary to address the source of the problem
2 | Remove coating from Grand Loggia stone walls |  |  | Scoping Documents call for the marble wall panel to be cleaned. | Recommend stripping the applied coating from the stone wall panels.
3 | Decorative Painting in Courtroom |  |  | Scoping Documents do not address the decorative paint | Recommend performing additional investigation to determine the paint pattern and then determine if restoration/recreation is desired by DPW.
4 | Flooring in Courtroom and Jury room |  |  | Scoping Documents call for new cork floors in the Courtroom and Jury Room | Recommend DPW consider carpet in these rooms to assist in the acoustics
5 | Chemically strip and reseal stone floors and stair treads ILO grinding. |  |  | Scoping Documents call for use of 300-400 grit grind on existing stone floors and stair treads. | Historic team suggests a less aggressive method to restore these terrazzo floors.
6 | Chemically strip and reseal terrazzo floors ILO grinding. |  |  | Scoping Documents call for use of 300-400 grit grind on existing terrazzo floors. | Historic team suggests a less aggressive method to restore these stone floors.
7 | Remove oxidized coating from Historic Stair balustrades to reveal gold finish | HOJ | Historic | Scoping Documents call for the cleaning only. | Apply cleaning compound that will reveal but not damage the gold finish on the balustrades of each of the historic stairs. | [5 empty] | 2012-06-20 |  | This is clearly a change. Just needs to be priced separately as an Add Alternate. |  | BL&A to have include in the specs a procedure for revealing the gold finish. However, this is to be clearly identified in the documents as an Add/Alternate.
8 | Enhanced Lighting Scope |  |  | Scoping Documents call for specific restoration and lighting requirements for each fixture. | Per RFIs 30.1, 33.1, 85, 86 an 87, the Design-Build team recommends enhancements to the specified lighting, particularly related to historic lobbies/entrances. | [9 empty] | Code Lighting - Continue Pricing
9 | Retention of Plaster Walls in Jury Room |  |  | Scoping Documents call for removal of HCT which would dictate that the plaster is new. | Because the HCT walls will remain in place, it may be possible to leave the plaster and restore it. Until the plaster is investigated, a price delta cannot yet be determined
TOTAL
Notes: | Consider the visability of the component when assigning priorities.
Consider compliance with the Secretary of the Interiors Standards when determining treatment methods.
When calculating costs, begin with assumed unit pricing and apply to total area.