## Sheet1
Issue Resolution Log
Item | Date Generated | Requested By | Priority | Item Description | Affected Task | Responsible Party | Original Commitment Date | Revised Commitment Date | Actual Close Date | Resolution / Comments
1 | 2016-11-05 | Owner - GZ | 1 | Project team to develop team charter & mission statement. | Team Integration | GC | 2016-11-30 | 2017-02-09
2 | 2016-11-05 | Owner - GZ | 1 | Team communication is inadequate. Provide co-location plan with consideration of team members, office layout, Big Room Concept, meeting plan, and posted metrics. | Team Integration | GC | 2016-11-30 | 2017-02-09
3 | 2016-11-05 | Owner - FC | 2 | Need site utilization plan to share with Campus operations showing truck access, parking, equipment plan, hoisting plan, dust and sound mitigation, re-routing of student traffic, security, utilities, and temp facilities. | NTP | GC | 2017-01-20 | 2017-02-09
4 | 2016-11-10 | GC | 2 | Will the building obtain chilled water from the central plant? | Mechanical Design | Owner | 2016-11-15 | 2016-11-15 | 2016-11-14 | Yes. Chilled water will be provided from the central plant.
5 | 2016-11-21 | Mech | 1 | Need to set a consistent time for full team Big Room meeting. | Planning | Owner | 2016-11-30 | 2016-11-30 | 2016-11-25 | Team to meet on Tuesdays 10:00 to 2:00. Pizza to be provided.
6 | 2016-11-25 | GC | 1 | To support the creation of the team charter the team needs to get to know each other better. | Creation of team Charter | Architect | 2016-11-30 | 2016-12-05 | 2016-12-06 | Project team to have pizza party every Monday.
7 | 2016-12-04 | Architect | 2 | Need to determine which buidling elements are to be designed as multiple options via a set based design process. Recommend no more than two elements due to resource constraints. Provide rational for estimate and constructability study. | Design Estimate | GC | 2016-12-14 | 2017-02-09
8 | 2016-12-05 | Architect | 1 | Provide recommendation to use concrete or steel structure. | Structural Design | GC | 2017-01-10 | 2017-02-09
9 | 2017-01-03 | Owner- KG | 1 | OFOI equipment has utility requirements that are not accounted for in the design. | Structural Design / MEP infrastructure | Owner/GC | 2017-02-01 | 2017-02-01 | 2017-01-31 | GC set deadline for ownership to prevent late OFOI changes. Big room approach to design allowed for incorporation of changes without going over university budget and no schedule impact.
10 | 2017-01-10 | Owner - FC | 1 | Project schedule with adequate detail to monitor progress towards project completion has not been developed. Needs to include the plan for design deliverables, procurement, and major construction activities. | Design/Construction/Procurement | GC | 2017-01-31 | 2017-02-09
11 | 2017-01-12 | Owner - WB | 1 | The fire marshall has indicated that there are two projects that are behind schedule in their review queue. They are concerned that they may not have the capacity to review this project until January 2018. Need to develop a design packaging strategy to allow for the Fire Marshall to review smaller components over a greater period of time. | Permitting | Architect | 2017-02-05 | 2017-02-09
12 | 2017-01-15 | Owner - RZ | 1 | The project estimate dated 1/10/17 is above the Allowable Cost for the project. Need to develop options to bring the estimate in line with the Allowable Cost. | Design | GC/Arch/TP's | 2017-01-31 | 2017-02-09
13 | 2017-01-20 | Owner - GZ | 2 | As the project team grows the shared purpose, values, and culture of the project must be conveyed. Prepare a five minute on-boarding presentation for new team members (that does not involve pizza). | Team Building | GC | 2017-02-01 | 2017-02-09
14 | 2017-02-05 | Owner - WB | 3 | Trustee has requested that team consider a modern glass and steel main entry to the building. Please provide a high level cost and design study. | Final funding approval | Architect/GC | 2017-02-09 | 2017-02-09