## Sheet1
Issue Resolution Log
Item | Date Generated | Requested By | Priority | Item Description | Affected Task | Responsible Party | Original Commitment Date | Revised Commitment Date | Actual Close Date | Resolution / Comments
1 | 2017-05-01 | O | 1 | Project team to develop team charter & mission statement. |  | AE/GC/TP/O | 2017-06-01 | 2018-02-08 |  | To be completed at meeting with Clark scheduled for 9:00am.
2 | 2017-05-01 | O | 2 | Formulate a process to capture lessons learned and rapidly implement on project to improve production, quality, and/or safety. |  | AE/GC/TP | 2017-06-01 | 2018-02-08
7 | 2017-05-01 | O | 1 | Develop site utilization plan showing truck access, parking, equipment plan, hoisting plan, dust and sound mitigation, security, utilities, and temp facilities. As part of the plan consider when the plaza should be excavated. Provide recommendations for crane and hoist locations based on your shoring design and site logistics plans. |  | GC/TP | 2018-07-15 | 2018-02-08
12 | 2017-07-01 | O | 1 | Schedule with adequate detail to monitor progress towards project completion has not been developed. Needs to include the plan for procurement and major construction activities. |  | GC | 2017-08-01 | 2017-08-01 | 2017-08-15 | Accepted, although weak on detail.
17 | 2017-08-16 | O | 1 | To support the leasing program and a St Patrick's Day marketing event, the job must be accelerated to achieve a TCO date of March 16, 2020. Provide an accelerated schedule (more detailed than current schedule) to achieve new TCO date. Identify what costs should be added to the estimate. Choose an appropriate schedule format (ie. CPM, SIPS, LPS, etc) to communicate the plan. |  | GC | 2017-09-16 | 2018-02-08
28 | 2017-08-17 | AE | 1 | After reviewing the plan for working on multiple LBEs at the same time, the geotechnical engineer has implemented a new restriction that the shaft can only be open for 36 hours. This requires you to only work on one hole at a time start to finish. Develop a plan for completing the LBEs in the original duration with this new time constraint. |  | GC | 2017-12-01 | 2017-12-15 | 2017-12-21 | Plan submitted and approved
35 | 2017-09-20 | AE | 2 | When building a high rise, material deliveries/hoisting are critical to the flow of the job. Provide a floor loading plan for a typical floor that includes all items that need to be stocked prior to the unitized curtainwall deliveries. |  | GC/TP | 2017-10-01 | 2018-02-08
41 | 2018-02-01 | O | 1 | The project estimate dated 01/31/18 was incomplete and was trending above the Target Cost. Complete the estimate and provide detailed backup for your work. |  | GC/TP | 2018-02-08 | 2018-02-08
42 | 2018-02-01 | O | 1 | The project estimate has been trending above the Target Cost. Provide options to reduce cost by $5M. |  | GC/AE/TP | 2018-02-06 | 2018-02-08
50 | 2018-02-01 | O | 1 | A prospective high rent tenant has requested a private entrance. Provide a schematic high and low cost option, with ROM cost and TIA analysis for each option. |  | GC/AE/TP | 2018-02-06 | 2018-02-08
53 | 2018-02-01 | O | 1 | It is anticipated that two or three shifts may be required to meet the project schedule. Identify associated risks and develop coutermeasures. |  | GC/AE/TP | 2018-02-08 | 2018-02-08
65 | 2018-02-07 | O | 2 | The safety of the workers and the public is a project priority. The team is about to begin the erection of the tallest building ever constructed in SF. Prepare a one minute safety statement to be delivered to the workers during the "Bottoming-Out Event" along with a logo for the t-shirt. Present during the OAC meeting on 2/9/18. |  | GC | 2018-02-08 | 2018-02-09

## Sheet2
Division 1