## Sheet1
SALESFORCE TOWER
SCHEDULE SUMMARY
FEBRUARY 2018
[27 empty] | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
SUMMARY ACTIVITIES | Weeks | Hourly rate | Weekly rate | Total | start | end | Months | orig budget/KPI | diff | Vehicle | Computer | Phone | time axis 2013-07-14 to 2020-08-01
TO BOTTOM OF HOLE
O Cell | bar: 2013-11-13
LBEs | bar: 2013-12-13 to 2014-03-14
CDSM/ Haz/ Shoring / Excav | bar: 2013-10-13 to 2013-11-13; 2014-04-14 to 2018-03-01
Mud / Mat slab | bar: 2018-04-01 to 2018-05-01
STRUCTURAL
Concrete core | bar: 2018-06-01 to 2019-06-01
Parking garage | bar: 2018-06-01 to 2019-01-01
Structural steel | bar: 2018-08-01 to 2019-06-01
Metal decks | bar: 2018-09-01 to 2019-08-01
P1/P2 Level Garage | bar: 2019-03-01 to 2019-10-01
EXTERIOR
Curtain Wall | bar: 2018-11-01 to 2019-10-01
Site work | bar: 2018-11-01 to 2019-10-01
INTERIOR
MEP rough in | bar: 2018-11-01 to 2019-12-01
Finishes | bar: 2018-11-01 to 2020-04-01
Elevators | bar: 2019-01-01 to 2020-06-01
Testing & Commissioning | bar: 2019-12-01 to 2020-06-01
FOUNDATION ELEMENTS (LBEs) | bar: 2014-07-14 to 2018-02-01
O Cell Test (COMPLETE)
Production Load Bearing Elements (COMPLETE)
Demobilize LBE / Mobilize Shoring | bar: 2018-02-01
Excavation and shoring | bar: 2018-03-01 to 2018-09-01
Mat Slab | bar: 2018-09-01 to 2018-12-01
Core Walls | bar: 2018-12-01 to 2019-11-01
Complete Structural Steel on occupiable floors | bar: 2019-12-01 to 2020-01-01
Ready Penthouse | bar: 2020-01-01 to 2020-02-01
Complete Service Elevators | bar: 2020-02-01 to 2020-05-01
Interior Buildout | bar: 2019-04-01 to 2020-06-01
Hoist Bay | bar: 2020-04-01 to 2020-05-01
Inspections /TCO | bar: 2020-06-01 to 2020-07-01
Substantial Completion | bar: 2020-08-01
*** BE ADVISED THAT ALL TIME FRAMES LISTED ABOVE ARE SUBJECT TO CHANGE