## SDSU
Chase Center Arena and Mixed Use Retail
Target Budget $860,000,000
| Division | Description | Budget | Projected Final | Projected Gain/Loss
1 | Div 01 | General Conditions | 60000000 | 60000000 | 0
2 | Div 02 | Sitework | 15000000 | 15000000 | 0
3 | Div 03 | Concrete | 150000000 | 150000000 | 0
4 | Div 04 | Masonry | 6000000 | 6000000 | 0
5 | Div 05 | Metals | 60000000 | 70000000 | -10000000
6 | Div 06 | Wood and Plastics | 7000000 | 7000000 | 0
7 | Div 07 | Moisture Thermal Control Total | 22000000 | 22000000 | 0
8 | Div 08 | Doors, Windows and Glass Total | 68000000 | 68000000 | 0
9 | Div 09 | Finishes Total | 18000000 | 26000000 | -8000000
10 | Div 10 | Specialties Total | 1500000 | 1500000 | 0
11 | Div 11 | Equipment Total | 20000000 | 20000000 | 0
12 | Div 12 | Furnishings Total | 8000000 | 8000000 | 0
13 | Div 14 | Conveying Systems Total | 14000000 | 14000000 | 0
14 | Div 21-23 | Mech, Plumbing, Fire Total | 120000000 | 120000000 | 0
15 | Div 26-28 | Electrical & Low VoltageTotal | 95000000 | 100000000 | -5000000
16 | Other | Neolith Installer Bankruptcy | 0 |  | 0
17 | Other | Bass Trap Design Exposure | 0 |  | 0
18 | Other | Installed Finished Impacted by Design | 0 |  | 0
19 | Other | Thrive City Steel Exposure | 0 |  | 0
20 | Other | Thanksgiving Water Impacts | 0 |  | 0
21 | Other | Mold Impacts to Electrical Scope | 0 |  | 0
22 | Other | Exterior Vapor Barrier Meltdown | 0 |  | 0
23 |  | Owner Allowances | 160000000 | 160000000 | 0
24 |  | Contingency | 13500000
25 |  | Fee | 22000000
26 | Total |  | 860000000 | 847500000
D29 + E29 = F29