## Important Instructions
Take-off & Pricing Workbook Instructions
1 | Pay close attention to shop welds and field welds
2 | Read pop-up notes in column headers
3 | Only takeoff piping activities that are included in the drop-down menu
4 | Take-off all welds as butt welds
5 | Drawings included in the pipe takeoff were completed by a previous estimator. They are a gift. We do NOT recommend redoing the takeoff of those isos
6 | Assume that all pipe will be provided to you from the vendor in DRLs (40'-0" +/- long)
7 | Pre-fabrication in your Sacramento shop will dictate that 40' +/- is the longest spool you can pre-fabricate without needing a permitted oversize load
8 | "Price Proposal Sheet" tab and Gen Conditions tab MUST be printed and placed in your deliverables binder. Failure to do so may result in not receiving a score for that section
9 | Assume all piping is carbon steel and standard weight
10 | Plan for a minimum of 75% welds prefabricated in the shop to take advantage of welding productivity
11
12
13
14
15
16
17
18
19
20

## Price Proposal Sheet
Project Name: North Energy Renewables Terminal Expansion
Project Description: Piping Installation
Project Location: Stockton, CA
Shop Fabrication
Labor | Total Hrs | Total Dollars
Direct | 4488.2722 | 439158.5018
Indirect | 320 | 25600
| 4808.2722 | 464758.5018
Field Installation
Labor | Total Hrs | Total Dollars
Direct | 5985.3027 | 559639.2446
Pressure Testing | 473.3689 | 44404.3423
Indirect | 3389.28 | 300398.4
| 9847.9517 | 904441.9868
HDD Preassembly & Assistance
Labor | Total Hrs | Total Dollars
Direct | 2720 | 373451.3503
Pressure Testing | 260 | 24389.2829
Indirect | 1522.72 | 134961.6
| 4502.72 | 532802.2332
Subcontractors | N/A | Dollars
Paint | n/a | 524700.45
HDD | n/a | 1143200
NDE | n/a | 98800
Recap | Hours | Dollars
Labor (Direct) | 13926.9439 | 1441042.7219
Labor (Indirect) | 5232 | 460960 | 27.31%
Material | n/a | 230002.4694
Equipment/Tools | n/a | 81040
Subcontractors | n/a | 1766700.45
Total | 19158.9439 | 3979745.6414
Profit & Overhead | 15% | 596961.8462
PF Shop Crew Rate (composite $ per MH) | 97.8458
PF Field Crew Rate (composite $ per MH) | 93.8049

## Gen Conditions
Project Name: | North Energy Renewables Terminal Expansion
Project Description: | Piping Installation
Project Location: | Stockton, California
Description | # of People | Days | Hours Per Shift | Total Hours | Rate | Total Costs | Important Notes
Safety Supervision | 1 | 60 | 8 | 480 | 75 | 36000
Safety Training/Orientation | 28 | 1 | 4 | 112 | 80 | 8960 | est. 4 hrs per person
Project Management | 1 | 100 | 8 | 800 | 100 | 80000
General Foreman | 1 | 60 | 8 | 480 | 100 | 48000
Clerical |  |  |  | 0 | 50 | 0
Field Engineering |  |  |  | 0 | 60 | 0
Superintendent | 1 | 80 | 8 | 640 | 120 | 76800
Project Scheduler | 1 | 20 | 8 | 160 | 90 | 14400
Document Control |  |  |  | 0 | 50 | 0
Non Working Foreman |  |  |  | 0 | 100 | 0
Detailing | 1 | 10 | 8 | 80 | 100 | 8000
Welder Testing/Qualification | 10 | 1 | 8 | 80 | 80 | 6400
QC Supervision | 2 | 100 | 8 | 1600 | 80 | 128000
Material Receiving/Control Crew | 1 | 30 | 8 | 240 | 80 | 19200
Mobilization | 4 | 5 | 8 | 160 | 80 | 12800
Cleaning | 1 | 60 | 4 | 240 | 40 | 9600
Demobilization | 4 | 5 | 8 | 160 | 80 | 12800
Other Miscellanous: |  |  |  | 0 | 75 | 0
0
0
|  |  | Total | 5232 |  | 460960

## Pipe Take-Off
TAKE OFF # | ACTIVITY | SIZE 1 | SIZE 2 | RATING | INSTALL QUANT | PURCH QUANT | LINE # | AREA | Special Sched | INSULATION | Pressure Test | PAINT | S/F | COMMENTS OR NOTES | SHOP LABOR UNIT | SHOPLABOR ADJ FACTOR | SHOP LABOR TOTAL | FIELD LABOR UNIT | FIELD LABOR ADJ FACTOR | FIELD LABOR TOTAL | MAT'L UNIT PRICE | MAT'L TOTAL
1 | PIPE HANDLING | 10 |  |  | 5.1 | 5.1 | STOT-10"-RD-354-A SH1 | TERMINAL |  |  | Y |  | S/F |  | 0.44 | 1 | 2.244 | 0.66 | 1 | 3.366 | 21 | 107.1 | ACTIVITY LIST
2 | SHOP BUTT WELD | 10 |  |  | 3 |  | STOT-10"-RD-354-A SH1 | TERMINAL |  |  | Y |  | S |  | 3.96 | 1 | 11.88 |  | 1 | 0 |  | 0 | PIPE HANDLING
3 | FIELD BUTT WELD | 10 |  |  | 1 |  | STOT-10"-RD-354-A SH1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 5.94 | 1 | 5.94 |  | 0 | PIPE SUPPORT
4 | SHOP BUTT WELD | 2 |  |  | 2 |  | STOT-10"-RD-354-A SH1 | TERMINAL |  |  | Y |  | S |  | 1.2 | 1 | 2.4 |  | 1 | 0 |  | 0 | TYPE 1 FOUNDATION
5 | BOLT UP | 10 |  | 150 | 1 |  | STOT-10"-RD-354-A SH1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 1.35 | 1 | 1.35 |  | 0 | TYPE 2 FOUNDATION
6 | BOLT UP | 2 |  | 150 | 2 |  | STOT-10"-RD-354-A SH1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.39 | 1 | 0.78 |  | 0 | BOLT UP
7 | PIPE HANDLING | 10 |  |  | 7.1 | 7.1 | STOT-10"-RD-355-A SH1 | TERMINAL |  |  | Y |  | S/F |  | 0.44 | 1 | 3.124 | 0.66 | 1 | 4.686 | 21 | 149.1 | SHOP BUTT WELD
8 | SHOP BUTT WELD | 10 |  |  | 4 |  | STOT-10"-RD-355-A SH1 | TERMINAL |  |  | Y |  | S |  | 3.96 | 1 | 15.84 |  | 1 | 0 |  | 0 | FIELD BUTT WELD
9 | SHOP BUTT WELD | 2 |  |  | 2 |  | STOT-10"-RD-355-A SH1 | TERMINAL |  |  | Y |  | S |  | 1.2 | 1 | 2.4 |  | 1 | 0 |  | 0
10 | FIELD BUTT WELD | 10 |  |  | 1 |  | STOT-10"-RD-355-A SH1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 5.94 | 1 | 5.94 |  | 0
11 | BOLT UP | 10 |  | 150 | 1 |  | STOT-10"-RD-355-A SH1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 1.35 | 1 | 1.35 |  | 0
12 | BOLT UP | 2 |  | 150 | 2 |  | STOT-10"-RD-355-A SH1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.39 | 1 | 0.78 |  | 0
13 | PIPE HANDLING | 10 |  |  | 35.9 | 35.9 | STOT-10-RD-363-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.44 | 1 | 15.796 | 0.66 | 1 | 23.694 | 21 | 753.9
14 | PIPE HANDLING | 6 |  |  | 3 | 3 | STOT-10-RD-363-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.29 | 1 | 0.87 | 0.44 | 1 | 1.32 | 16.5 | 49.5
15 | SHOP BUTT WELD | 10 |  |  | 7 |  | STOT-10-RD-363-A SH 1 | TERMINAL |  |  | Y |  | S |  | 3.96 | 1 | 27.72 |  | 1 | 0 |  | 0
16 | SHOP BUTT WELD | 6 |  |  | 4 |  | STOT-10-RD-363-A SH 1 | TERMINAL |  |  | Y |  | S |  | 2.48 | 1 | 9.92 |  | 1 | 0 |  | 0
17 | FIELD BUTT WELD | 10 |  |  | 1 |  | STOT-10-RD-363-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 5.94 | 1 | 5.94 |  | 0
18 | BOLT UP | 10 |  | 150 | 1 |  | STOT-10-RD-363-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 1.35 | 1 | 1.35 |  | 0
19 | BOLT UP | 1 |  | 150 | 4 |  | STOT-10-RD-363-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.39 | 1 | 1.56 |  | 0
20 | BOLT UP | 6 |  | 150 | 2 |  | STOT-10-RD-363-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.86 | 1 | 1.72 |  | 0
21 | PIPE SUPPORT | 10 |  |  | 4 | 4 | STOT-10-RD-363-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 5.5 | 1 | 22 | 5.5 | 1 | 22 | 200 | 800
22 | PIPE HANDLING | 10 |  |  | 82.9 | 82.9 | STOT-10-RD-363-A SH 2 | TERMINAL |  |  | Y |  | S/F |  | 0.44 | 1 | 36.476 | 0.66 | 1 | 54.714 | 21 | 1740.9
23 | SHOP BUTT WELD | 10 |  |  | 6 |  | STOT-10-RD-363-A SH 2 | TERMINAL |  |  | Y |  | S |  | 3.96 | 1 | 23.76 |  | 1 | 0 |  | 0
24 | FIELD BUTT WELD | 10 |  |  | 2 |  | STOT-10-RD-363-A SH 2 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 5.94 | 1 | 11.88 |  | 0
25 | PIPE SUPPORT | 10 |  |  | 4 | 4 | STOT-10-RD-363-A SH 2 | TERMINAL |  |  | Y |  | S/F |  | 5.5 | 1 | 22 | 5.5 | 1 | 22 | 200 | 800
26 | PIPE HANDLING | 10 |  |  | 30.5 | 30.5 | STOT-10-RD-363-A SH 3 | TERMINAL |  |  | Y |  | S/F |  | 0.44 | 1 | 13.42 | 0.66 | 1 | 20.13 | 21 | 640.5
27 | SHOP BUTT WELD | 10 |  |  | 3 |  | STOT-10-RD-363-A SH 3 | TERMINAL |  |  | Y |  | S |  | 3.96 | 1 | 11.88 |  | 1 | 0 |  | 0
28 | FIELD BUTT WELD | 10 |  |  | 1 |  | STOT-10-RD-363-A SH 3 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 5.94 | 1 | 5.94 |  | 0
29 | PIPE SUPPORT | 10 |  |  | 1 | 1 | STOT-10-RD-363-A SH 3 | TERMINAL |  |  | Y |  | S/F |  | 5.5 | 1 | 5.5 | 5.5 | 1 | 5.5 | 200 | 200
30 | PIPE HANDLING | 10 |  |  | 67.3 | 37.3 | STOT-10-RD-363-A SH 4 | TERMINAL |  |  | Y |  | S/F |  | 0.44 | 1 | 29.612 | 0.66 | 1 | 44.418 | 21 | 783.3
31 | PIPE HANDLING | 1 |  |  | 0.25 | 0.25 | STOT-10-RD-363-A SH 4 | TERMINAL |  |  | Y |  | S/F |  | 0.07 | 1 | 0.0175 | 0.11 | 1 | 0.0275 | 6.5 | 1.625
32 | SHOP BUTT WELD | 10 |  |  | 10 |  | STOT-10-RD-363-A SH 4 | TERMINAL |  |  | Y |  | S |  | 3.96 | 1 | 39.6 |  | 1 | 0 |  | 0
33 | SHOP BUTT WELD | 1 |  |  | 2 |  | STOT-10-RD-363-A SH 4 | TERMINAL |  |  | Y |  | S |  | 0.6 | 1 | 1.2 |  | 1 | 0 |  | 0
34 | FIELD BUTT WELD | 10 |  |  | 5 |  | STOT-10-RD-363-A SH 4 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 5.94 | 1 | 29.7 |  | 0
35 | PIPE SUPPORT | 10 |  |  | 6 | 6 | STOT-10-RD-363-A SH 4 | TERMINAL |  |  | Y |  | S/F |  | 5.5 | 1 | 33 | 5.5 | 1 | 33 | 200 | 1200
36 | PIPE HANDLING | 10 |  |  | 5.9 | 5.9 | STOT-10-RD-363-A SH 5 | TERMINAL |  |  | Y |  | S/F |  | 0.44 | 1 | 2.596 | 0.66 | 1 | 3.894 | 21 | 123.9
37 | SHOP BUTT WELD | 10 |  |  | 8 |  | STOT-10-RD-363-A SH 5 | TERMINAL |  |  | Y |  | S |  | 3.96 | 1 | 31.68 |  | 1 | 0 |  | 0
38 | PIPE HANDLING | 10 |  |  | 48 | 48 | STOT-10-RD-363-A SH 6 | TERMINAL |  |  | Y |  | S/F |  | 0.44 | 1 | 21.12 | 0.66 | 1 | 31.68 | 21 | 1008
39 | SHOP BUTT WELD | 10 |  |  | 3 |  | STOT-10-RD-363-A SH 6 | TERMINAL |  |  | Y |  | S |  | 3.96 | 1 | 11.88 |  | 1 | 0 |  | 0
40 | FIELD BUTT WELD | 10 |  |  | 1 |  | STOT-10-RD-363-A SH 6 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 5.94 | 1 | 5.94 |  | 0
41 | PIPE SUPPORT | 10 |  |  | 6 | 6 | STOT-10-RD-363-A SH 6 | TERMINAL |  |  | Y |  | S/F |  | 5.5 | 1 | 33 | 5.5 | 1 | 33 | 200 | 1200
42 | PIPE HANDLING | 10 |  |  | 94.9 | 94.9 | STOT-10-RD-363-A SH 7 | TERMINAL |  |  | Y |  | S/F |  | 0.44 | 1 | 41.756 | 0.66 | 1 | 62.634 | 21 | 1992.9
43 | SHOP BUTT WELD | 10 |  |  | 1 |  | STOT-10-RD-363-A SH 7 | TERMINAL |  |  | Y |  | S |  | 3.96 | 1 | 3.96 |  | 1 | 0 |  | 0
44 | FIELD BUTT WELD | 10 |  |  | 3 |  | STOT-10-RD-363-A SH 7 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 5.94 | 1 | 17.82 |  | 0
45 | PIPE SUPPORT | 10 |  |  | 5 | 5 | STOT-10-RD-363-A SH 7 | TERMINAL |  |  | Y |  | S/F |  | 5.5 | 1 | 27.5 | 5.5 | 1 | 27.5 | 200 | 1000
46 | PIPE HANDLING | 10 |  |  | 29.25 | 29.25 | STOT-10-RD-363-A SH 8 | TERMINAL |  |  | Y |  | S/F |  | 0.44 | 1 | 12.87 | 0.66 | 1 | 19.305 | 21 | 614.25
47 | SHOP BUTT WELD | 10 |  |  | 8 |  | STOT-10-RD-363-A SH 8 | TERMINAL |  |  | Y |  | S |  | 3.96 | 1 | 31.68 |  | 1 | 0 |  | 0
48 | FIELD BUTT WELD | 10 |  |  | 1 |  | STOT-10-RD-363-A SH 8 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 5.94 | 1 | 5.94 |  | 0
49 | PIPE HANDLING | 10 |  |  | 2 | 2 | STOT-10-RD-363-A SH 9 | TERMINAL |  |  | Y |  | S/F |  | 0.44 | 1 | 0.88 | 0.66 | 1 | 1.32 | 21 | 42
50 | SHOP BUTT WELD | 10 |  |  | 5 |  | STOT-10-RD-363-A SH 9 | TERMINAL |  |  | Y |  | S |  | 3.96 | 1 | 19.8 |  | 1 | 0 |  | 0
51 | SHOP BUTT WELD | 2 |  |  | 1 |  | STOT-10-RD-363-A SH 9 | TERMINAL |  |  | Y |  | S |  | 1.2 | 1 | 1.2 |  | 1 | 0 |  | 0
52 | BOLT UP | 10 |  | 150 | 4 |  | STOT-10-RD-363-A SH 9 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 1.35 | 1 | 5.4 |  | 0
53 | BOLT UP | 2 |  | 150 | 2 |  | STOT-10-RD-363-A SH 9 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.39 | 1 | 0.78 |  | 0
54 | PIPE SUPPORT | 10 |  |  | 1 | 1 | STOT-10-RD-363-A SH 9 | TERMINAL |  |  | Y |  | S/F |  | 5.5 | 1 | 5.5 | 5.5 | 1 | 5.5 | 200 | 200
55 | PIPE HANDLING | 10 |  |  | 2.25 | 2.25 | STOT-10-RD-386-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.44 | 1 | 0.99 | 0.66 | 1 | 1.485 | 21 | 47.25
56 | SHOP BUTT WELD | 2 |  |  | 4 |  | STOT-10-RD-386-A SH 1 | TERMINAL |  |  | Y |  | S |  | 1.2 | 1 | 4.8 |  | 1 | 0 |  | 0
57 | SHOP BUTT WELD | 2 |  |  | 1 |  | STOT-10-RD-386-A SH 1 | TERMINAL |  |  | Y |  | S |  | 1.2 | 1 | 1.2 |  | 1 | 0 |  | 0
58 | BOLT UP | 2 |  | 150 | 2 |  | STOT-10-RD-386-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.39 | 1 | 0.78 |  | 0
59 | BOLT UP | 10 |  | 150 | 1 |  | STOT-10-RD-386-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 1.35 | 1 | 1.35 |  | 0
60 | PIPE HANDLING | 12 |  |  | 34 | 34 | STOT-12-RD-350-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.52 | 1 | 17.68 | 0.77 | 1 | 26.18 | 24 | 816
61 | PIPE HANDLING | 10 |  |  | 1.5 | 1.5 | STOT-12-RD-350-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.44 | 1 | 0.66 | 0.66 | 1 | 0.99 | 21 | 31.5
62 | SHOP BUTT WELD | 12 |  |  | 4 |  | STOT-12-RD-350-A SH 1 | TERMINAL |  |  | Y |  | S |  | 4.86 | 1 | 19.44 |  | 1 | 0 |  | 0
63 | SHOP BUTT WELD | 10 |  |  | 3 |  | STOT-12-RD-350-A SH 1 | TERMINAL |  |  | Y |  | S |  | 3.96 | 1 | 11.88 |  | 1 | 0 |  | 0
64 | FIELD BUTT WELD | 12 |  |  | 2 |  | STOT-12-RD-350-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 7.29 | 1 | 14.58 |  | 0
65 | FIELD BUTT WELD | 10 |  |  | 1 |  | STOT-12-RD-350-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 5.94 | 1 | 5.94 |  | 0
66 | BOLT UP | 10 |  | 150 | 1 |  | STOT-12-RD-350-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 1.35 | 1 | 1.35 |  | 0
67 | PIPE SUPPORT | 12 |  |  | 2 | 2 | STOT-12-RD-350-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 6 | 1 | 12 | 6 | 1 | 12 | 240 | 480
68 | PIPE HANDLING | 12 |  |  | 37.2 | 37.2 | STOT-12-RD-350-A SH 2 | TERMINAL |  |  | Y |  | S/F |  | 0.52 | 1 | 19.344 | 0.77 | 1 | 28.644 | 24 | 892.8
69 | PIPE HANDLING | 8 |  |  | 2 | 2 | STOT-12-RD-350-A SH 2 | TERMINAL |  |  | Y |  | S/F |  | 0.36 | 1 | 0.72 | 0.54 | 1 | 1.08 | 18 | 36
70 | SHOP BUTT WELD | 12 |  |  | 5 |  | STOT-12-RD-350-A SH 2 | TERMINAL |  |  | Y |  | S |  | 4.86 | 1 | 24.3 |  | 1 | 0 |  | 0
71 | SHOP BUTT WELD | 8 |  |  | 6 |  | STOT-12-RD-350-A SH 2 | TERMINAL |  |  | Y |  | S |  | 3.13 | 1 | 18.78 |  | 1 | 0 |  | 0
72 | PIPE SUPPORT | 12 |  |  | 4 | 4 | STOT-12-RD-350-A SH 2 | TERMINAL |  |  | Y |  | S/F |  | 6 | 1 | 24 | 6 | 1 | 24 | 240 | 960
73 | BOLT UP | 12 |  | 150 | 1 |  | STOT-12-RD-350-A SH 2 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 1.35 | 1 | 1.35 |  | 0
74 | PIPE HANDLING | 12 |  |  | 25.2 | 25.2 | STOT-12-RD-351-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.52 | 1 | 13.104 | 0.77 | 1 | 19.404 | 24 | 604.8
75 | SHOP BUTT WELD | 12 |  |  | 6 |  | STOT-12-RD-351-A SH 1 | TERMINAL |  |  | Y |  | S |  | 4.86 | 1 | 29.16 |  | 1 | 0 |  | 0
76 | SHOP BUTT WELD | 1 |  |  | 2 |  | STOT-12-RD-351-A SH 1 | TERMINAL |  |  | Y |  | S |  | 0.6 | 1 | 1.2 |  | 1 | 0 |  | 0
77 | FIELD BUTT WELD | 12 |  |  | 2 |  | STOT-12-RD-351-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 7.29 | 1 | 14.58 |  | 0
78 | PIPE SUPPORT | 12 |  |  | 1 | 1 | STOT-12-RD-351-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 6 | 1 | 6 | 6 | 1 | 6 | 240 | 240
79 | PIPE HANDLING | 12 |  |  | 185.5 | 185.5 | STOT-12-RD-351-A SH 2 | TERMINAL |  |  | Y |  | S/F |  | 0.52 | 1 | 96.46 | 0.77 | 1 | 142.835 | 24 | 4452
80 | FIELD BUTT WELD | 12 |  |  | 4 |  | STOT-12-RD-351-A SH 2 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 7.29 | 1 | 29.16 |  | 0
81 | PIPE SUPPORT | 12 |  |  | 9 | 9 | STOT-12-RD-351-A SH 2 | TERMINAL |  |  | Y |  | S/F |  | 6 | 1 | 54 | 6 | 1 | 54 | 240 | 2160
82 | PIPE HANDLING | 12 |  |  | 102.5 | 102.5 | STOT-12-RD-351-A SH 3 | TERMINAL |  |  | Y |  | S/F |  | 0.52 | 1 | 53.3 | 0.77 | 1 | 78.925 | 24 | 2460
83 | SHOP BUTT WELD | 12 |  |  | 6 |  | STOT-12-RD-351-A SH 3 | TERMINAL |  |  | Y |  | S |  | 4.86 | 1 | 29.16 |  | 1 | 0 |  | 0
84 | FIELD BUTT WELD | 12 |  |  | 4 |  | STOT-12-RD-351-A SH 3 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 7.29 | 1 | 29.16 |  | 0
85 | PIPE SUPPORT | 12 |  |  | 5 | 5 | STOT-12-RD-351-A SH 3 | TERMINAL |  |  | Y |  | S/F |  | 6 | 1 | 30 | 6 | 1 | 30 | 240 | 1200
86 | PIPE HANDLING | 12 |  |  | 33.5 | 33.5 | STOT-12-RD-351-A SH 4 | TERMINAL |  |  | Y |  | S/F |  | 0.52 | 1 | 17.42 | 0.77 | 1 | 25.795 | 24 | 804
87 | PIPE HANDLING | 2 |  |  | 0.5 | 0.5 | STOT-12-RD-351-A SH 4 | TERMINAL |  |  | Y |  | S/F |  | 0.11 | 1 | 0.055 | 0.16 | 1 | 0.08 | 9.5 | 4.75
88 | SHOP BUTT WELD | 12 |  |  | 6 |  | STOT-12-RD-351-A SH 4 | TERMINAL |  |  | Y |  | S |  | 4.86 | 1 | 29.16 |  | 1 | 0 |  | 0
89 | SHOP BUTT WELD | 2 |  |  | 6 |  | STOT-12-RD-351-A SH 4 | TERMINAL |  |  | Y |  | S |  | 1.2 | 1 | 7.2 |  | 1 | 0 |  | 0
90 | BOLT UP | 2 |  | 150 | 4 |  | STOT-12-RD-351-A SH 4 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.39 | 1 | 1.56 |  | 0
91 | BOLT UP | 12 |  | 150 | 2 |  | STOT-12-RD-351-A SH 4 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 1.35 | 1 | 2.7 |  | 0
92 | PIPE HANDLING | 12 |  |  | 34.5 | 34.5 | STOT-12-RD-351-A SH 5 | TERMINAL |  |  | Y |  | S/F |  | 0.52 | 1 | 17.94 | 0.77 | 1 | 26.565 | 24 | 828
93 | SHOP BUTT WELD | 12 |  |  | 9 |  | STOT-12-RD-351-A SH 5 | TERMINAL |  |  | Y |  | S |  | 4.86 | 1 | 43.74 |  | 1 | 0 |  | 0
94 | SHOP BUTT WELD | 8 |  |  | 2 |  | STOT-12-RD-351-A SH 5 | TERMINAL |  |  | Y |  | S |  | 3.13 | 1 | 6.26 |  | 1 | 0 |  | 0
95 | SHOP BUTT WELD | 1 |  |  | 2 |  | STOT-12-RD-351-A SH 5 | TERMINAL |  |  | Y |  | S |  | 0.6 | 1 | 1.2 |  | 1 | 0 |  | 0
96 | FIELD BUTT WELD | 12 |  |  | 2 |  | STOT-12-RD-351-A SH 5 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 7.29 | 1 | 14.58 |  | 0
97 | PIPE SUPPORT | 12 |  |  | 3 | 3 | STOT-12-RD-351-A SH 5 | TERMINAL |  |  | Y |  | S/F |  | 6 | 1 | 18 | 6 | 1 | 18 | 240 | 720
98 | PIPE HANDLING | 12 |  |  | 199.2 | 199.2 | STOT-12-RD-351-A SH 6 | TERMINAL |  |  | Y |  | S/F |  | 0.52 | 1 | 103.584 | 0.77 | 1 | 153.384 | 24 | 4780.8
99 | SHOP BUTT WELD | 12 |  |  | 1 |  | STOT-12-RD-351-A SH 6 | TERMINAL |  |  | Y |  | S |  | 4.86 | 1 | 4.86 |  | 1 | 0 |  | 0
100 | FIELD BUTT WELD | 12 |  |  | 4 |  | STOT-12-RD-351-A SH 6 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 7.29 | 1 | 29.16 |  | 0
101 | PIPE SUPPORT | 12 |  |  | 7 | 7 | STOT-12-RD-351-A SH 6 | TERMINAL |  |  | Y |  | S/F |  | 6 | 1 | 42 | 6 | 1 | 42 | 240 | 1680
102 | PIPE HANDLING | 12 |  |  | 168.7 | 168.7 | STOT-12-RD-351-A SH 7 | TERMINAL |  |  | Y |  | S/F |  | 0.52 | 1 | 87.724 | 0.77 | 1 | 129.899 | 24 | 4048.8
103 | FIELD BUTT WELD | 12 |  |  | 5 |  | STOT-12-RD-351-A SH 7 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 7.29 | 1 | 36.45 |  | 0
104 | PIPE SUPPORT | 12 |  |  | 9 | 9 | STOT-12-RD-351-A SH 7 | TERMINAL |  |  | Y |  | S/F |  | 6 | 1 | 54 | 6 | 1 | 54 | 240 | 2160
105 | PIPE HANDLING | 12 |  |  | 129.5 | 129.5 | STOT-12-RD-351-A SH 8 | TERMINAL |  |  | Y |  | S/F |  | 0.52 | 1 | 67.34 | 0.77 | 1 | 99.715 | 24 | 3108
106 | SHOP BUTT WELD | 12 |  |  | 10 |  | STOT-12-RD-351-A SH 8 | TERMINAL |  |  | Y |  | S |  | 4.86 | 1 | 48.6 |  | 1 | 0 |  | 0
107 | FIELD BUTT WELD | 12 |  |  | 3 |  | STOT-12-RD-351-A SH 8 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 7.29 | 1 | 21.87 |  | 0
108 | PIPE SUPPORT | 12 |  |  | 6 | 6 | STOT-12-RD-351-A SH 8 | TERMINAL |  |  | Y |  | S/F |  | 6 | 1 | 36 | 6 | 1 | 36 | 240 | 1440
109 | PIPE HANDLING | 12 |  |  | 50.5 | 50.5 | STOT-12-RD-351-A SH 9 | TERMINAL |  |  | Y |  | S/F |  | 0.52 | 1 | 26.26 | 0.77 | 1 | 38.885 | 24 | 1212
110 | SHOP BUTT WELD | 12 |  |  | 3 |  | STOT-12-RD-351-A SH 9 | TERMINAL |  |  | Y |  | S |  | 4.86 | 1 | 14.58 |  | 1 | 0 |  | 0
111 | FIELD BUTT WELD | 12 |  |  | 1 |  | STOT-12-RD-351-A SH 9 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 7.29 | 1 | 7.29 |  | 0
112 | PIPE SUPPORT | 12 |  |  | 2 | 2 | STOT-12-RD-351-A SH 9 | TERMINAL |  |  | Y |  | S/F |  | 6 | 1 | 12 | 6 | 1 | 12 | 240 | 480
113 | PIPE HANDLING | 12 |  |  | 141 | 141 | STOT-12-RD-351-A SH 10 | TERMINAL |  |  | Y |  | S/F |  | 0.52 | 1 | 73.32 | 0.77 | 1 | 108.57 | 24 | 3384
114 | SHOP BUTT WELD | 12 |  |  | 1 |  | STOT-12-RD-351-A SH 10 | TERMINAL |  |  | Y |  | S |  | 4.86 | 1 | 4.86 |  | 1 | 0 |  | 0
115 | FIELD BUTT WELD | 12 |  |  | 4 |  | STOT-12-RD-351-A SH 10 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 7.29 | 1 | 29.16 |  | 0
116 | PIPE SUPPORT | 12 |  |  | 6 | 6 | STOT-12-RD-351-A SH 10 | TERMINAL |  |  | Y |  | S/F |  | 6 | 1 | 36 | 6 | 1 | 36 | 240 | 1440
117 | PIPE HANDLING | 12 |  |  | 13.5 | 13.5 | STOT-12-RD-351-A SH 11 | TERMINAL |  |  | Y |  | S/F |  | 0.52 | 1 | 7.02 | 0.77 | 1 | 10.395 | 24 | 324
118 | SHOP BUTT WELD | 12 |  |  | 5 |  | STOT-12-RD-351-A SH 11 | TERMINAL |  |  | Y |  | S |  | 4.86 | 1 | 24.3 |  | 1 | 0 |  | 0
119 | FIELD BUTT WELD | 12 |  |  | 1 |  | STOT-12-RD-351-A SH 11 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 7.29 | 1 | 7.29 |  | 0
120 | PIPE SUPPORT | 12 |  |  | 1 | 1 | STOT-12-RD-351-A SH 11 | TERMINAL |  |  | Y |  | S/F |  | 6 | 1 | 6 | 6 | 1 | 6 | 240 | 240
121 | PIPE HANDLING | 12 |  |  | 168 | 168 | STOT-12-RD-351-A SH 12 | TERMINAL |  |  | Y |  | S/F |  | 0.52 | 1 | 87.36 | 0.77 | 1 | 129.36 | 24 | 4032
122 | SHOP BUTT WELD | 12 |  |  | 3 |  | STOT-12-RD-351-A SH 12 | TERMINAL |  |  | Y |  | S |  | 4.86 | 1 | 14.58 |  | 1 | 0 |  | 0
123 | FIELD BUTT WELD | 12 |  |  | 4 |  | STOT-12-RD-351-A SH 12 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 7.29 | 1 | 29.16 |  | 0
124 | PIPE SUPPORT | 12 |  |  | 8 | 8 | STOT-12-RD-351-A SH 12 | TERMINAL |  |  | Y |  | S/F |  | 6 | 1 | 48 | 6 | 1 | 48 | 240 | 1920
125 | PIPE HANDLING | 12 |  |  | 42.6 | 42.6 | STOT-12-RD-351-A SH 13 | TERMINAL |  |  | Y |  | S/F |  | 0.52 | 1 | 22.152 | 0.77 | 1 | 32.802 | 24 | 1022.4
126 | SHOP BUTT WELD | 12 |  |  | 2 |  | STOT-12-RD-351-A SH 13 | TERMINAL |  |  | Y |  | S |  | 4.86 | 1 | 9.72 |  | 1 | 0 |  | 0
127 | FIELD BUTT WELD | 12 |  |  | 1 |  | STOT-12-RD-351-A SH 13 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 7.29 | 1 | 7.29 |  | 0
128 | PIPE SUPPORT | 12 |  |  | 3 | 3 | STOT-12-RD-351-A SH 13 | TERMINAL |  |  | Y |  | S/F |  | 6 | 1 | 18 | 6 | 1 | 18 | 240 | 720
129 | PIPE HANDLING | 12 |  |  | 43.5 | 43.5 | STOT-12-RD-351-A SH 14 | TERMINAL |  |  | Y |  | S/F |  | 0.52 | 1 | 22.62 | 0.77 | 1 | 33.495 | 24 | 1044
130 | PIPE HANDLING | 1 |  |  | 0.25 | 0.25 | STOT-12-RD-351-A SH 14 | TERMINAL |  |  | Y |  | S/F |  | 0.07 | 1 | 0.0175 | 0.11 | 1 | 0.0275 | 6.5 | 1.625
131 | SHOP BUTT WELD | 12 |  |  | 8 |  | STOT-12-RD-351-A SH 14 | TERMINAL |  |  | Y |  | S |  | 4.86 | 1 | 38.88 |  | 1 | 0 |  | 0
132 | SHOP BUTT WELD | 1 |  |  | 2 |  | STOT-12-RD-351-A SH 14 | TERMINAL |  |  | Y |  | S |  | 0.6 | 1 | 1.2 |  | 1 | 0 |  | 0
133 | FIELD BUTT WELD | 12 |  |  | 2 |  | STOT-12-RD-351-A SH 14 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 7.29 | 1 | 14.58 |  | 0
134 | PIPE SUPPORT | 12 |  |  | 4 | 4 | STOT-12-RD-351-A SH 14 | TERMINAL |  |  | Y |  | S/F |  | 6 | 1 | 24 | 6 | 1 | 24 | 240 | 960
135 | PIPE HANDLING | 12 |  |  | 38.6 | 38.6 | STOT-12-RD-351-A SH 15 | TERMINAL |  |  | Y |  | S/F |  | 0.52 | 1 | 20.072 | 0.77 | 1 | 29.722 | 24 | 926.4
136 | SHOP BUTT WELD | 12 |  |  | 4 |  | STOT-12-RD-351-A SH 15 | TERMINAL |  |  | Y |  | S |  | 4.86 | 1 | 19.44 |  | 1 | 0 |  | 0
137 | FIELD BUTT WELD | 12 |  |  | 2 |  | STOT-12-RD-351-A SH 15 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 7.29 | 1 | 14.58 |  | 0
138 | PIPE SUPPORT | 12 |  |  | 1 | 1 | STOT-12-RD-351-A SH 15 | TERMINAL |  |  | Y |  | S/F |  | 6 | 1 | 6 | 6 | 1 | 6 | 240 | 240
139 | PIPE HANDLING | 12 |  |  | 32.2 | 32.2 | STOT-12-RD-351-A SH 16 | TERMINAL |  |  | Y |  | S/F |  | 0.52 | 1 | 16.744 | 0.77 | 1 | 24.794 | 24 | 772.8
140 | SHOP BUTT WELD | 12 |  |  | 4 |  | STOT-12-RD-351-A SH 16 | TERMINAL |  |  | Y |  | S |  | 4.86 | 1 | 19.44 |  | 1 | 0 |  | 0
141 | FIELD BUTT WELD | 12 |  |  | 1 |  | STOT-12-RD-351-A SH 16 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 7.29 | 1 | 7.29 |  | 0
142 | PIPE SUPPORT | 12 |  |  | 2 | 2 | STOT-12-RD-351-A SH 16 | TERMINAL |  |  | Y |  | S/F |  | 6 | 1 | 12 | 6 | 1 | 12 | 240 | 480
143 | PIPE HANDLING | 12 |  |  | 4.8 | 4.8 | STOT-12-RD-351-A SH 17 | TERMINAL |  |  | Y |  | S/F |  | 0.52 | 1 | 2.496 | 0.77 | 1 | 3.696 | 24 | 115.2
144 | PIPE HANDLING | 10 |  |  | 1.5 | 1.5 | STOT-12-RD-351-A SH 17 | TERMINAL |  |  | Y |  | S/F |  | 0.44 | 1 | 0.66 | 0.66 | 1 | 0.99 | 21 | 31.5
145 | SHOP BUTT WELD | 12 |  |  | 3 |  | STOT-12-RD-351-A SH 17 | TERMINAL |  |  | Y |  | S |  | 4.86 | 1 | 14.58 |  | 1 | 0 |  | 0
146 | SHOP BUTT WELD | 10 |  |  | 2 |  | STOT-12-RD-351-A SH 17 | TERMINAL |  |  | Y |  | S |  | 3.96 | 1 | 7.92 |  | 1 | 0 |  | 0
147 | BOLT UP | 12 |  | 150 | 2 |  | STOT-12-RD-351-A SH 17 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 1.35 | 1 | 2.7 |  | 0
148 | BOLT UP | 10 |  | 150 | 1 |  | STOT-12-RD-351-A SH 17 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 1.35 | 1 | 1.35 |  | 0
149 | PIPE HANDLING | 12 |  |  | 12.5 | 12.5 | STOT-12-RD-369-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.52 | 1 | 6.5 | 0.77 | 1 | 9.625 | 24 | 300
150 | SHOP BUTT WELD | 12 |  |  | 14 |  | STOT-12-RD-369-A SH 1 | TERMINAL |  |  | Y |  | S |  | 4.86 | 1 | 68.04 |  | 1 | 0 |  | 0
151 | FIELD BUTT WELD | 12 |  |  | 2 |  | STOT-12-RD-369-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 7.29 | 1 | 14.58 |  | 0
152 | SHOP BUTT WELD | 4 |  |  | 1 |  | STOT-12-RD-369-A SH 1 | TERMINAL |  |  | Y |  | S |  | 1.94 | 1 | 1.94 |  | 1 | 0 |  | 0
153 | SHOP BUTT WELD | 2 |  |  | 2 |  | STOT-12-RD-369-A SH 1 | TERMINAL |  |  | Y |  | S |  | 1.2 | 1 | 2.4 |  | 1 | 0 |  | 0
154 | BOLT UP | 12 |  | 150 | 3 |  | STOT-12-RD-369-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 1.35 | 1 | 4.05 |  | 0
155 | BOLT UP | 2 |  | 150 | 2 |  | STOT-12-RD-369-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.39 | 1 | 0.78 |  | 0
156 | BOLT UP | 1 |  | 150 | 6 |  | STOT-12-RD-369-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.39 | 1 | 2.34 |  | 0
157 | PIPE SUPPORT | 12 |  |  | 2 | 2 | STOT-12-RD-369-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 6 | 1 | 12 | 6 | 1 | 12 | 240 | 480
158 | PIPE HANDLING | 12 |  |  | 188.5 | 188.5 | STOT-12-RD-369-A SH 2 | TERMINAL |  |  | Y |  | S/F |  | 0.52 | 1 | 98.02 | 0.77 | 1 | 145.145 | 24 | 4524
159 | SHOP BUTT WELD | 12 |  |  | 3 |  | STOT-12-RD-369-A SH 2 | TERMINAL |  |  | Y |  | S |  | 4.86 | 1 | 14.58 |  | 1 | 0 |  | 0
160 | FIELD BUTT WELD | 12 |  |  | 5 |  | STOT-12-RD-369-A SH 2 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 7.29 | 1 | 36.45 |  | 0
161 | PIPE SUPPORT | 12 |  |  | 9 | 9 | STOT-12-RD-369-A SH 2 | TERMINAL |  |  | Y |  | S/F |  | 6 | 1 | 54 | 6 | 1 | 54 | 240 | 2160
162 | PIPE HANDLING | 12 |  |  | 348.75 | 348.75 | STOT-12-RD-369-A SH 3 | TERMINAL |  |  | Y |  | S/F |  | 0.52 | 1 | 181.35 | 0.77 | 1 | 268.5375 | 24 | 8370
163 | SHOP BUTT WELD | 12 |  |  | 4 |  | STOT-12-RD-369-A SH 3 | TERMINAL |  |  | Y |  | S |  | 4.86 | 1 | 19.44 |  | 1 | 0 |  | 0
164 | FIELD BUTT WELD | 12 |  |  | 10 |  | STOT-12-RD-369-A SH 3 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 7.29 | 1 | 72.9 |  | 0
165 | PIPE HANDLING | 12 |  |  | 11.5 | 11.5 | STOT-12-RD-370-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.52 | 1 | 5.98 | 0.77 | 1 | 8.855 | 24 | 276
166 | SHOP BUTT WELD | 12 |  |  | 4 |  | STOT-12-RD-370-A SH 1 | TERMINAL |  |  | Y |  | S |  | 4.86 | 1 | 19.44 |  | 1 | 0 |  | 0
167 | FIELD BUTT WELD | 12 |  |  | 2 |  | STOT-12-RD-370-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 7.29 | 1 | 14.58 |  | 0
168 | BOLT UP | 12 |  | 150 | 2 |  | STOT-12-RD-370-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 1.35 | 1 | 2.7 |  | 0
169 | PIPE SUPPORT | 12 |  |  | 1 | 1 | STOT-12-RD-370-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 6 | 1 | 6 | 6 | 1 | 6 | 240 | 240
170 | PIPE HANDLING | 12 |  |  | 73.9 | 73.9 | STOT-12-RD-370-A SH 2 | TERMINAL |  |  | Y |  | S/F |  | 0.52 | 1 | 38.428 | 0.77 | 1 | 56.903 | 24 | 1773.6
171 | SHOP BUTT WELD | 12 |  |  | 2 |  | STOT-12-RD-370-A SH 2 | TERMINAL |  |  | Y |  | S |  | 4.86 | 1 | 9.72 |  | 1 | 0 |  | 0
172 | FIELD BUTT WELD | 12 |  |  | 1 |  | STOT-12-RD-370-A SH 2 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 7.29 | 1 | 7.29 |  | 0
173 | PIPE SUPPORT | 12 |  |  | 5 | 5 | STOT-12-RD-370-A SH 2 | TERMINAL |  |  | Y |  | S/F |  | 6 | 1 | 30 | 6 | 1 | 30 | 240 | 1200
174 | PIPE HANDLING | 12 |  |  | 47.7 | 47.7 | STOT-12-RD-370-A SH 3 | TERMINAL |  |  | Y |  | S/F |  | 0.52 | 1 | 24.804 | 0.77 | 1 | 36.729 | 24 | 1144.8
175 | SHOP BUTT WELD | 12 |  |  | 3 |  | STOT-12-RD-370-A SH 3 | TERMINAL |  |  | Y |  | S |  | 4.86 | 1 | 14.58 |  | 1 | 0 |  | 0
176 | FIELD BUTT WELD | 12 |  |  | 2 |  | STOT-12-RD-370-A SH 3 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 7.29 | 1 | 14.58 |  | 0
177 | PIPE SUPPORT | 12 |  |  | 2 | 2 | STOT-12-RD-370-A SH 3 | TERMINAL |  |  | Y |  | S/F |  | 6 | 1 | 12 | 6 | 1 | 12 | 240 | 480
178 | PIPE HANDLING | 12 |  |  | 42.2 | 42.2 | STOT-12-RD-370-A SH 4 | TERMINAL |  |  | Y |  | S/F |  | 0.52 | 1 | 21.944 | 0.77 | 1 | 32.494 | 24 | 1012.8
179 | SHOP BUTT WELD | 12 |  |  | 6 |  | STOT-12-RD-370-A SH 4 | TERMINAL |  |  | Y |  | S |  | 4.86 | 1 | 29.16 |  | 1 | 0 |  | 0
180 | SHOP BUTT WELD | 3 |  |  | 1 |  | STOT-12-RD-370-A SH 4 | TERMINAL |  |  | Y |  | S |  | 1.57 | 1 | 1.57 |  | 1 | 0 |  | 0
181 | FIELD BUTT WELD | 12 |  |  | 1 |  | STOT-12-RD-370-A SH 4 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 7.29 | 1 | 7.29 |  | 0
182 | BOLT UP | 3 |  | 150 | 2 |  | STOT-12-RD-370-A SH 4 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.38 | 1 | 0.76 |  | 0
183 | PIPE SUPPORT | 12 |  |  | 3 | 3 | STOT-12-RD-370-A SH 4 | TERMINAL |  |  | Y |  | S/F |  | 6 | 1 | 18 | 6 | 1 | 18 | 240 | 720
184 | PIPE HANDLING | 12 |  |  | 125.8 | 125.8 | STOT-12-RD-370-A SH 5 | TERMINAL |  |  | Y |  | S/F |  | 0.52 | 1 | 65.416 | 0.77 | 1 | 96.866 | 24 | 3019.2
185 | SHOP BUTT WELD | 12 |  |  | 1 |  | STOT-12-RD-370-A SH 5 | TERMINAL |  |  | Y |  | S |  | 4.86 | 1 | 4.86 |  | 1 | 0 |  | 0
186 | FIELD BUTT WELD | 12 |  |  | 4 |  | STOT-12-RD-370-A SH 5 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 7.29 | 1 | 29.16 |  | 0
187 | PIPE SUPPORT | 12 |  |  | 7 | 7 | STOT-12-RD-370-A SH 5 | TERMINAL |  |  | Y |  | S/F |  | 6 | 1 | 42 | 6 | 1 | 42 | 240 | 1680
188 | PIPE HANDLING | 12 |  |  | 13 | 13 | STOT-12-RD-370-A SH 6 | TERMINAL |  |  | Y |  | S/F |  | 0.52 | 1 | 6.76 | 0.77 | 1 | 10.01 | 24 | 312
189 | SHOP BUTT WELD | 12 |  |  | 7 |  | STOT-12-RD-370-A SH 6 | TERMINAL |  |  | Y |  | S |  | 4.86 | 1 | 34.02 |  | 1 | 0 |  | 0
190 | FIELD BUTT WELD | 12 |  |  | 1 |  | STOT-12-RD-370-A SH 6 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 7.29 | 1 | 7.29 |  | 0
191 | BOLT UP | 12 |  | 150 | 2 |  | STOT-12-RD-370-A SH 6 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 1.35 | 1 | 2.7 |  | 0
192 | BOLT UP | 1 |  | 150 | 2 |  | STOT-12-RD-370-A SH 6 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.39 | 1 | 0.78 |  | 0
193 | PIPE SUPPORT | 12 |  |  | 1 | 1 | STOT-12-RD-370-A SH 6 | TERMINAL |  |  | Y |  | S/F |  | 6 | 1 | 6 | 6 | 1 | 6 | 240 | 240
194 | PIPE HANDLING | 12 |  |  | 16.4 | 16.4 | STOT-12-RD-371-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.52 | 1 | 8.528 | 0.77 | 1 | 12.628 | 24 | 393.6
195 | SHOP BUTT WELD | 12 |  |  | 5 |  | STOT-12-RD-371-A SH 1 | TERMINAL |  |  | Y |  | S |  | 4.86 | 1 | 24.3 |  | 1 | 0 |  | 0
196 | SHOP BUTT WELD | 2 |  |  | 2 |  | STOT-12-RD-371-A SH 1 | TERMINAL |  |  | Y |  | S |  | 1.2 | 1 | 2.4 |  | 1 | 0 |  | 0
197 | FIELD BUTT WELD | 12 |  |  | 1 |  | STOT-12-RD-371-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 7.29 | 1 | 7.29 |  | 0
198 | BOLT UP | 12 |  | 150 | 1 |  | STOT-12-RD-371-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 1.35 | 1 | 1.35 |  | 0
199 | BOLT UP | 2 |  | 150 | 2 |  | STOT-12-RD-371-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.39 | 1 | 0.78 |  | 0
200 | PIPE SUPPORT | 12 |  |  | 1 | 1 | STOT-12-RD-371-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 6 | 1 | 6 | 6 | 1 | 6 | 240 | 240
201 | PIPE HANDLING | 12 |  |  | 22 | 22 | STOT-12-RD-372-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.52 | 1 | 11.44 | 0.77 | 1 | 16.94 | 24 | 528
202 | SHOP BUTT WELD | 12 |  |  | 7 |  | STOT-12-RD-372-A SH 1 | TERMINAL |  |  | Y |  | S |  | 4.86 | 1 | 34.02 |  | 1 | 0 |  | 0
203 | SHOP BUTT WELD | 2 |  |  | 2 |  | STOT-12-RD-372-A SH 1 | TERMINAL |  |  | Y |  | S |  | 1.2 | 1 | 2.4 |  | 1 | 0 |  | 0
204 | FIELD BUTT WELD | 12 |  |  | 1 |  | STOT-12-RD-372-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 7.29 | 1 | 7.29 |  | 0
205 | BOLT UP | 12 |  | 150 | 1 |  | STOT-12-RD-372-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 1.35 | 1 | 1.35 |  | 0
206 | BOLT UP | 2 |  | 150 | 2 |  | STOT-12-RD-372-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.39 | 1 | 0.78 |  | 0
207 | BOLT UP | 1 |  | 150 | 2 |  | STOT-12-RD-372-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.39 | 1 | 0.78 |  | 0
208 | PIPE SUPPORT | 12 |  |  | 1 | 1 | STOT-12-RD-372-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 6 | 1 | 6 | 6 | 1 | 6 | 240 | 240
209 | PIPE HANDLING | 12 |  |  | 128.75 | 128.75 | STOT-12-RD-376-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.52 | 1 | 66.95 | 0.77 | 1 | 99.1375 | 24 | 3090
210 | SHOP BUTT WELD | 12 |  |  | 3 |  | STOT-12-RD-376-A SH 1 | TERMINAL |  |  | Y |  | S |  | 4.86 | 1 | 14.58 |  | 1 | 0 |  | 0
211 | SHOP BUTT WELD | 1 |  |  | 2 |  | STOT-12-RD-376-A SH 1 | TERMINAL |  |  | Y |  | S |  | 0.6 | 1 | 1.2 |  | 1 | 0 |  | 0
212 | FIELD BUTT WELD | 12 |  |  | 3 |  | STOT-12-RD-376-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 7.29 | 1 | 21.87 |  | 0
213 | BOLT UP | 12 |  | 150 | 2 |  | STOT-12-RD-376-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 1.35 | 1 | 2.7 |  | 0
214 | PIPE SUPPORT | 12 |  |  | 2 | 2 | STOT-12-RD-376-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 6 | 1 | 12 | 6 | 1 | 12 | 240 | 480
215 | PIPE HANDLING | 12 |  |  | 31 | 31 | STOT-12-RD-376-A SH 2 | TERMINAL |  |  | Y |  | S/F |  | 0.52 | 1 | 16.12 | 0.77 | 1 | 23.87 | 24 | 744
216 | SHOP BUTT WELD | 12 |  |  | 2 |  | STOT-12-RD-376-A SH 2 | TERMINAL |  |  | Y |  | S |  | 4.86 | 1 | 9.72 |  | 1 | 0 |  | 0
217 | PIPE SUPPORT | 12 |  |  | 2 | 2 | STOT-12-RD-376-A SH 2 | TERMINAL |  |  | Y |  | S/F | CONCRETE VAULT SPPT | 6 | 1 | 12 | 6 | 1 | 12 | 240 | 480
218 | PIPE HANDLING | 12 |  |  | 12.4 | 12.4 | STOT-12-RD-376-A SH 3 | TERMINAL |  |  | Y |  | S/F |  | 0.52 | 1 | 6.448 | 0.77 | 1 | 9.548 | 24 | 297.6
219 | SHOP BUTT WELD | 12 |  |  | 3 |  | STOT-12-RD-376-A SH 3 | TERMINAL |  |  | Y |  | S |  | 4.86 | 1 | 14.58 |  | 1 | 0 |  | 0
220 | SHOP BUTT WELD | 3 |  |  | 1 |  | STOT-12-RD-376-A SH 3 | TERMINAL |  |  | Y |  | S |  | 1.57 | 1 | 1.57 |  | 1 | 0 |  | 0
221 | FIELD BUTT WELD | 12 |  |  | 1 |  | STOT-12-RD-376-A SH 3 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 7.29 | 1 | 7.29 |  | 0
222 | BOLT UP | 3 |  | 150 | 2 |  | STOT-12-RD-376-A SH 3 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.38 | 1 | 0.76 |  | 0
223 | PIPE SUPPORT | 12 |  |  | 1 | 1 | STOT-12-RD-376-A SH 3 | TERMINAL |  |  | Y |  | S/F |  | 6 | 1 | 6 | 6 | 1 | 6 | 240 | 240
224 | PIPE HANDLING | 12 |  |  | 46.2 | 46.2 | STOT-12-RD-376-A SH 4 | TERMINAL |  |  | Y |  | S/F |  | 0.52 | 1 | 24.024 | 0.77 | 1 | 35.574 | 24 | 1108.8
225 | SHOP BUTT WELD | 12 |  |  | 1 |  | STOT-12-RD-376-A SH 4 | TERMINAL |  |  | Y |  | S |  | 4.86 | 1 | 4.86 |  | 1 | 0 |  | 0
226 | FIELD BUTT WELD | 12 |  |  | 2 |  | STOT-12-RD-376-A SH 4 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 7.29 | 1 | 14.58 |  | 0
227 | PIPE SUPPORT | 12 |  |  | 2 | 2 | STOT-12-RD-376-A SH 4 | TERMINAL |  |  | Y |  | S/F |  | 6 | 1 | 12 | 6 | 1 | 12 | 240 | 480
228 | PIPE HANDLING | 12 |  |  | 83.9 | 83.9 | STOT-12-RD-376-A SH 5 | TERMINAL |  |  | Y |  | S/F |  | 0.52 | 1 | 43.628 | 0.77 | 1 | 64.603 | 24 | 2013.6
229 | SHOP BUTT WELD | 12 |  |  | 4 |  | STOT-12-RD-376-A SH 5 | TERMINAL |  |  | Y |  | S |  | 4.86 | 1 | 19.44 |  | 1 | 0 |  | 0
230 | FIELD BUTT WELD | 12 |  |  | 3 |  | STOT-12-RD-376-A SH 5 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 7.29 | 1 | 21.87 |  | 0
231 | BOLT UP | 1 |  | 150 | 4 |  | STOT-12-RD-376-A SH 5 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.39 | 1 | 1.56 |  | 0
232 | PIPE SUPPORT | 12 |  |  | 6 | 6 | STOT-12-RD-376-A SH 5 | TERMINAL |  |  | Y |  | S/F |  | 6 | 1 | 36 | 6 | 1 | 36 | 240 | 1440
233 | PIPE HANDLING | 12 |  |  | 4.25 | 4.25 | STOT-12-RD-376-A SH 6 | TERMINAL |  |  | Y |  | S/F |  | 0.52 | 1 | 2.21 | 0.77 | 1 | 3.2725 | 24 | 102
234 | PIPE HANDLING | 6 |  |  | 0.75 | 0.75 | STOT-12-RD-376-A SH 6 | TERMINAL |  |  | Y |  | S/F |  | 0.29 | 1 | 0.2175 | 0.44 | 1 | 0.33 | 16.5 | 12.375
235 | SHOP BUTT WELD | 12 |  |  | 5 |  | STOT-12-RD-376-A SH 6 | TERMINAL |  |  | Y |  | S |  | 4.86 | 1 | 24.3 |  | 1 | 0 |  | 0
236 | SHOP BUTT WELD | 6 |  |  | 4 |  | STOT-12-RD-376-A SH 6 | TERMINAL |  |  | Y |  | S |  | 2.48 | 1 | 9.92 |  | 1 | 0 |  | 0
237 | FIELD BUTT WELD | 12 |  |  | 1 |  | STOT-12-RD-376-A SH 6 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 7.29 | 1 | 7.29 |  | 0
238 | BOLT UP | 6 |  | 150 | 4 |  | STOT-12-RD-376-A SH 6 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.86 | 1 | 3.44 |  | 0
239 | PIPE SUPPORT | 12 |  |  | 1 | 1 | STOT-12-RD-376-A SH 6 | TERMINAL |  |  | Y |  | S/F |  | 6 | 1 | 6 | 6 | 1 | 6 | 240 | 240
240 | PIPE HANDLING | 6 |  |  | 5.75 | 5.75 | STOT-12-RD-376-A SH 7 | TERMINAL |  |  | Y |  | S/F |  | 0.29 | 1 | 1.6675 | 0.44 | 1 | 2.53 | 16.5 | 94.875
241 | PIPE HANDLING | 4 |  |  | 1.5 | 1.5 | STOT-12-RD-376-A SH 7 | TERMINAL |  |  | Y |  | S/F |  | 0.22 | 1 | 0.33 | 0.33 | 1 | 0.495 | 13.75 | 20.625
242 | SHOP BUTT WELD | 6 |  |  | 4 |  | STOT-12-RD-376-A SH 7 | TERMINAL |  |  | Y |  | S |  | 2.48 | 1 | 9.92 |  | 1 | 0 |  | 0
243 | SHOP BUTT WELD | 4 |  |  | 3 |  | STOT-12-RD-376-A SH 7 | TERMINAL |  |  | Y |  | S |  | 1.94 | 1 | 5.82 |  | 1 | 0 |  | 0
244 | FIELD BUTT WELD | 4 |  |  | 1 |  | STOT-12-RD-376-A SH 7 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 2.91 | 1 | 2.91 |  | 0
245 | BOLT UP | 6 |  | 150 | 1 |  | STOT-12-RD-376-A SH 7 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.86 | 1 | 0.86 |  | 0
246 | BOLT UP | 4 |  | 150 | 1 |  | STOT-12-RD-376-A SH 7 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.78 | 1 | 0.78 |  | 0
247 | PIPE SUPPORT | 6 |  |  | 1 | 1 | STOT-12-RD-376-A SH 7 | TERMINAL |  |  | Y |  | S/F |  | 4.5 | 1 | 4.5 | 4.5 | 1 | 4.5 | 120 | 120
248 | PIPE HANDLING | 4 |  |  | 2.1 | 2.1 | STOT-4-DI-124-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.22 | 1 | 0.462 | 0.33 | 1 | 0.693 | 13.75 | 28.875
249 | SHOP BUTT WELD | 4 |  |  | 6 |  | STOT-4-DI-124-A SH 1 | TERMINAL |  |  | Y |  | S |  | 1.94 | 1 | 11.64 |  | 1 | 0 |  | 0
250 | SHOP BUTT WELD | 1 |  |  | 2 |  | STOT-4-DI-124-A SH 1 | TERMINAL |  |  | Y |  | S |  | 0.6 | 1 | 1.2 |  | 1 | 0 |  | 0
251 | FIELD BUTT WELD | 4 |  |  | 1 |  | STOT-4-DI-124-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 2.91 | 1 | 2.91 |  | 0
252 | BOLT UP | 4 |  | 150 | 6 |  | STOT-4-DI-124-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.78 | 1 | 4.68 |  | 0
253 | PIPE HANDLING | 4 |  |  | 2 | 2 | STOT-4-DI-125-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.22 | 1 | 0.44 | 0.33 | 1 | 0.66 | 13.75 | 27.5
254 | SHOP BUTT WELD | 4 |  |  | 5 |  | STOT-4-DI-125-A SH 1 | TERMINAL |  |  | Y |  | S |  | 1.94 | 1 | 9.7 |  | 1 | 0 |  | 0
255 | SHOP BUTT WELD | 1 |  |  | 2 |  | STOT-4-DI-125-A SH 1 | TERMINAL |  |  | Y |  | S |  | 0.6 | 1 | 1.2 |  | 1 | 0 |  | 0
256 | FIELD BUTT WELD | 4 |  |  | 2 |  | STOT-4-DI-125-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 2.91 | 1 | 5.82 |  | 0
257 | BOLT UP | 4 |  | 150 | 6 |  | STOT-4-DI-125-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.78 | 1 | 4.68 |  | 0
258 | PIPE HANDLING | 4 |  |  | 1.9 | 1.9 | STOT-4-DI-126-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.22 | 1 | 0.418 | 0.33 | 1 | 0.627 | 13.75 | 26.125
259 | SHOP BUTT WELD | 4 |  |  | 5 |  | STOT-4-DI-126-A SH 1 | TERMINAL |  |  | Y |  | S |  | 1.94 | 1 | 9.7 |  | 1 | 0 |  | 0
260 | SHOP BUTT WELD | 1 |  |  | 2 |  | STOT-4-DI-126-A SH 1 | TERMINAL |  |  | Y |  | S |  | 0.6 | 1 | 1.2 |  | 1 | 0 |  | 0
261 | FIELD BUTT WELD | 4 |  |  | 2 |  | STOT-4-DI-126-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 2.91 | 1 | 5.82 |  | 0
262 | BOLT UP | 4 |  | 150 | 6 |  | STOT-4-DI-126-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.78 | 1 | 4.68 |  | 0
263 | PIPE HANDLING | 4 |  |  | 1.9 | 1.9 | STOT-4-DI-127-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.22 | 1 | 0.418 | 0.33 | 1 | 0.627 | 13.75 | 26.125
264 | SHOP BUTT WELD | 4 |  |  | 5 |  | STOT-4-DI-127-A SH 1 | TERMINAL |  |  | Y |  | S |  | 1.94 | 1 | 9.7 |  | 1 | 0 |  | 0
265 | SHOP BUTT WELD | 1 |  |  | 2 |  | STOT-4-DI-127-A SH 1 | TERMINAL |  |  | Y |  | S |  | 0.6 | 1 | 1.2 |  | 1 | 0 |  | 0
266 | FIELD BUTT WELD | 4 |  |  | 2 |  | STOT-4-DI-127-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 2.91 | 1 | 5.82 |  | 0
267 | BOLT UP | 4 |  | 150 | 6 |  | STOT-4-DI-127-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.78 | 1 | 4.68 |  | 0
268 | PIPE HANDLING | 4 |  |  | 30.33 | 30.33 | STOT-4-DI-280-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.22 | 1 | 6.6726 | 0.33 | 1 | 10.0089 | 13.75 | 417.0375
269 | SHOP BUTT WELD | 4 |  |  | 18 |  | STOT-4-DI-280-A SH 1 | TERMINAL |  |  | Y |  | S |  | 1.94 | 1 | 34.92 |  | 1 | 0 |  | 0
270 | SHOP BUTT WELD | 1 |  |  | 8 |  | STOT-4-DI-280-A SH 1 | TERMINAL |  |  | Y |  | S |  | 0.6 | 1 | 4.8 |  | 1 | 0 |  | 0
271 | FIELD BUTT WELD | 4 |  |  | 2 |  | STOT-4-DI-280-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 2.91 | 1 | 5.82 |  | 0
272 | BOLT UP | 4 |  | 150 | 4 |  | STOT-4-DI-280-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.78 | 1 | 3.12 |  | 0
273 | PIPE SUPPORT | 4 |  |  | 3 | 3 | STOT-4-DI-280-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 3.5 | 1 | 10.5 | 3.5 | 1 | 10.5 | 80 | 240
274 | PIPE HANDLING | 4 |  |  | 30.33 | 30.33 | STOT-4-DI-281-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.22 | 1 | 6.6726 | 0.33 | 1 | 10.0089 | 13.75 | 417.0375
275 | SHOP BUTT WELD | 4 |  |  | 18 |  | STOT-4-DI-281-A SH 1 | TERMINAL |  |  | Y |  | S |  | 1.94 | 1 | 34.92 |  | 1 | 0 |  | 0
276 | SHOP BUTT WELD | 1 |  |  | 8 |  | STOT-4-DI-281-A SH 1 | TERMINAL |  |  | Y |  | S |  | 0.6 | 1 | 4.8 |  | 1 | 0 |  | 0
277 | FIELD BUTT WELD | 4 |  |  | 2 |  | STOT-4-DI-281-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 2.91 | 1 | 5.82 |  | 0
278 | BOLT UP | 4 |  | 150 | 4 |  | STOT-4-DI-281-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.78 | 1 | 3.12 |  | 0
279 | PIPE SUPPORT | 4 |  |  | 3 | 3 | STOT-4-DI-281-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 3.5 | 1 | 10.5 | 3.5 | 1 | 10.5 | 80 | 240
280 | PIPE HANDLING | 4 |  |  | 4.5 | 4.5 | STOT-4-RD-382-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.22 | 1 | 0.99 | 0.33 | 1 | 1.485 | 13.75 | 61.875
281 | SHOP BUTT WELD | 4 |  |  | 4 |  | STOT-4-RD-382-A SH 1 | TERMINAL |  |  | Y |  | S |  | 1.94 | 1 | 7.76 |  | 1 | 0 |  | 0
282 | BOLT UP | 4 |  | 150 | 3 |  | STOT-4-RD-382-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.78 | 1 | 2.34 |  | 0
283 | PIPE HANDLING | 4 |  |  | 11.2 | 11.2 | STOT-4-RD-388-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.22 | 1 | 2.464 | 0.33 | 1 | 3.696 | 13.75 | 154
284 | SHOP BUTT WELD | 4 |  |  | 8 |  | STOT-4-RD-388-A SH 1 | TERMINAL |  |  | Y |  | S |  | 1.94 | 1 | 15.52 |  | 1 | 0 |  | 0
285 | SHOP BUTT WELD | 1 |  |  | 2 |  | STOT-4-RD-388-A SH 1 | TERMINAL |  |  | Y |  | S |  | 0.6 | 1 | 1.2 |  | 1 | 0 |  | 0
286 | FIELD BUTT WELD | 4 |  |  | 1 |  | STOT-4-RD-388-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 2.91 | 1 | 2.91 |  | 0
287 | BOLT UP | 4 |  | 150 | 2 |  | STOT-4-RD-388-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.78 | 1 | 1.56 |  | 0
288 | PIPE SUPPORT | 4 |  |  | 1 | 1 | STOT-4-RD-388-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 3.5 | 1 | 3.5 | 3.5 | 1 | 3.5 | 80 | 80
289 | PIPE HANDLING | 4 |  |  | 11.2 | 11.2 | STOT-4-RD-389-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.22 | 1 | 2.464 | 0.33 | 1 | 3.696 | 13.75 | 154
290 | SHOP BUTT WELD | 4 |  |  | 8 |  | STOT-4-RD-389-A SH 1 | TERMINAL |  |  | Y |  | S |  | 1.94 | 1 | 15.52 |  | 1 | 0 |  | 0
291 | SHOP BUTT WELD | 1 |  |  | 2 |  | STOT-4-RD-389-A SH 1 | TERMINAL |  |  | Y |  | S |  | 0.6 | 1 | 1.2 |  | 1 | 0 |  | 0
292 | FIELD BUTT WELD | 4 |  |  | 1 |  | STOT-4-RD-389-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 2.91 | 1 | 2.91 |  | 0
293 | BOLT UP | 4 |  | 150 | 2 |  | STOT-4-RD-389-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.78 | 1 | 1.56 |  | 0
294 | PIPE SUPPORT | 4 |  |  | 1 | 1 | STOT-4-RD-389-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 3.5 | 1 | 3.5 | 3.5 | 1 | 3.5 | 80 | 80
295 | PIPE HANDLING | 4 |  |  | 4.5 | 4.5 | STOT-4-RD-390-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.22 | 1 | 0.99 | 0.33 | 1 | 1.485 | 13.75 | 61.875
296 | PIPE HANDLING | 3 |  |  | 3.2 | 3.2 | STOT-4-RD-390-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.17 | 1 | 0.544 | 0.25 | 1 | 0.8 | 10.75 | 34.4
297 | SHOP BUTT WELD | 4 |  |  | 11 |  | STOT-4-RD-390-A SH 1 | TERMINAL |  |  | Y |  | S |  | 1.94 | 1 | 21.34 |  | 1 | 0 |  | 0
298 | SHOP BUTT WELD | 3 |  |  | 7 |  | STOT-4-RD-390-A SH 1 | TERMINAL |  |  | Y |  | S |  | 1.57 | 1 | 10.99 |  | 1 | 0 |  | 0
299 | SHOP BUTT WELD | 1 |  |  | 4 |  | STOT-4-RD-390-A SH 1 | TERMINAL |  |  | Y |  | S |  | 0.6 | 1 | 2.4 |  | 1 | 0 |  | 0
300 | SHOP BUTT WELD | 1.5 |  |  | 2 |  | STOT-4-RD-390-A SH 1 | TERMINAL |  |  | Y |  | S |  | 0.9 | 1 | 1.8 |  | 1 | 0 |  | 0
301 | BOLT UP | 4 |  | 150 | 5 |  | STOT-4-RD-390-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.78 | 1 | 3.9 |  | 0
302 | BOLT UP | 3 |  | 150 | 2 |  | STOT-4-RD-390-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.38 | 1 | 0.76 |  | 0
303 | BOLT UP | 1.5 |  | 150 | 2 |  | STOT-4-RD-390-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.39 | 1 | 0.78 |  | 0
304 | PIPE SUPPORT | 4 |  |  | 2 | 2 | STOT-4-RD-390-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 3.5 | 1 | 7 | 3.5 | 1 | 7 | 80 | 160
305 | PIPE SUPPORT | 3 |  |  | 2 | 2 | STOT-4-RD-390-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 3 | 1 | 6 | 3 | 1 | 6 | 60 | 120
306 | FIELD BUTT WELD | 4 |  |  | 2 |  | STOT-4-RD-390-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 2.91 | 1 | 5.82 |  | 0
307 | PIPE HANDLING | 4 |  |  | 4.5 | 4.5 | STOT-4-RD-391-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.22 | 1 | 0.99 | 0.33 | 1 | 1.485 | 13.75 | 61.875
308 | PIPE HANDLING | 3 |  |  | 3.2 | 3.2 | STOT-4-RD-391-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.17 | 1 | 0.544 | 0.25 | 1 | 0.8 | 10.75 | 34.4
309 | SHOP BUTT WELD | 4 |  |  | 11 |  | STOT-4-RD-391-A SH 1 | TERMINAL |  |  | Y |  | S |  | 1.94 | 1 | 21.34 |  | 1 | 0 |  | 0
310 | SHOP BUTT WELD | 3 |  |  | 7 |  | STOT-4-RD-391-A SH 1 | TERMINAL |  |  | Y |  | S |  | 1.57 | 1 | 10.99 |  | 1 | 0 |  | 0
311 | SHOP BUTT WELD | 1 |  |  | 4 |  | STOT-4-RD-391-A SH 1 | TERMINAL |  |  | Y |  | S |  | 0.6 | 1 | 2.4 |  | 1 | 0 |  | 0
312 | SHOP BUTT WELD | 1.5 |  |  | 2 |  | STOT-4-RD-391-A SH 1 | TERMINAL |  |  | Y |  | S |  | 0.9 | 1 | 1.8 |  | 1 | 0 |  | 0
313 | BOLT UP | 4 |  | 150 | 5 |  | STOT-4-RD-391-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.78 | 1 | 3.9 |  | 0
314 | BOLT UP | 3 |  | 150 | 2 |  | STOT-4-RD-391-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.38 | 1 | 0.76 |  | 0
315 | BOLT UP | 1.5 |  | 150 | 2 |  | STOT-4-RD-391-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.39 | 1 | 0.78 |  | 0
316 | PIPE SUPPORT | 4 |  |  | 2 | 2 | STOT-4-RD-391-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 3.5 | 1 | 7 | 3.5 | 1 | 7 | 80 | 160
317 | PIPE SUPPORT | 3 |  |  | 1 | 1 | STOT-4-RD-391-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 3 | 1 | 3 | 3 | 1 | 3 | 60 | 60
318 | FIELD BUTT WELD | 4 |  |  | 2 |  | STOT-4-RD-391-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 2.91 | 1 | 5.82 |  | 0
319 | PIPE HANDLING | 6 |  |  | 18.25 | 18.25 | STOT-6-DI-366-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.29 | 1 | 5.2925 | 0.44 | 1 | 8.03 | 16.5 | 301.125
320 | SHOP BUTT WELD | 6 |  |  | 6 |  | STOT-6-DI-366-A SH 1 | TERMINAL |  |  | Y |  | S |  | 2.48 | 1 | 14.88 |  | 1 | 0 |  | 0
321 | FIELD BUTT WELD | 6 |  |  | 2 |  | STOT-6-DI-366-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 3.72 | 1 | 7.44 |  | 0
322 | FIELD BUTT WELD | 10 |  |  | 1 |  | STOT-6-DI-366-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 5.94 | 1 | 5.94 |  | 0
323 | BOLT UP | 6 |  | 150 | 2 |  | STOT-6-DI-366-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.86 | 1 | 1.72 |  | 0
324 | PIPE SUPPORT | 6 |  |  | 2 | 2 | STOT-6-DI-366-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 4.5 | 1 | 9 | 4.5 | 1 | 9 | 120 | 240
325 | PIPE HANDLING | 6 |  |  | 35 | 35 | STOT-6-DI-366-A SH 2 | TERMINAL |  |  | Y |  | S/F |  | 0.29 | 1 | 10.15 | 0.44 | 1 | 15.4 | 16.5 | 577.5
326 | SHOP BUTT WELD | 6 |  |  | 6 |  | STOT-6-DI-366-A SH 2 | TERMINAL |  |  | Y |  | S |  | 2.48 | 1 | 14.88 |  | 1 | 0 |  | 0
327 | SHOP BUTT WELD | 1 |  |  | 2 |  | STOT-6-DI-366-A SH 2 | TERMINAL |  |  | Y |  | S |  | 0.6 | 1 | 1.2 |  | 1 | 0 |  | 0
328 | FIELD BUTT WELD | 6 |  |  | 1 |  | STOT-6-DI-366-A SH 2 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 3.72 | 1 | 3.72 |  | 0
329 | PIPE SUPPORT | 6 |  |  | 3 | 3 | STOT-6-DI-366-A SH 2 | TERMINAL |  |  | Y |  | S/F |  | 4.5 | 1 | 13.5 | 4.5 | 1 | 13.5 | 120 | 360
330 | PIPE HANDLING | 1 |  |  | 0.25 | 0.25 | STOT-6-DI-366-A SH 2 | TERMINAL |  |  | Y |  | S/F |  | 0.07 | 1 | 0.0175 | 0.11 | 1 | 0.0275 | 6.5 | 1.625
331 | PIPE HANDLING | 6 |  |  | 7.6 | 7.6 | STOT-6-DI-366-A SH 3 | TERMINAL |  |  | Y |  | S/F |  | 0.29 | 1 | 2.204 | 0.44 | 1 | 3.344 | 16.5 | 125.4
332 | SHOP BUTT WELD | 6 |  |  | 14 |  | STOT-6-DI-366-A SH 3 | TERMINAL |  |  | Y |  | S |  | 2.48 | 1 | 34.72 |  | 1 | 0 |  | 0
333 | FIELD BUTT WELD | 10 |  |  | 1 |  | STOT-6-DI-366-A SH 3 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 5.94 | 1 | 5.94 |  | 0
334 | BOLT UP | 6 |  | 150 | 4 |  | STOT-6-DI-366-A SH 3 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.86 | 1 | 3.44 |  | 0
335 | PIPE SUPPORT | 6 |  |  | 1 | 1 | STOT-6-DI-366-A SH 3 | TERMINAL |  |  | Y |  | S/F |  | 4.5 | 1 | 4.5 | 4.5 | 1 | 4.5 | 120 | 120
336 | PIPE HANDLING | 8 |  |  | 1.5 | 1.5 | STOT-6-RD-282-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.36 | 1 | 0.54 | 0.54 | 1 | 0.81 | 18 | 27
337 | PIPE HANDLING | 6 |  |  | 0.9 | 0.9 | STOT-6-RD-282-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.29 | 1 | 0.261 | 0.44 | 1 | 0.396 | 16.5 | 14.85
338 | SHOP BUTT WELD | 8 |  |  | 3 |  | STOT-6-RD-282-A SH 1 | TERMINAL |  |  | Y |  | S |  | 3.13 | 1 | 9.39 |  | 1 | 0 |  | 0
339 | SHOP BUTT WELD | 6 |  |  | 3 |  | STOT-6-RD-282-A SH 1 | TERMINAL |  |  | Y |  | S |  | 2.48 | 1 | 7.44 |  | 1 | 0 |  | 0
340 | BOLT UP | 8 |  | 150 | 2 |  | STOT-6-RD-282-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.84 | 1 | 1.68 |  | 0
341 | PIPE HANDLING | 6 |  |  | 4.6 | 4.6 | STOT-6-RD-282-A SH 2 | TERMINAL |  |  | Y |  | S/F |  | 0.29 | 1 | 1.334 | 0.44 | 1 | 2.024 | 16.5 | 75.9
342 | SHOP BUTT WELD | 6 |  |  | 5 |  | STOT-6-RD-282-A SH 2 | TERMINAL |  |  | Y |  | S |  | 2.48 | 1 | 12.4 |  | 1 | 0 |  | 0
343 | FIELD BUTT WELD | 6 |  |  | 1 |  | STOT-6-RD-282-A SH 2 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 3.72 | 1 | 3.72 |  | 0
344 | BOLT UP | 6 |  | 150 | 5 |  | STOT-6-RD-282-A SH 2 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.86 | 1 | 4.3 |  | 0
345 | PIPE SUPPORT | 6 |  |  | 1 | 1 | STOT-6-RD-282-A SH 2 | TERMINAL |  |  | Y |  | S/F |  | 4.5 | 1 | 4.5 | 4.5 | 1 | 4.5 | 120 | 120
346 | PIPE HANDLING | 6 |  |  | 4.5 | 4.5 | STOT-6-RD-359-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.29 | 1 | 1.305 | 0.44 | 1 | 1.98 | 16.5 | 74.25
347 | PIPE HANDLING | 4 |  |  | 1.33 | 1.33 | STOT-6-RD-359-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.22 | 1 | 0.2926 | 0.33 | 1 | 0.4389 | 13.75 | 18.2875
348 | PIPE HANDLING | 1 |  |  | 0.25 | 0.25 | STOT-6-RD-359-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.07 | 1 | 0.0175 | 0.11 | 1 | 0.0275 | 6.5 | 1.625
349 | SHOP BUTT WELD | 6 |  |  | 5 |  | STOT-6-RD-359-A SH 1 | TERMINAL |  |  | Y |  | S |  | 2.48 | 1 | 12.4 |  | 1 | 0 |  | 0
350 | SHOP BUTT WELD | 4 |  |  | 5 |  | STOT-6-RD-359-A SH 1 | TERMINAL |  |  | Y |  | S |  | 1.94 | 1 | 9.7 |  | 1 | 0 |  | 0
351 | SHOP BUTT WELD | 1 |  |  | 2 |  | STOT-6-RD-359-A SH 1 | TERMINAL |  |  | Y |  | S |  | 0.6 | 1 | 1.2 |  | 1 | 0 |  | 0
352 | FIELD BUTT WELD | 4 |  |  | 1 |  | STOT-6-RD-359-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 2.91 | 1 | 2.91 |  | 0
353 | BOLT UP | 6 |  | 150 | 4 |  | STOT-6-RD-359-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.86 | 1 | 3.44 |  | 0
354 | BOLT UP | 4 |  | 150 | 1 |  | STOT-6-RD-359-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.78 | 1 | 0.78 |  | 0
355 | PIPE SUPPORT | 6 |  |  | 1 | 1 | STOT-6-RD-359-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 4.5 | 1 | 4.5 | 4.5 | 1 | 4.5 | 120 | 120
356 | PIPE HANDLING | 6 |  |  | 4.5 | 4.5 | STOT-6-RD-362-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.29 | 1 | 1.305 | 0.44 | 1 | 1.98 | 16.5 | 74.25
357 | PIPE HANDLING | 4 |  |  | 1.33 | 1.33 | STOT-6-RD-362-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.22 | 1 | 0.2926 | 0.33 | 1 | 0.4389 | 13.75 | 18.2875
358 | PIPE HANDLING | 1 |  |  | 0.25 | 0.25 | STOT-6-RD-362-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.07 | 1 | 0.0175 | 0.11 | 1 | 0.0275 | 6.5 | 1.625
359 | SHOP BUTT WELD | 6 |  |  | 5 |  | STOT-6-RD-362-A SH 1 | TERMINAL |  |  | Y |  | S |  | 2.48 | 1 | 12.4 |  | 1 | 0 |  | 0
360 | SHOP BUTT WELD | 4 |  |  | 5 |  | STOT-6-RD-362-A SH 1 | TERMINAL |  |  | Y |  | S |  | 1.94 | 1 | 9.7 |  | 1 | 0 |  | 0
361 | SHOP BUTT WELD | 1 |  |  | 2 |  | STOT-6-RD-362-A SH 1 | TERMINAL |  |  | Y |  | S |  | 0.6 | 1 | 1.2 |  | 1 | 0 |  | 0
362 | FIELD BUTT WELD | 4 |  |  | 1 |  | STOT-6-RD-362-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 2.91 | 1 | 2.91 |  | 0
363 | BOLT UP | 6 |  | 150 | 4 |  | STOT-6-RD-362-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.86 | 1 | 3.44 |  | 0
364 | BOLT UP | 4 |  | 150 | 1 |  | STOT-6-RD-362-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.78 | 1 | 0.78 |  | 0
365 | PIPE SUPPORT | 6 |  |  | 1 | 1 | STOT-6-RD-362-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 4.5 | 1 | 4.5 | 4.5 | 1 | 4.5 | 120 | 120
366 | PIPE HANDLING | 6 |  |  | 19.75 | 19.75 | STOT-6-RD-387-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.29 | 1 | 5.7275 | 0.44 | 1 | 8.69 | 16.5 | 325.875
367 | SHOP BUTT WELD | 6 |  |  | 6 |  | STOT-6-RD-387-A SH 1 | TERMINAL |  |  | Y |  | S |  | 2.48 | 1 | 14.88 |  | 1 | 0 |  | 0
368 | SHOP BUTT WELD | 1 |  |  | 2 |  | STOT-6-RD-387-A SH 1 | TERMINAL |  |  | Y |  | S |  | 0.6 | 1 | 1.2 |  | 1 | 0 |  | 0
369 | FIELD BUTT WELD | 6 |  |  | 1 |  | STOT-6-RD-387-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 3.72 | 1 | 3.72 |  | 0
370 | BOLT UP | 6 |  | 150 | 2 |  | STOT-6-RD-387-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.86 | 1 | 1.72 |  | 0
371 | PIPE SUPPORT | 6 |  |  | 2 | 2 | STOT-6-RD-387-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 4.5 | 1 | 9 | 4.5 | 1 | 9 | 120 | 240
372 | PIPE HANDLING | 6 |  |  | 19 | 19 | STOT-6-RD-387-A SH 2 | TERMINAL |  |  | Y |  | S/F |  | 0.29 | 1 | 5.51 | 0.44 | 1 | 8.36 | 16.5 | 313.5
373 | SHOP BUTT WELD | 6 |  |  | 5 |  | STOT-6-RD-387-A SH 2 | TERMINAL |  |  | Y |  | S |  | 2.48 | 1 | 12.4 |  | 1 | 0 |  | 0
374 | FIELD BUTT WELD | 6 |  |  | 2 |  | STOT-6-RD-387-A SH 2 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 3.72 | 1 | 7.44 |  | 0
375 | PIPE SUPPORT | 6 |  |  | 1 | 1 | STOT-6-RD-387-A SH 2 | TERMINAL |  |  | Y |  | S/F |  | 4.5 | 1 | 4.5 | 4.5 | 1 | 4.5 | 120 | 120
376 | PIPE HANDLING | 6 |  |  | 25.25 | 25.25 | STOT-6-RD-387-A SH 3 | TERMINAL |  |  | Y |  | S/F |  | 0.29 | 1 | 7.3225 | 0.44 | 1 | 11.11 | 16.5 | 416.625
377 | SHOP BUTT WELD | 6 |  |  | 5 |  | STOT-6-RD-387-A SH 3 | TERMINAL |  |  | Y |  | S |  | 2.48 | 1 | 12.4 |  | 1 | 0 |  | 0
378 | BOLT UP | 6 |  | 150 | 1 |  | STOT-6-RD-387-A SH 3 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.86 | 1 | 0.86 |  | 0
379 | PIPE SUPPORT | 6 |  |  | 2 | 2 | STOT-6-RD-387-A SH 3 | TERMINAL |  |  | Y |  | S/F |  | 4.5 | 1 | 9 | 4.5 | 1 | 9 | 120 | 240
380 | PIPE HANDLING | 8 |  |  | 27.33 | 27.33 | STOT-8-DI-347-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.36 | 1 | 9.8388 | 0.54 | 1 | 14.7582 | 18 | 491.94
381 | PIPE HANDLING | 4 |  |  | 0.8 | 0.8 | STOT-8-DI-347-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.22 | 1 | 0.176 | 0.33 | 1 | 0.264 | 13.75 | 11
382 | SHOP BUTT WELD | 8 |  |  | 5 |  | STOT-8-DI-347-A SH 1 | TERMINAL |  |  | Y |  | S |  | 3.13 | 1 | 15.65 |  | 1 | 0 |  | 0
383 | SHOP BUTT WELD | 4 |  |  | 8 |  | STOT-8-DI-347-A SH 1 | TERMINAL |  |  | Y |  | S |  | 1.94 | 1 | 15.52 |  | 1 | 0 |  | 0
384 | SHOP BUTT WELD | 1 |  |  | 2 |  | STOT-8-DI-347-A SH 1 | TERMINAL |  |  | Y |  | S |  | 0.6 | 1 | 1.2 |  | 1 | 0 |  | 0
385 | FIELD BUTT WELD | 8 |  |  | 1 |  | STOT-8-DI-347-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 4.7 | 1 | 4.7 |  | 0
386 | BOLT UP | 8 |  | 150 | 2 |  | STOT-8-DI-347-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.84 | 1 | 1.68 |  | 0
387 | BOLT UP | 4 |  | 150 | 2 |  | STOT-8-DI-347-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.78 | 1 | 1.56 |  | 0
388 | PIPE HANDLING | 8 |  |  | 1.33 | 1.33 | STOT-8-RD-358-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.36 | 1 | 0.4788 | 0.54 | 1 | 0.7182 | 18 | 23.94
389 | SHOP BUTT WELD | 8 |  |  | 2 |  | STOT-8-RD-358-A SH 1 | TERMINAL |  |  | Y |  | S |  | 3.13 | 1 | 6.26 |  | 1 | 0 |  | 0
390 | BOLT UP | 8 |  | 150 | 4 |  | STOT-8-RD-358-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.84 | 1 | 3.36 |  | 0
391 | PIPE HANDLING | 6 |  |  | 4.5 | 4.5 | STOT-8-RD-358-A SH 2 | TERMINAL |  |  | Y |  | S/F |  | 0.29 | 1 | 1.305 | 0.44 | 1 | 1.98 | 16.5 | 74.25
392 | PIPE HANDLING | 1 |  |  | 0.25 | 0.25 | STOT-8-RD-358-A SH 2 | TERMINAL |  |  | Y |  | S/F |  | 0.07 | 1 | 0.0175 | 0.11 | 1 | 0.0275 | 6.5 | 1.625
393 | SHOP BUTT WELD | 8 |  |  | 1 |  | STOT-8-RD-358-A SH 2 | TERMINAL |  |  | Y |  | S |  | 3.13 | 1 | 3.13 |  | 1 | 0 |  | 0
394 | SHOP BUTT WELD | 6 |  |  | 6 |  | STOT-8-RD-358-A SH 2 | TERMINAL |  |  | Y |  | S |  | 2.48 | 1 | 14.88 |  | 1 | 0 |  | 0
395 | SHOP BUTT WELD | 2 |  |  | 2 |  | STOT-8-RD-358-A SH 2 | TERMINAL |  |  | Y |  | S |  | 1.2 | 1 | 2.4 |  | 1 | 0 |  | 0
396 | SHOP BUTT WELD | 1 |  |  | 2 |  | STOT-8-RD-358-A SH 2 | TERMINAL |  |  | Y |  | S |  | 0.6 | 1 | 1.2 |  | 1 | 0 |  | 0
397 | FIELD BUTT WELD | 6 |  |  | 1 |  | STOT-8-RD-358-A SH 2 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 3.72 | 1 | 3.72 |  | 0
398 | BOLT UP | 8 |  | 150 | 1 |  | STOT-8-RD-358-A SH 2 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.84 | 1 | 0.84 |  | 0
399 | BOLT UP | 6 |  | 150 | 1 |  | STOT-8-RD-358-A SH 2 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.86 | 1 | 0.86 |  | 0
400 | BOLT UP | 2 |  | 150 | 2 |  | STOT-8-RD-358-A SH 2 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.39 | 1 | 0.78 |  | 0
401 | PIPE SUPPORT | 6 |  |  | 1 | 1 | STOT-8-RD-358-A SH 2 | TERMINAL |  |  | Y |  | S/F |  | 4.5 | 1 | 4.5 | 4.5 | 1 | 4.5 | 120 | 120
402 | PIPE HANDLING | 8 |  |  | 1.33 | 1.33 | STOT-8-RD-360-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.36 | 1 | 0.4788 | 0.54 | 1 | 0.7182 | 18 | 23.94
403 | SHOP BUTT WELD | 8 |  |  | 2 |  | STOT-8-RD-360-A SH 1 | TERMINAL |  |  | Y |  | S |  | 3.13 | 1 | 6.26 |  | 1 | 0 |  | 0
404 | BOLT UP | 8 |  | 150 | 4 |  | STOT-8-RD-360-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.84 | 1 | 3.36 |  | 0
405 | PIPE HANDLING | 6 |  |  | 4.5 | 4.5 | STOT-8-RD-360-A SH 2 | TERMINAL |  |  | Y |  | S/F |  | 0.29 | 1 | 1.305 | 0.44 | 1 | 1.98 | 16.5 | 74.25
406 | PIPE HANDLING | 1 |  |  | 0.25 | 0.25 | STOT-8-RD-360-A SH 2 | TERMINAL |  |  | Y |  | S/F |  | 0.07 | 1 | 0.0175 | 0.11 | 1 | 0.0275 | 6.5 | 1.625
407 | SHOP BUTT WELD | 8 |  |  | 1 |  | STOT-8-RD-360-A SH 2 | TERMINAL |  |  | Y |  | S |  | 3.13 | 1 | 3.13 |  | 1 | 0 |  | 0
408 | SHOP BUTT WELD | 6 |  |  | 6 |  | STOT-8-RD-360-A SH 2 | TERMINAL |  |  | Y |  | S |  | 2.48 | 1 | 14.88 |  | 1 | 0 |  | 0
409 | SHOP BUTT WELD | 2 |  |  | 2 |  | STOT-8-RD-360-A SH 2 | TERMINAL |  |  | Y |  | S |  | 1.2 | 1 | 2.4 |  | 1 | 0 |  | 0
410 | SHOP BUTT WELD | 1 |  |  | 2 |  | STOT-8-RD-360-A SH 2 | TERMINAL |  |  | Y |  | S |  | 0.6 | 1 | 1.2 |  | 1 | 0 |  | 0
411 | FIELD BUTT WELD | 6 |  |  | 1 |  | STOT-8-RD-360-A SH 2 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 3.72 | 1 | 3.72 |  | 0
412 | BOLT UP | 8 |  | 150 | 1 |  | STOT-8-RD-360-A SH 2 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.84 | 1 | 0.84 |  | 0
413 | BOLT UP | 6 |  | 150 | 1 |  | STOT-8-RD-360-A SH 2 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.86 | 1 | 0.86 |  | 0
414 | BOLT UP | 2 |  | 150 | 2 |  | STOT-8-RD-360-A SH 2 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.39 | 1 | 0.78 |  | 0
415 | PIPE SUPPORT | 6 |  |  | 1 | 1 | STOT-8-RD-360-A SH 2 | TERMINAL |  |  | Y |  | S/F |  | 4.5 | 1 | 4.5 | 4.5 | 1 | 4.5 | 120 | 120
416 | PIPE HANDLING | 8 |  |  | 20.1 | 20.1 | STOT-8-RD-373-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.36 | 1 | 7.236 | 0.54 | 1 | 10.854 | 18 | 361.8
417 | SHOP BUTT WELD | 8 |  |  | 7 |  | STOT-8-RD-373-A SH 1 | TERMINAL |  |  | Y |  | S |  | 3.13 | 1 | 21.91 |  | 1 | 0 |  | 0
418 | SHOP BUTT WELD | 2 |  |  | 2 |  | STOT-8-RD-373-A SH 1 | TERMINAL |  |  | Y |  | S |  | 1.2 | 1 | 2.4 |  | 1 | 0 |  | 0
419 | FIELD BUTT WELD | 8 |  |  | 2 |  | STOT-8-RD-373-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 4.7 | 1 | 9.4 |  | 0
420 | BOLT UP | 8 |  | 150 | 1 |  | STOT-8-RD-373-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.84 | 1 | 0.84 |  | 0
421 | BOLT UP | 2 |  | 150 | 2 |  | STOT-8-RD-373-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.39 | 1 | 0.78 |  | 0
422 | PIPE SUPPORT | 8 |  |  | 1 | 1 | STOT-8-RD-373-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 5 | 1 | 5 | 5 | 1 | 5 | 160 | 160
423 | PIPE HANDLING | 8 |  |  | 16.6 | 16.6 | STOT-8-RD-374-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.36 | 1 | 5.976 | 0.54 | 1 | 8.964 | 18 | 298.8
424 | PIPE HANDLING | 1 |  |  | 0.67 | 0.67 | STOT-8-RD-374-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.07 | 1 | 0.0469 | 0.11 | 1 | 0.0737 | 6.5 | 4.355
425 | SHOP BUTT WELD | 8 |  |  | 4 |  | STOT-8-RD-374-A SH 1 | TERMINAL |  |  | Y |  | S |  | 3.13 | 1 | 12.52 |  | 1 | 0 |  | 0
426 | SHOP BUTT WELD | 2 |  |  | 2 |  | STOT-8-RD-374-A SH 1 | TERMINAL |  |  | Y |  | S |  | 1.2 | 1 | 2.4 |  | 1 | 0 |  | 0
427 | FIELD BUTT WELD | 8 |  |  | 1 |  | STOT-8-RD-374-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 4.7 | 1 | 4.7 |  | 0
428 | BOLT UP | 8 |  | 150 | 1 |  | STOT-8-RD-374-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.84 | 1 | 0.84 |  | 0
429 | PIPE SUPPORT | 8 |  |  | 1 | 1 | STOT-8-RD-374-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 5 | 1 | 5 | 5 | 1 | 5 | 160 | 160
430 | PIPE HANDLING | 8 |  |  | 6 | 6 | STOT-8-RD-375-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.36 | 1 | 2.16 | 0.54 | 1 | 3.24 | 18 | 108
431 | SHOP BUTT WELD | 8 |  |  | 5 |  | STOT-8-RD-375-A SH 1 | TERMINAL |  |  | Y |  | S |  | 3.13 | 1 | 15.65 |  | 1 | 0 |  | 0
432 | FIELD BUTT WELD | 8 |  |  | 2 |  | STOT-8-RD-375-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 4.7 | 1 | 9.4 |  | 0
433 | BOLT UP | 8 |  | 150 | 4 |  | STOT-8-RD-375-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.84 | 1 | 3.36 |  | 0
434 | PIPE SUPPORT | 8 |  |  | 1 | 1 | STOT-8-RD-375-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 5 | 1 | 5 | 5 | 1 | 5 | 160 | 160
435 | PIPE HANDLING | 6 |  |  | 4.9 | 4.9 | STOT-8-RD-375-A SH 2 | TERMINAL |  |  | Y |  | S/F |  | 0.29 | 1 | 1.421 | 0.44 | 1 | 2.156 | 16.5 | 80.85
436 | SHOP BUTT WELD | 8 |  |  | 1 |  | STOT-8-RD-375-A SH 2 | TERMINAL |  |  | Y |  | S |  | 3.13 | 1 | 3.13 |  | 1 | 0 |  | 0
437 | SHOP BUTT WELD | 6 |  |  | 6 |  | STOT-8-RD-375-A SH 2 | TERMINAL |  |  | Y |  | S |  | 2.48 | 1 | 14.88 |  | 1 | 0 |  | 0
438 | SHOP BUTT WELD | 2 |  |  | 2 |  | STOT-8-RD-375-A SH 2 | TERMINAL |  |  | Y |  | S |  | 1.2 | 1 | 2.4 |  | 1 | 0 |  | 0
439 | FIELD BUTT WELD | 6 |  |  | 1 |  | STOT-8-RD-375-A SH 2 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 3.72 | 1 | 3.72 |  | 0
440 | BOLT UP | 8 |  | 150 | 1 |  | STOT-8-RD-375-A SH 2 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.84 | 1 | 0.84 |  | 0
441 | BOLT UP | 6 |  | 150 | 1 |  | STOT-8-RD-375-A SH 2 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.86 | 1 | 0.86 |  | 0
442 | BOLT UP | 2 |  | 150 | 2 |  | STOT-8-RD-375-A SH 2 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.39 | 1 | 0.78 |  | 0
443 | BOLT UP | 1 |  | 150 | 2 |  | STOT-8-RD-375-A SH 2 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.39 | 1 | 0.78 |  | 0
444 | PIPE SUPPORT | 6 |  |  | 1 | 1 | STOT-8-RD-375-A SH 2 | TERMINAL |  |  | Y |  | S/F |  | 4.5 | 1 | 4.5 | 4.5 | 1 | 4.5 | 120 | 120
445 | PIPE HANDLING | 8 |  |  | 8.25 | 8.25 | STOT-8-RD-386-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.36 | 1 | 2.97 | 0.54 | 1 | 4.455 | 18 | 148.5
446 | SHOP BUTT WELD | 8 |  |  | 4 |  | STOT-8-RD-386-A SH 1 | TERMINAL |  |  | Y |  | S |  | 3.13 | 1 | 12.52 |  | 1 | 0 |  | 0
447 | FIELD BUTT WELD | 8 |  |  | 2 |  | STOT-8-RD-386-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 4.7 | 1 | 9.4 |  | 0
448 | FIELD BUTT WELD | 6 |  |  | 1 |  | STOT-8-RD-386-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 3.72 | 1 | 3.72 |  | 0
449 | PIPE HANDLING | 8 |  |  | 71 | 71 | STOT-8-RD-386-A SH 2 | TERMINAL |  |  | Y |  | S/F |  | 0.36 | 1 | 25.56 | 0.54 | 1 | 38.34 | 18 | 1278
450 | PIPE HANDLING | 1 |  |  | 0.25 | 0.25 | STOT-8-RD-386-A SH 2 | TERMINAL |  |  | Y |  | S/F |  | 0.07 | 1 | 0.0175 | 0.11 | 1 | 0.0275 | 6.5 | 1.625
451 | SHOP BUTT WELD | 8 |  |  | 6 |  | STOT-8-RD-386-A SH 2 | TERMINAL |  |  | Y |  | S |  | 3.13 | 1 | 18.78 |  | 1 | 0 |  | 0
452 | SHOP BUTT WELD | 1 |  |  | 4 |  | STOT-8-RD-386-A SH 2 | TERMINAL |  |  | Y |  | S |  | 0.6 | 1 | 2.4 |  | 1 | 0 |  | 0
453 | FIELD BUTT WELD | 8 |  |  | 1 |  | STOT-8-RD-386-A SH 2 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 4.7 | 1 | 4.7 |  | 0
454 | BOLT UP | 8 |  | 150 | 1 |  | STOT-8-RD-386-A SH 2 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.84 | 1 | 0.84 |  | 0
455 | PIPE SUPPORT | 8 |  |  | 5 | 5 | STOT-8-RD-386-A SH 2 | TERMINAL |  |  | Y |  | S/F |  | 5 | 1 | 25 | 5 | 1 | 25 | 160 | 800
456 | PIPE HANDLING | 8 |  |  | 4.25 | 4.25 | STOT-8-RD-396-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.36 | 1 | 1.53 | 0.54 | 1 | 2.295 | 18 | 76.5
457 | SHOP BUTT WELD | 8 |  |  | 8 |  | STOT-8-RD-396-A SH 1 | TERMINAL |  |  | Y |  | S |  | 3.13 | 1 | 25.04 |  | 1 | 0 |  | 0
458 | SHOP BUTT WELD | 1 |  |  | 2 |  | STOT-8-RD-396-A SH 1 | TERMINAL |  |  | Y |  | S |  | 0.6 | 1 | 1.2 |  | 1 | 0 |  | 0
459 | FIELD BUTT WELD | 8 |  |  | 1 |  | STOT-8-RD-396-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 4.7 | 1 | 4.7 |  | 0
460 | BOLT UP | 8 |  | 150 | 4 |  | STOT-8-RD-396-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.84 | 1 | 3.36 |  | 0
461 | PIPE HANDLING | 12 |  |  | 2733 | 2733 |  | HDD |  |  | Y |  | F |  |  | 1 | 0 | 0.77 | 1 | 2104.41 | 24 | 65592
462 | FIELD BUTT WELD | 12 |  |  | 68 |  |  | HDD |  |  | Y |  | F |  |  | 1 | 0 | 7.29 | 1 | 495.72 |  | 0
463 | PIPE HANDLING | 12 |  |  |  |  | PULL-BACK | HDD | [7 empty] | 1 | 0 | 0.77 | 1 | 120 |  | 0
464 | PIPE HANDLING | 8 |  |  | 7.5 | 7.5 |  | DOCK |  |  | Y |  | F |  |  | 1 | 0 | 0.54 | 1 | 4.05 | 18 | 135
465 | PIPE HANDLING | 2 |  |  | 24.25 | 24.25 |  | DOCK |  |  | Y |  | F |  |  | 1 | 0 | 0.16 | 1 | 3.88 | 10 | 242.5
466 | PIPE HANDLING | 1.5 |  |  | 16.8 | 16.8 |  | DOCK |  |  | Y |  | F |  |  | 1 | 0 | 0.14 | 1 | 2.352 | 8 | 134.4
467 | FIELD BUTT WELD | 8 |  |  | 7 |  |  | DOCK |  |  | Y |  | F |  |  | 1 | 0 | 4.7 | 1 | 32.9 |  | 0
468 | FIELD BUTT WELD | 2 |  |  | 20 |  |  | DOCK |  |  | Y |  | F |  |  | 1 | 0 | 1.8 | 1 | 36 |  | 0
469 | FIELD BUTT WELD | 1.5 |  |  | 28 |  |  | DOCK |  |  | Y |  | F |  |  | 1 | 0 | 1.35 | 1 | 37.8 |  | 0
470 | FIELD BUTT WELD | 12 |  |  | 4 |  |  | DOCK |  |  | Y |  | F |  |  | 1 | 0 | 7.29 | 1 | 29.16 |  | 0
471 | PIPE HANDLING | 12 |  |  | 5.2 | 5.2 |  | DOCK |  |  | Y |  | F |  |  | 1 | 0 | 0.77 | 1 | 4.004 | 24 | 124.8
472 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
473 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
474 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
475 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
476 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
477 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
478 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
479 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
480 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
481 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
482 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
483 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
484 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
485 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
486 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
487 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
488 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
489 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
490 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
491 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
492 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
493 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
494 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
495 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
496 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
497 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
498 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
499 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
500 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
501 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
502 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
503 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
504 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
505 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
506 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
507 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
508 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
509 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
510 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
511 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
512 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
513 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
514 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
515 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
516 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
517 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
518 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
519 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
520 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
521 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
522 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
523 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
524 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
525 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
526 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
527 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
528 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
529 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
530 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
531 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
532 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
533 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
534 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
535 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
536 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
537 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
538 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
539 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
540 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
541 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
542 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
543 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
544 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
545 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
546 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
547 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
548 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
549 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
550 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
551 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
552 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
553 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
554 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
555 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
556 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
557 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
558 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
559 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
560 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
561 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
562 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
563 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
564 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
565 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
566 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
567 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
568 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
569 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
570 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
571 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
572 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
573 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
574 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
575 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
576 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
577 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
578 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
579 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
580 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
581 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
582 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
583 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
584 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
585 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
586 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
587 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
588 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
589 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
590 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
591 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
592 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
593 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
594 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
595 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
596 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
597 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
598 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
599 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
600 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
601 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
602 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
603 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
604 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
605 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
606 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
607 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
608 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
609 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
610 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
611 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
612 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
613 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
614 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
615 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
616 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
617 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
618 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
619 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
620 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
621 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
622 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
623 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
624 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
625 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
626 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
627 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
628 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
629 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
630 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
631 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
632 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
633 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
634 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
635 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
636 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
637 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
638 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
639 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
640 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
641 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
642 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
643 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
644 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
645 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
646 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
647 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
648 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
649 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
650 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
651 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
652 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
653 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
654 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
655 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
656 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
657 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
658 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
659 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
660 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
661 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
662 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
663 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
664 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
665 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
666 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
667 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
668 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
669 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
670 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
671 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
672 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
673 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
674 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
675 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
676 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
677 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
678 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
679 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
680 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
681 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
682 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
683 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
684 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
685 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
686 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
687 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
688 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
689 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
690 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
691 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
692 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
693 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
694 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
695 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
696 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
697 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
698 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
699 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
700 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
701 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
702 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
703 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
704 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
705 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
706 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
707 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
708 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
709 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
710 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
711 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
712 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
713 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
714 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
715 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
716 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
717 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
718 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
719 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
720 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
721 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
722 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
723 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
724 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
725 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
726 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
727 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
728 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
729 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
730 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
731 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
732 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
733 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
734 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
735 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
736 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
737 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
738 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
739 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
740 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
741 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
742 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
743 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
744 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
745 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
746 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
747 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
748 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
749 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
750 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
1190 | TOTALS | [12 empty] | TOTALS |  |  | 4488.2722 |  |  | 7453.6894 |  | 184628.025
[14 empty] | Qty Shop Welds | 603
[14 empty] | Qty Field Welds | 269
[14 empty] | Total Welds | 872
[14 empty] | HDD total MH | 2720.13
Note on I1: Rick M. Carpenter: This may help you break down your labor on the Price Proposal Sheet
Note on L1: Steve Kraak: Yes or No? This will help you determine pressure testing hours
Note on N1: Steve Kraak: SHOP OR FIELD ACTIVITY? S=SHOP, F=FIELD, SOME ACTIVITES MAY BE BOTH. S/F=SHOP AND FIELD.
Note on F16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Changed from 5 to 7. I counted 4 butt welds and 3 olet (branchette) welds

## Piping Labor Units
PIPE HANDLING -SHOP | [14 empty] | PIPE HANDLING -FIELD
Dia. In. | Activity | Material | Sch 20 | Sch 30 | Std Wt | Sch 40 | Sch 60 | XS | Sch 80 | Sch 100 | Sch 120 | Sch 140 | Sch 160 | XXS | Dia. In. | Activity | Material | Sch 20 | Sch 30 | Std Wt | Sch 40 | Sch 60 | XS | Sch 80 | Sch 100 | Sch 120 | Sch 140 | Sch 160 | XXS
1/2 | pipe handling | CS |  |  | 0.06 |  |  | 0.062 |  |  |  |  | 0.068 | 0.074 | 1/2 | pipe handling | CS |  |  | 0.09 |  |  | 0.093 |  |  |  |  | 0.102 | 0.111 | 1.25
3/4 | pipe handling | CS |  |  | 0.065 |  |  | 0.069 |  |  |  |  | 0.078 | 0.086 | 3/4 | pipe handling | CS |  |  | 0.0975 |  |  | 0.1035 |  |  |  |  | 0.117 | 0.129
1 | pipe handling | CS |  |  | 0.074 |  |  | 0.08 |  |  |  |  | 0.093 | 0.106 | 1 | pipe handling | CS |  |  | 0.111 |  |  | 0.12 |  |  |  |  | 0.1395 | 0.159
1-1/4 | pipe handling | CS |  |  | 0.083 |  |  | 0.093 |  |  |  |  | 0.108 | 0.131 | 1-1/4 | pipe handling | CS |  |  | 0.1245 |  |  | 0.1395 |  |  |  |  | 0.162 | 0.1965
1-1/2 | pipe handling | CS |  |  | 0.091 |  |  | 0.102 |  |  |  |  | 0.125 | 0.15 | 1-1/2 | pipe handling | CS |  |  | 0.1365 |  |  | 0.153 |  |  |  |  | 0.1875 | 0.225
2 | pipe handling | CS |  |  | 0.107 |  |  | 0.124 |  |  |  |  | 0.167 | 0.192 | 2 | pipe handling | CS |  |  | 0.1605 |  |  | 0.186 |  |  |  |  | 0.2505 | 0.288
2-1/2 | pipe handling | CS |  |  | 0.14 |  |  | 0.164 |  |  |  |  | 0.208 | 0.255 | 2-1/2 | pipe handling | CS |  |  | 0.21 |  |  | 0.246 |  |  |  |  | 0.312 | 0.3825
3 | pipe handling | CS |  |  | 0.168 |  |  | 0.204 |  |  |  |  | 0.258 | 0.29 | 3 | pipe handling | CS |  |  | 0.252 |  |  | 0.306 |  |  |  |  | 0.387 | 0.435
3-1/2 | pipe handling | CS |  |  | 0.192 |  |  | 0.238 | [5 empty] | 0.32 | 3-1/2 | pipe handling | CS |  |  | 0.288 |  |  | 0.357 | [5 empty] | 0.48
4 | pipe handling | CS |  |  | 0.218 |  |  | 0.255 |  |  | 0.291 |  | 0.316 | 0.354 | 4 | pipe handling | CS |  |  | 0.327 |  |  | 0.3825 |  |  | 0.4365 |  | 0.474 | 0.531
5 | pipe handling | CS |  |  | 0.26 |  |  | 0.294 |  |  | 0.349 |  | 0.39 | 0.431 | 5 | pipe handling | CS |  |  | 0.39 |  |  | 0.441 |  | 0 | 0.5235 | 0 | 0.585 | 0.6465
6 | pipe handling | CS |  |  | 0.291 |  |  | 0.346 |  |  | 0.415 |  | 0.477 | 0.524 | 6 | pipe handling | CS |  |  | 0.4365 |  |  | 0.519 |  | 0 | 0.6225 | 0 | 0.7155 | 0.786
8 | pipe handling | CS | 0.314 | 0.331 | 0.358 |  | 0.406 | 0.446 |  | 0.516 | 0.538 | 0.55 | 0.562 | 0.56 | 8 | pipe handling | CS | 0.471 | 0.4965 | 0.537 |  | 0.609 | 0.669 |  | 0.774 | 0.807 | 0.825 | 0.843 | 0.84
10 | pipe handling | CS | 0.355 | 0.398 | 0.441 |  | 0.522 | 0.507 | 0.541 | 0.562 | 0.589 | 0.614 | 0.639 | 0.614 | 10 | pipe handling | CS | 0.5325 | 0.597 | 0.6615 |  | 0.783 | 0.7605 | 0.8115 | 0.843 | 0.8835 | 0.921 | 0.9585 | 0.921
12 | pipe handling | CS | 0.393 | 0.465 | 0.515 | 0.515 | 0.556 | 0.526 | 0.585 | 0.619 | 0.654 | 0.683 | 0.727 | 0.654 | 12 | pipe handling | CS | 0.5895 | 0.6975 | 0.7725 | 0.7725 | 0.834 | 0.789 | 0.8775 | 0.9285 | 0.981 | 1.0245 | 1.0905 | 0.981
14 | pipe handling | CS | 0.48 | 0.526 | 0.526 | 0.539 | 0.581 | 0.537 | 0.62 | 0.666 | 0.702 | 0.745 | 0.788 |  | 14 | pipe handling | CS | 0.72 | 0.789 | 0.789 | 0.8085 | 0.8715 | 0.8055 | 0.93 | 0.999 | 1.053 | 1.1175 | 1.182 | 0
16 | pipe handling | CS | 0.523 | 0.541 | 0.541 | 0.574 | 0.624 | 0.556 | 0.676 | 0.731 | 0.783 | 0.845 | 0.894 |  | 16 | pipe handling | CS | 0.7845 | 0.8115 | 0.8115 | 0.861 | 0.936 | 0.834 | 1.014 | 1.0965 | 1.1745 | 1.2675 | 1.341 | 0
18 | pipe handling | CS | 0.536 | 0.576 | 0.556 | 0.617 | 0.679 | 0.574 | 0.741 | 0.812 | 0.884 | 0.945 | 1.016 |  | 18 | pipe handling | CS | 0.804 | 0.864 | 0.834 | 0.9255 | 1.0185 | 0.861 | 1.1115 | 1.218 | 1.326 | 1.4175 | 1.524 | 0
20 | pipe handling | CS | 0.571 | 0.614 | 0.571 | 0.65 | 0.733 | 0.593 | 0.813 | 0.903 | 0.986 | 1.075 | 1.153 |  | 20 | pipe handling | CS | 0.8565 | 0.921 | 0.8565 | 0.975 | 1.0995 | 0.8895 | 1.2195 | 1.3545 | 1.479 | 1.6125 | 1.7295 | 0
24 | pipe handling | CS | 0.602 | 0.683 | 0.602 | 0.741 | 0.867 | 0.629 | 0.978 | 1.116 | 1.248 | 1.354 | 1.476 |  | 24 | pipe handling | CS | 0.903 | 1.0245 | 0.903 | 1.1115 | 1.3005 | 0.9435 | 1.467 | 1.674 | 1.872 | 2.031 | 2.214 | 0
30 | pipe handling | CS | 0.707 | 0.78 | 0.648 |  |  | 0.684 | [6 empty] | 30 | pipe handling | CS | 1.0605 | 1.17 | 0.972 |  |  | 1.026
36 | pipe handling | CS | 0.766 | 0.853 | 0.694 |  |  | 0.739 | [6 empty] | 36 | pipe handling | CS | 1.149 | 1.2795 | 1.041 |  |  | 1.1085
42 | pipe handling | CS |  |  | 0.74 |  |  | 0.794 | [6 empty] | 42 | pipe handling | CS |  |  | 1.11 |  |  | 1.191
48 | pipe handling | CS |  |  | 0.785 |  |  | 0.85 | [6 empty] | 48 | pipe handling | CS |  |  | 1.1775 |  |  | 1.275
54 | pipe handling | CS |  |  | 0.831 |  |  | 1.115 | [6 empty] | 54 | pipe handling | CS |  |  | 1.2465 |  |  | 1.6725
60 | pipe handling | CS |  |  | 0.877 |  |  | 1.193 | [6 empty] | 60 | pipe handling | CS |  |  | 1.3155 |  |  | 1.7895
PIPE JOINTS-SHOP | [14 empty] | PIPE JOINTS -FIELD
CARBON STEEL | [14 empty] | CARBON STEEL
Dia. In. | Activity | Material | Sch 20 | Sch 30 | Std Wt | Sch 40 | Sch 60 | XS | Sch 80 | Sch 100 | Sch 120 | Sch 140 | Sch 160 | XXS | Dia. In. | Activity | Material | Sch 20 | Sch 30 | Std Wt | Sch 40 | Sch 60 | XS | Sch 80 | Sch 100 | Sch 120 | Sch 140 | Sch 160 | XXS
1/2 | butt weld | CS |  |  | 0.3 |  |  | 0.33 |  |  |  |  | 0.39 | 0.48 | 1/2 | butt weld | CS |  |  | 0.45 |  |  | 0.495 |  |  |  |  | 0.585 | 0.72
3/4 | butt weld | CS |  |  | 0.45 |  |  | 0.5 |  |  |  |  | 0.59 | 0.72 | 3/4 | butt weld | CS |  |  | 0.675 |  |  | 0.75 |  |  |  |  | 0.885 | 1.08
1 | butt weld | CS |  |  | 0.6 |  |  | 0.66 |  |  |  |  | 0.78 | 0.96 | 1 | butt weld | CS |  |  | 0.9 |  |  | 0.99 |  |  |  |  | 1.17 | 1.44
1-1/4 | butt weld | CS |  |  | 0.75 |  |  | 0.83 |  |  |  |  | 0.98 | 1.2 | 1-1/4 | butt weld | CS |  |  | 1.125 |  |  | 1.245 |  |  |  |  | 1.47 | 1.8
1-1/2 | butt weld | CS |  |  | 0.9 |  |  | 0.99 |  |  |  |  | 1.17 | 1.44 | 1-1/2 | butt weld | CS |  |  | 1.35 |  |  | 1.485 |  |  |  |  | 1.755 | 2.16
2 | butt weld | CS |  |  | 1.2 |  |  | 1.32 |  |  |  |  | 1.56 | 1.92 | 2 | butt weld | CS |  |  | 1.8 |  |  | 1.98 |  |  |  |  | 2.34 | 2.88
2-1/2 | butt weld | CS |  |  | 1.5 |  |  | 1.66 |  |  |  |  | 1.94 | 2.49 | 2-1/2 | butt weld | CS |  |  | 2.25 |  |  | 2.49 |  |  |  |  | 2.91 | 3.735
3 | butt weld | CS |  |  | 1.57 |  |  | 1.72 |  |  |  |  | 2.14 | 2.91 | 3 | butt weld | CS |  |  | 2.355 |  |  | 2.58 |  |  |  |  | 3.21 | 4.365
3-1/2 | butt weld | CS |  |  | 1.79 |  |  | 1.96 | [5 empty] | 3.35 | 3-1/2 | butt weld | CS |  |  | 2.685 |  |  | 2.94 |  |  |  |  | 0 | 5.025
4 | butt weld | CS |  |  | 1.94 |  |  | 2.14 |  |  | 2.55 |  | 2.86 | 3.77 | 4 | butt weld | CS |  |  | 2.91 |  |  | 3.21 |  |  | 3.825 |  | 4.29 | 5.655
5 | butt weld | CS |  |  | 2.23 |  |  | 2.42 |  |  | 3.38 |  | 3.76 | 4.59 | 5 | butt weld | CS |  |  | 3.345 |  |  | 3.63 |  |  | 5.07 |  | 5.64 | 6.885
6 | butt weld | CS |  |  | 2.48 |  |  | 2.71 |  |  | 4.33 |  | 4.8 | 5.57 | 6 | butt weld | CS |  |  | 3.72 |  |  | 4.065 |  |  | 6.495 |  | 7.2 | 8.355
8 | butt weld | CS | 2.71 | 2.82 | 3.13 |  | 3.34 | 3.65 |  | 4.38 | 6.16 | 6.58 | 7.1 | 7.31 | 8 | butt weld | CS | 4.065 | 4.23 | 4.695 |  | 5.01 | 5.475 |  | 6.57 | 9.24 | 9.87 | 10.65 | 10.965
10 | butt weld | CS | 3.43 | 3.7 | 3.96 |  | 4.62 | 4.62 | 5.54 | 6.2 | 8.32 | 8.98 | 10.56 | 8.98 | 10 | butt weld | CS | 5.145 | 5.55 | 5.94 |  | 6.93 | 6.93 | 8.31 | 9.3 | 12.48 | 13.47 | 15.84 | 13.47
12 | butt weld | CS | 4.21 | 4.7 | 4.86 | 4.86 | 6.16 | 5.51 | 7.61 | 9.23 | 10.85 | 12.8 | 16.2 | 11.02 | 12 | butt weld | CS | 6.315 | 7.05 | 7.29 | 7.29 | 9.24 | 8.265 | 11.415 | 13.845 | 16.275 | 19.2 | 24.3 | 16.53
14 | butt weld | CS | 5.29 | 5.67 | 5.67 | 5.67 | 7.94 | 6.24 | 9.83 | 12.1 | 13.42 | 17.01 | 20.79 |  | 14 | butt weld | CS | 7.935 | 8.505 | 8.505 | 8.505 | 11.91 | 9.36 | 14.745 | 18.15 | 20.13 | 25.515 | 31.185
16 | butt weld | CS | 6.05 | 6.48 | 6.48 | 7.13 | 10.15 | 7.13 | 12.31 | 15.34 | 18.14 | 22.03 | 25.92 |  | 16 | butt weld | CS | 9.075 | 9.72 | 9.72 | 10.695 | 15.225 | 10.695 | 18.465 | 23.01 | 27.21 | 33.045 | 38.88
18 | butt weld | CS | 6.8 | 7.78 | 7.29 | 9.48 | 12.64 | 8.02 | 15.55 | 19.44 | 23.81 | 27.95 | 32.81 |  | 18 | butt weld | CS | 10.2 | 11.67 | 10.935 | 14.22 | 18.96 | 12.03 | 23.325 | 29.16 | 35.715 | 41.925 | 49.215
20 | butt weld | CS | 8.1 | 8.91 | 8.1 | 11.07 | 15.39 | 8.91 | 19.17 | 24.03 | 29.7 | 35.1 | 40.5 |  | 20 | butt weld | CS | 12.15 | 13.365 | 12.15 | 16.605 | 23.085 | 13.365 | 28.755 | 36.045 | 44.55 | 52.65 | 60.75
24 | butt weld | CS | 9.72 | 12.64 | 9.72 | 15.55 | 21.71 | 10.69 | 27.54 | 35.64 | 45.36 | 51.84 | 59.94 |  | 24 | butt weld | CS | 14.58 | 18.96 | 14.58 | 23.325 | 32.565 | 16.035 | 41.31 | 53.46 | 68.04 | 77.76 | 89.91
30 | butt weld | CS | 12.15 | 15.8 | 12.15 |  |  | 13.37 | [6 empty] | 30 | butt weld | CS | 18.225 | 23.7 | 18.225 |  |  | 20.055
36 | butt weld | CS | 14.58 | 18.95 | 14.58 |  |  | 16.04 | [6 empty] | 36 | butt weld | CS | 21.87 | 28.425 | 21.87 |  |  | 24.06
42 | butt weld | CS |  |  | 17.01 |  |  | 18.71 | [6 empty] | 42 | butt weld | CS |  |  | 25.515 |  |  | 28.065
48 | butt weld | CS |  |  | 19.44 |  |  | 21.38 | [6 empty] | 48 | butt weld | CS |  |  | 29.16 |  |  | 32.07
54 | butt weld | CS |  |  | 21.87 |  |  | 24.06 | [6 empty] | 54 | butt weld | CS |  |  | 32.805 |  |  | 36.09
60 | butt weld | CS |  |  | 24.3 |  |  | 26.73 | [6 empty] | 60 | butt weld | CS |  |  | 36.45 |  |  | 40.095
STAINLES SSTEEL | [14 empty] | STAINLES SSTEEL
Dia. In. | Activity | Material | Sch 10 | Sch 30 | Std Wt | Sch 40 | Sch 60 | XS | Sch 80 | Sch 100 | Sch 120 | Sch 140 | Sch 160 | XXS | Dia. In. | Activity | Material | Sch 10 | Sch 30 | Std Wt | Sch 40 | Sch 60 | XS | Sch 80 | Sch 100 | Sch 120 | Sch 140 | Sch 160 | XXS
3/4 | butt weld | SS 304L | 1.75 | [11 empty] | 3/4 | butt weld | SS 304L | 2.625
1 | butt weld | SS 304L | 1.75 | [11 empty] | 1 | butt weld | SS 304L | 2.625
1-1/4 | butt weld | SS 304L | 1.75 | [11 empty] | 1-1/4 | butt weld | SS 304L | 2.625
1-1/2 | butt weld | SS 304L | 1.75 | [11 empty] | 1-1/2 | butt weld | SS 304L | 2.625
2 | butt weld | SS 304L | 1.75 | [11 empty] | 2 | butt weld | SS 304L | 2.625
THREADED
Dia. In. | Activity | Material | All Sch
1/8 | threaded | N/A | 0.2
1/4 | threaded | N/A | 0.2
3/8 | threaded | N/A | 0.2
1/2 | threaded | N/A | 0.2
3/4 | threaded | N/A | 0.28
1 | threaded | N/A | 0.34
1-1/4 | threaded | N/A | 0.4
1-1/2 | threaded | N/A | 0.44
2 | threaded | N/A | 0.53
2-1/2 | threaded | N/A | 0.89
3 | threaded | N/A | 1.06
3-1/2 | threaded | N/A | 1.24
4 | threaded | N/A | 1.42
5 | threaded | N/A | 2.32
6 | threaded | N/A | 2.78
bolt-up
Dia. In. | Activity | Material | 150# | 300# | 400# | 600# | 900# | 1500# | 2500#
1/2 | bolt up | N/A | 0.24 | 0.26 | 0.26 | 0.26 | 0.29 | 0.34 | 0.42
3/4 | bolt up | N/A | 0.36 | 0.39 | 0.39 | 0.39 | 0.43 | 0.51 | 0.63
1 | bolt up | N/A | 0.36 | 0.39 | 0.39 | 0.39 | 0.45 | 0.54 | 0.72
1-1/4 | bolt up | N/A | 0.36 | 0.39 | 0.39 | 0.39 | 0.49 | 0.58 | 0.75
1-1/2 | bolt up | N/A | 0.36 | 0.43 | 0.43 | 0.43 | 0.51 | 0.62 | 0.79
2 | bolt up | N/A | 0.39 | 0.78 | 0.78 | 0.78 | 0.84 | 0.9 | 1.05
2-1/2 | bolt up | N/A | 0.39 | 0.84 | 0.84 | 0.84 | 0.94 | 1.03 | 1.13
3 | bolt up | N/A | 0.38 | 0.86 | 0.8 | 0.86 | 0.9 | 1.13 | 1.22
3-1/2 | bolt up | N/A | 0.79 | 0.84 | 0.84 | 0.84 | 1.05 | 1.26 | 1.31
4 | bolt up | N/A | 0.78 | 0.84 | 0.9 | 0.9 | 1.14 | 1.38 | 1.5
5 | bolt up | N/A | 0.9 | 0.86 | 0.9 | 1.01 | 1.28 | 1.58 | 1.73
6 | bolt up | N/A | 0.86 | 1.26 | 1.35 | 1.53 | 1.71 | 2.07 | 2.16
8 | bolt up | N/A | 0.84 | 1.38 | 1.56 | 1.74 | 1.92 | 2.4 | 2.46
10 | bolt up | N/A | 1.35 | 2.03 | 2.25 | 2.55 | 2.63 | 3 | 3.15
12 | bolt up | N/A | 1.35 | 2.34 | 2.52 | 3.15 | 3.24 | 3.42 | 3.87
14 | bolt up | N/A | 1.79 | 2.84 | 3.15 | 3.26 | 3.36 | 3.68
16 | bolt up | N/A | 2.04 | 2.52 | 3.24 | 3.24 | 3.48 | 3.84
18 | bolt up | N/A | 2.3 | 3.78 | 4.05 | 4.19 | 4.32 | 4.46
20 | bolt up | N/A | 2.85 | 3.9 | 4.05 | 4.2 | 4.35 | 4.65
24 | bolt up | N/A | 3.24 | 3.96 | 4.14 | 4.32 | 4.5 | 5.76
30 | bolt up | N/A | 4.05 | 4.95
36 | bolt up | N/A | 4.86 | 5.94
42 | bolt up | N/A | 5.67 | 6.93
48 | bolt up | N/A | 6.48 | 7.92
54 | bolt up | N/A | 7.29 | 8.91
60 | bolt up | N/A | 8.1 | 9.9
VALVE HANDLING
Dia. In. | Activity | Material | Std Bore | XS Bore | Sch 160 Bore | XXS Bore
2 | welded valve | N/A | 0.65 | 0.65 | 0.65 | 1.1
2-1/2 | welded valve | N/A | 0.76 | 0.75 | 0.76 | 1.39
3 | welded valve | N/A | 0.93 | 0.93 | 0.93 | 1.83
4 | welded valve | N/A | 1.43 | 1.43 | 1.43 | 2.51
5 | welded valve | N/A | 2.37 | 2.37 | 2.37 | 3.35
6 | welded valve | N/A | 2.76 | 2.76 | 2.76 | 3.66
8 | welded valve | N/A | 3.93 | 3.93 | 3.93 | 4.17
10 | welded valve | N/A | 5.08 | 5.08 | 5.08 | 3.28
12 | welded valve | N/A | 6.18 | 6.18 | 6.18 | 0.42
14 | welded valve | N/A | 6.98 | 6.98 | 6.98
16 | welded valve | N/A | 8.84 | 8.84 | 8.84
18 | welded valve | N/A | 9.28 | 9.28 | 9.28
20 | welded valve | N/A | 9.9 | 9.9 | 9.9
24 | welded valve | N/A | 10.63 | 10.63 | 10.63
30 | welded valve | N/A | 16.44 | 16.44
36 | welded valve | N/A | 18.25 | 18.25
Dia. In. | Activity | Material | 150# | 300# | 600# | 900# | 1500# | 2500#
1/2 | flanged valve | N/A | 0.14 | 0.17 | 0.17 |  | 0.31
3/4 | flanged valve | N/A | 0.16 | 0.22 | 0.23 |  | 0.35
1 | flanged valve | N/A | 0.23 | 0.28 | 0.3 |  | 0.56
1-1/4 | flanged valve | N/A | 0.32 | 0.36 | 0.39
1-1/2 | flanged valve | N/A | 0.39 | 0.49 | 0.5 |  | 0.79
2 | flanged valve | N/A | 0.75 | 1.17 | 1.5 | 2.6 | 3.35 | 4.15
2-1/2 | flanged valve | N/A | 0.92 | 1.36 | 2.06 |  | 4.11 | 5.04
3 | flanged valve | N/A | 1.16 | 1.74 | 2.69 | 3.9 | 4.77 | 6.42
4 | flanged valve | N/A | 1.73 | 2.69 | 4.35 | 5.27 | 6.47 | 8.95
5 | flanged valve | N/A | 2.6 | 3.73 | 5.81 | 6.66
6 | flanged valve | N/A | 3.09 | 4.19 | 6.84 | 8.44 | 9.86 | 11.26
8 | flanged valve | N/A | 4.14 | 5.86 | 9.41 | 10.21 | 11.9 | 14.57
10 | flanged valve | N/A | 5.25 | 7.47 | 10.22 | 11.48 | 14.74 | 18.89
12 | flanged valve | N/A | 6.74 | 9.16 | 11.6 | 13.34 | 19.36 | 26.35
14 | flanged valve | N/A | 8.29 | 10.44 | 13.07 | 15.48 | 20.15
16 | flanged valve | N/A | 9.6 | 11.68 | 14.68 | 17.3 | 21.01
18 | flanged valve | N/A | 9.96 | 12.35 | 17.6 | 21
20 | flanged valve | N/A | 10.64 | 13.83 | 19.08 | 23.7
24 | flanged valve | N/A | 11.65 | 17.3 | 22.58 | 28.55
30 | flanged valve | N/A | 16.16 | 24.93 | 47.54
36 | flanged valve | N/A | 17.91 | 33.44 | 47.35
42 | flanged valve | N/A | 25.44 | 37.22 | 60.27
48 | flanged valve | N/A | 31.04
54 | flanged valve | N/A
60 | flanged valve | N/A
Pipe Support
Dia. In. | Activity | Fabriacte | Install
1/2 | Pipe Support | 2 | 2
3/4 | Pipe Support | 2 | 2
1 | Pipe Support | 2 | 2
1-1/4 | Pipe Support | 2 | 2
1-1/2 | Pipe Support | 2 | 2
2 | Pipe Support | 2 | 2
2-1/2 | Pipe Support | 2 | 2
3 | Pipe Support | 3 | 3
4 | Pipe Support | 3.5 | 3.5
5 | Pipe Support | 4 | 4
6 | Pipe Support | 4.5 | 4.5
8 | Pipe Support | 5 | 5
10 | Pipe Support | 5.5 | 5.5
12 | Pipe Support | 6 | 6
14 | Pipe Support | 6.5 | 6.5
16 | Pipe Support | 7 | 7
18 | Pipe Support | 7.5 | 7.5
20 | Pipe Support | 8 | 8
24 | Pipe Support | 8.5 | 8.5
Notes:
all rates based on MCAA's work activity method estimating units
valve rates are only the handling of the valve. The joining method will need to be captured separately
if any new units are created by your team need to be noted by highlighting the cell yellow

## Equipment Installation
Equipment ID | Foundation Material Cost | Foundation Manhours | Foundation Crew Mix Rate | Foundation Labor Cost | Foundation Total Cost | Equipment Setting Manhours | Equip. Setting Crew Mix Rate | Equip Setting Labor Cost | Equip. Setting Total Cost | Total Cost
Pump # 43 | 1155 | 6.6 | 95 | 627 | 1782 | 16 | 93.8 | 1500.8 | 1500.8 | 3282.8
Pump # 43 Containment | 1470 | 33.6 | 95 | 3192 | 4662 |  |  |  | 0 | 4662
Pump # 45 | 1155 | 26.4 | 95 | 2508 | 3663 | 16 | 93.8 | 1500.8 | 1500.8 | 5163.8
Pump # 46 | 1155 | 26.4 | 95 | 2508 | 3663 | 16 | 93.8 | 1500.8 | 1500.8 | 5163.8
Pump # 45/46 Containment | 1820 | 41.6 | 95 | 3952 | 5772 |  |  |  | 0 | 5772
Electrical Building (PH-02) | 9234.9444 | 395.7833 | 95 | 37599.4167 | 46834.3611 | by others | by others |  | by others | 46834.3611
Transformer | 2500 | 10 | 95 | 950 | 3450 | by others | by others |  | by others | 3450
SWBD 8 | 584.5 | 13.36 | 95 | 1269.2 | 1853.7 | by others | by others |  | by others | 1853.7
Totals | 19074.4444 | 553.7433 |  | 52605.6167 | 71680.0611 | 48 |  | 4502.4 | 4502.4 | 76182.4611

## NDE
Qty of Welds | # of 8-hr shifts | Cost on 8-hrs | # of 10-hr shifts | Cost on 10-hrs | # of 12-hr shifts | Cost on 12-hrs
872 | 54.5 | 98100 | 43.6 | 95920 | 36.3333 | 109000 | Weekdays
872 | 54.5 | 128075 | 43.6 | 113360 | 36.3333 | 138066.6667 | Weekends

## Material Pricing & civil
Material Pricing by the Foot
Carbon Steel |  | Civil/Foundations
Dia. In. | $/FT | Description | Material Cost | UOM | Manhours | UOM | Notes
1/2 | 5 | Excav/Place/Finish Conc. | 350 | per CY | 8 | per CY | used for Equipment Installation Only
3/4 | 6 | PS Foundation Type 1 | 650 | each | 15 | each | used for pipe supports
1 | 6.5 | PS Foundation Type 2 | 400 | each | 10 | each | used for pipe supports
1-1/4 | 7
1-1/2 | 8
2 | 9.5
2-1/2 | 10 | Pipe Supports Mat'l
3 | 10.75 | Dia. In. | Activity | Material Cost
3-1/2 | 11.5 | 1/2 | Pipe Support | 10
4 | 13.75 | 3/4 | Pipe Support | 15
5 | 15 | 1 | Pipe Support | 20
6 | 16.5 | 1-1/4 | Pipe Support | 25
8 | 18 | 1-1/2 | Pipe Support | 30
10 | 21 | 2 | Pipe Support | 40
12 | 24 | 2-1/2 | Pipe Support | 50
14 | 26 | 3 | Pipe Support | 60
16 | 29 | 4 | Pipe Support | 80
18 | 34 | 5 | Pipe Support | 100
20 | 40 | 6 | Pipe Support | 120
24 | 48 | 8 | Pipe Support | 160
|  | 10 | Pipe Support | 200
|  | 12 | Pipe Support | 240
|  | 14 | Pipe Support | 280
|  | 16 | Pipe Support | 320
|  | 18 | Pipe Support | 360
|  | 20 | Pipe Support | 400
|  | 24 | Pipe Support | 480

## Pipe Support Foundation
PS Foundation Type | Quantity | Material Unit Cost | Foundation Material Cost | Foundation Labor Unit | Foundation Manhours | Foundation Crew Mix Rate | Foundation Labor Cost | Foundation Total Cost
Type I | 6 | 650 | 3900 | 15 | 90 | 90 | 8100 | 12000
Type II | 56 | 400 | 22400 | 10 | 560 | 90 | 50400 | 72800
Totals | 62 |  | 26300 |  | 650 |  | 58500 | 84800

## Painting Pricing
Painting by the Foot
Dia. In. | $/FT | LF | Ext.$
.5 | 15 | 0 | 0
0.75 | 20 | 0 | 0
1 | 25 | 2.67 | 66.75
1.25 | 30 | 0 | 0
1.5 | 35 | 0 | 0
2 | 40 | 0.5 | 20
2.5 | 45 | 0 | 0
3 | 50 | 6.4 | 320
3.5 | 55 | 0 | 0
4 | 60 | 109.42 | 6565.2
5 | 65 | 0 | 0
6 | 70 | 162.75 | 11392.5
8 | 75 | 159.69 | 11976.75
10 | 80 | 414.1 | 33128
12 | 85 | 5426.25 | 461231.25
14 | 90 | 0 | 0
16 | 95 | 0 | 0
18 | 100 | 0 | 0
20 | 105 | 0 | 0
24 | 110 | 0 | 0
|  | Total Cost | 524700.45

## Crew Rates
Pipe Fitter - SHOP
Crew Mix No. 2 | Sacramento Fabrication Shop
| PRE |  | FM | GEN | SUPT. | 4th | 5th | 6th | 7th
| APPR | JNYMN |  | FM |  | APR | APR | APR | APR
# of Man |  | 5 | 1 |  |  |  | 1 |  | 2 | These quantities are for reference only. Teams should create the crew mix based upon the project dynamics
Straight Time |  | 100.7136 | 108.2876 | 111.1234 | 115.838 | 77.1393 | 86.4345 | 88.7977 | 91.1609
Overtime (1-1/2) |  | 123.7451 | 135.0099 | 139.2276 | 146.2396 | 92.8007 | 102.5566 | 106.0713 | 109.5861
Double Time (2) |  | 146.7766 | 161.7322 | 167.3318 | 176.6412 | 108.4621 | 118.6786 | 123.345 | 128.0113
SHOP CREW MIX | 97.8458 |  | OVERTIME + |  | 21.6503 |  | DOUBLE TIME + |  | 43.3005
Pipe Fitter - FIELD
Crew Mix No. 3
| PRE |  | Local 447 | Local 447 | SUPT. | 4th | 5th | 6th | 7th
| APPR | JNYMN | FM | GEN FM |  | APR | APR | APR | APR
# of Man |  | 4 | 1 |  |  |  |  | 1 | 1 | These quantities are for reference only. Teams should create the crew mix based upon the project dynamics
Straight Time |  | 97.7703 | 105.5876 | 108.4234 | 111.9422 | 72.2142 | 75.32 | 78.4358 | 81.5298
Overtime (1-1/2) |  | 119.2653 | 132.3099 | 136.5276 | 142.3459 | 84.6277 | 88.7694 | 92.9211 | 97.0452
Double Time (2) |  | 140.7602 | 159.0322 | 164.6318 | 172.7496 | 97.0412 | 102.2188 | 107.4064 | 112.5607
CREW MIX : | 93.8049 |  | OVERTIME + |  | 20.3861 |  | DOUBLE TIME + |  | 40.7722
Note: Be sure to provide Crew mix rates to the management team

## Contractor Supplied Equipment
Project Name: New Standard Renewables Terminal Expansion
Project Description: Piping Installation
Project Location: Stockton, CA
Description | UNIT | Quantity | Duration | Total Duration | Rate | TOTAL $ | IMPORTANT NOTES
Pickup Truck | wk | 1 | 12 | 12 | 480 | 5760
Gator | wk |  |  | 0 | 250 | 0
Fork Lift 5 Ton Gradall | wk | 2 | 12 | 24 | 1210 | 29040
Scissor Lift (30 ft) | mo |  |  | 0 | 1250 | 0
Scissor Lift (50 ft) | mo |  |  | 0 | 2400 | 0
JLG - 40 ft 4WD | mo |  |  | 0 | 2015 | 0
JLG - 60 ft 4WD | mo |  |  | 0 | 2550 | 0
250 amp Diesel Weld Machine | wk | 5 | 12 | 60 | 350 | 21000
Flat-bed Truck & Trailer | ea | 1 | 16 | 16 | 1200 | 19200
535 Pipe Machine (threader) | wk |  |  | 0 | 225 | 0
Chain Hoists - 2 ton | wk |  |  | 0 | 50 | 0
Compressor - 125 cfm | wk | 1 | 2 | 2 | 365 | 730
Generator - Honda / Yamaha | wk |  |  | 0 | 260 | 0
Test Pump (Gas - Hi Power) | wk | 1 | 2 | 2 | 255 | 510
Office Trailer (40'x10') | mo | 1 | 4 | 4 | 900 | 3600
Storage Container | mo | 1 | 4 | 4 | 300 | 1200
Other | [6 empty] | Please list any additional equipment you are including
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
TOTAL | [5 empty] | 81040