## Important Instructions
Take-off & Pricing Workbook Instructions
1 | Pay close attention to shop welds and field welds
2 | Read pop-up notes in column headers
3 | Only takeoff piping activities that are included in the drop-down menu
4 | Take-off all welds as butt welds
5 | Drawings included in the pipe takeoff were completed by a previous estimator. They are a gift. We do NOT recommend redoing the takeoff of those isos
6 | Assume that all pipe will be provided to you from the vendor in DRLs (40'-0" +/- long)
7 | Pre-fabrication in your Sacramento shop will dictate that 40' +/- is the longest spool you can pre-fabricate without needing a permitted oversize load
8 | "Price Proposal Sheet" tab and Gen Conditions tab MUST be printed and placed in your deliverables binder. Failure to do so may result in not receiving a score for that section
9 | Assume all piping is carbon steel and standard weight
10 | Plan for a minimum of 75% welds prefabricated in the shop to take advantage of welding productivity
11
12
13
14
15
16
17
18
19
20

## Price Proposal Sheet
Project Name: North Energy Renewables Terminal Expansion
Project Description: Piping Installation
Project Location: Stockton, CA
Shop Fabrication
Labor | Total Hrs | Total Dollars
Direct | 576.0815 | 56367.1447
Indirect |  | 0
| 576.0815 | 56367.1447
Field Installation
Labor | Total Hrs | Total Dollars
Direct | 707.7985 | 61904.3055
Pressure Testing | 64.9799 | 6095.4306
Indirect |  | 0
| 772.7784 | 67999.7361
HDD Preassembly & Assistance
Labor | Total Hrs | Total Dollars
Direct
Pressure Testing |  | 0
Indirect
| 0 | 0
Subcontractors | N/A | Dollars
Paint | n/a | 32924.25
HDD | n/a
NDE | n/a
Recap | Hours | Dollars
Labor (Direct) | 1348.8599 | 124366.8808
Labor (Indirect) | 0 | 0 | 0%
Material | n/a | 13406.975
Equipment/Tools | n/a | 0
Subcontractors | n/a | 32924.25
Total | 1348.8599 | 170698.1058
Profit & Overhead |  | 0
PF Shop Crew Rate (composite $ per MH) | 97.8458
PF Field Crew Rate (composite $ per MH) | 93.8049
Note on B20: Rick M. Carpenter: Pressure Testing = 10% of installation hours

## Gen Conditions
Project Name: | North Energy Renewables Terminal Expansion
Project Description: | Piping Installation
Project Location: | Stockton, California
Description | # of People | Days | Hours Per Shift | Total Hours | Rate | Total Costs | Important Notes
Safety Supervision |  |  |  | 0 | 75 | 0
Safety Training/Orientation |  |  |  | 0 | 80 | 0 | est. 4 hrs per person
Project Management |  |  |  | 0 | 100 | 0
General Foreman |  |  |  | 0 | 100 | 0
Clerical |  |  |  | 0 | 50 | 0
Field Engineering |  |  |  | 0 | 60 | 0
Superintendent |  |  |  | 0 | 120 | 0
Project Scheduler |  |  |  | 0 | 90 | 0
Document Control |  |  |  | 0 | 50 | 0
Non Working Foreman |  |  |  | 0 | 100 | 0
Detailing |  |  |  | 0 | 100 | 0
Welder Testing/Qualification |  |  |  | 0 | 80 | 0
QC Supervision |  |  |  | 0 | 80 | 0
Material Receiving/Control Crew |  |  |  | 0 | 80 | 0
Mobilization |  |  |  | 0 | 80 | 0
Cleaning |  |  |  | 0 | 40 | 0
Demobilization |  |  |  | 0 | 80 | 0
Other Miscellanous: |  |  |  | 0 | 75 | 0
0
0
|  |  | Total | 0 |  | 0

## Pipe Take-Off
TAKE OFF # | ACTIVITY | SIZE 1 | SIZE 2 | RATING | INSTALL QUANT | PURCH QUANT | LINE # | AREA | Special Sched | INSULATION | Pressure Test | PAINT | S/F | COMMENTS OR NOTES | SHOP LABOR UNIT | SHOPLABOR ADJ FACTOR | SHOP LABOR TOTAL | FIELD LABOR UNIT | FIELD LABOR ADJ FACTOR | FIELD LABOR TOTAL | MAT'L UNIT PRICE | MAT'L TOTAL
1 | PIPE HANDLING | 10 |  |  | 5.1 | 5.1 | STOT-10"-RD-354-A SH1 | TERMINAL |  |  | Y |  | S/F |  | 0.44 | 1 | 2.244 | 0.66 | 1 | 3.366 | 21 | 107.1 | ACTIVITY LIST
2 | SHOP BUTT WELD | 10 |  |  | 3 |  | STOT-10"-RD-354-A SH1 | TERMINAL |  |  | Y |  | S |  | 3.96 | 1 | 11.88 |  | 1 | 0 |  | 0 | PIPE HANDLING
3 | FIELD BUTT WELD | 10 |  |  | 1 |  | STOT-10"-RD-354-A SH1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 5.94 | 1 | 5.94 |  | 0 | PIPE SUPPORT
4 | SHOP BUTT WELD | 2 |  |  | 2 |  | STOT-10"-RD-354-A SH1 | TERMINAL |  |  | Y |  | S |  | 1.2 | 1 | 2.4 |  | 1 | 0 |  | 0 | TYPE 1 FOUNDATION
5 | BOLT UP | 10 |  | 150 | 1 |  | STOT-10"-RD-354-A SH1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 1.35 | 1 | 1.35 |  | 0 | TYPE 2 FOUNDATION
6 | BOLT UP | 2 |  | 150 | 2 |  | STOT-10"-RD-354-A SH1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.39 | 1 | 0.78 |  | 0 | BOLT UP
7 | PIPE HANDLING | 10 |  |  | 7.1 | 7.1 | STOT-10"-RD-355-A SH1 | TERMINAL |  |  | Y |  | S/F |  | 0.44 | 1 | 3.124 | 0.66 | 1 | 4.686 | 21 | 149.1 | SHOP BUTT WELD
8 | SHOP BUTT WELD | 10 |  |  | 4 |  | STOT-10"-RD-355-A SH1 | TERMINAL |  |  | Y |  | S |  | 3.96 | 1 | 15.84 |  | 1 | 0 |  | 0 | FIELD BUTT WELD
9 | SHOP BUTT WELD | 2 |  |  | 2 |  | STOT-10"-RD-355-A SH1 | TERMINAL |  |  | Y |  | S |  | 1.2 | 1 | 2.4 |  | 1 | 0 |  | 0
10 | FIELD BUTT WELD | 10 |  |  | 1 |  | STOT-10"-RD-355-A SH1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 5.94 | 1 | 5.94 |  | 0
11 | BOLT UP | 10 |  | 150 | 1 |  | STOT-10"-RD-355-A SH1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 1.35 | 1 | 1.35 |  | 0
12 | BOLT UP | 2 |  | 150 | 2 |  | STOT-10"-RD-355-A SH1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.39 | 1 | 0.78 |  | 0
13 | PIPE HANDLING | 10 |  |  | 35.9 | 35.9 | STOT-10-RD-363-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.44 | 1 | 15.796 | 0.66 | 1 | 23.694 | 21 | 753.9
14 | PIPE HANDLING | 6 |  |  | 3 | 3 | STOT-10-RD-363-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 0.29 | 1 | 0.87 | 0.44 | 1 | 1.32 | 16.5 | 49.5
15 | SHOP BUTT WELD | 10 |  |  | 7 |  | STOT-10-RD-363-A SH 1 | TERMINAL |  |  | Y |  | S |  | 3.96 | 1 | 27.72 |  | 1 | 0 |  | 0
16 | SHOP BUTT WELD | 6 |  |  | 4 |  | STOT-10-RD-363-A SH 1 | TERMINAL |  |  | Y |  | S |  | 2.48 | 1 | 9.92 |  | 1 | 0 |  | 0
17 | FIELD BUTT WELD | 10 |  |  | 1 |  | STOT-10-RD-363-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 5.94 | 1 | 5.94 |  | 0
18 | BOLT UP | 10 |  | 150 | 1 |  | STOT-10-RD-363-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 1.35 | 1 | 1.35 |  | 0
19 | BOLT UP | 1 |  | 150 | 4 |  | STOT-10-RD-363-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.39 | 1 | 1.56 |  | 0
20 | BOLT UP | 6 |  | 150 | 2 |  | STOT-10-RD-363-A SH 1 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.86 | 1 | 1.72 |  | 0
21 | PIPE SUPPORT | 10 |  |  | 4 | 4 | STOT-10-RD-363-A SH 1 | TERMINAL |  |  | Y |  | S/F |  | 5.5 | 1 | 22 | 5.5 | 1 | 22 | 200 | 800
22 | PIPE HANDLING | 10 |  |  | 82.9 | 82.9 | STOT-10-RD-363-A SH 2 | TERMINAL |  |  | Y |  | S/F |  | 0.44 | 1 | 36.476 | 0.66 | 1 | 54.714 | 21 | 1740.9
23 | SHOP BUTT WELD | 10 |  |  | 6 |  | STOT-10-RD-363-A SH 2 | TERMINAL |  |  | Y |  | S |  | 3.96 | 1 | 23.76 |  | 1 | 0 |  | 0
24 | FIELD BUTT WELD | 10 |  |  | 2 |  | STOT-10-RD-363-A SH 2 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 5.94 | 1 | 11.88 |  | 0
25 | PIPE SUPPORT | 10 |  |  | 4 | 4 | STOT-10-RD-363-A SH 2 | TERMINAL |  |  | Y |  | S/F |  | 5.5 | 1 | 22 | 5.5 | 1 | 22 | 200 | 800
26 | PIPE HANDLING | 10 |  |  | 30.5 | 30.5 | STOT-10-RD-363-A SH 3 | TERMINAL |  |  | Y |  | S/F |  | 0.44 | 1 | 13.42 | 0.66 | 1 | 20.13 | 21 | 640.5
27 | SHOP BUTT WELD | 10 |  |  | 3 |  | STOT-10-RD-363-A SH 3 | TERMINAL |  |  | Y |  | S |  | 3.96 | 1 | 11.88 |  | 1 | 0 |  | 0
28 | FIELD BUTT WELD | 10 |  |  | 1 |  | STOT-10-RD-363-A SH 3 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 5.94 | 1 | 5.94 |  | 0
29 | PIPE SUPPORT | 10 |  |  | 1 | 1 | STOT-10-RD-363-A SH 3 | TERMINAL |  |  | Y |  | S/F |  | 5.5 | 1 | 5.5 | 5.5 | 1 | 5.5 | 200 | 200
30 | PIPE HANDLING | 10 |  |  | 67.3 | 37.3 | STOT-10-RD-363-A SH 4 | TERMINAL |  |  | Y |  | S/F |  | 0.44 | 1 | 29.612 | 0.66 | 1 | 44.418 | 21 | 783.3
31 | PIPE HANDLING | 1 |  |  | 0.25 | 0.25 | STOT-10-RD-363-A SH 4 | TERMINAL |  |  | Y |  | S/F |  | 0.07 | 1 | 0.0175 | 0.11 | 1 | 0.0275 | 6.5 | 1.625
32 | SHOP BUTT WELD | 10 |  |  | 10 |  | STOT-10-RD-363-A SH 4 | TERMINAL |  |  | Y |  | S |  | 3.96 | 1 | 39.6 |  | 1 | 0 |  | 0
33 | SHOP BUTT WELD | 1 |  |  | 2 |  | STOT-10-RD-363-A SH 4 | TERMINAL |  |  | Y |  | S |  | 0.6 | 1 | 1.2 |  | 1 | 0 |  | 0
34 | FIELD BUTT WELD | 10 |  |  | 5 |  | STOT-10-RD-363-A SH 4 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 5.94 | 1 | 29.7 |  | 0
35 | PIPE SUPPORT | 10 |  |  | 6 | 6 | STOT-10-RD-363-A SH 4 | TERMINAL |  |  | Y |  | S/F |  | 5.5 | 1 | 33 | 5.5 | 1 | 33 | 200 | 1200
36 | PIPE HANDLING | 10 |  |  | 5.9 | 5.9 | STOT-10-RD-363-A SH 5 | TERMINAL |  |  | Y |  | S/F |  | 0.44 | 1 | 2.596 | 0.66 | 1 | 3.894 | 21 | 123.9
37 | SHOP BUTT WELD | 10 |  |  | 8 |  | STOT-10-RD-363-A SH 5 | TERMINAL |  |  | Y |  | S |  | 3.96 | 1 | 31.68 |  | 1 | 0 |  | 0
38 | PIPE HANDLING | 10 |  |  | 48 | 48 | STOT-10-RD-363-A SH 6 | TERMINAL |  |  | Y |  | S/F |  | 0.44 | 1 | 21.12 | 0.66 | 1 | 31.68 | 21 | 1008
39 | SHOP BUTT WELD | 10 |  |  | 3 |  | STOT-10-RD-363-A SH 6 | TERMINAL |  |  | Y |  | S |  | 3.96 | 1 | 11.88 |  | 1 | 0 |  | 0
40 | FIELD BUTT WELD | 10 |  |  | 1 |  | STOT-10-RD-363-A SH 6 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 5.94 | 1 | 5.94 |  | 0
41 | PIPE SUPPORT | 10 |  |  | 6 | 6 | STOT-10-RD-363-A SH 6 | TERMINAL |  |  | Y |  | S/F |  | 5.5 | 1 | 33 | 5.5 | 1 | 33 | 200 | 1200
42 | PIPE HANDLING | 10 |  |  | 94.9 | 94.9 | STOT-10-RD-363-A SH 7 | TERMINAL |  |  | Y |  | S/F |  | 0.44 | 1 | 41.756 | 0.66 | 1 | 62.634 | 21 | 1992.9
43 | SHOP BUTT WELD | 10 |  |  | 1 |  | STOT-10-RD-363-A SH 7 | TERMINAL |  |  | Y |  | S |  | 3.96 | 1 | 3.96 |  | 1 | 0 |  | 0
44 | FIELD BUTT WELD | 10 |  |  | 3 |  | STOT-10-RD-363-A SH 7 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 5.94 | 1 | 17.82 |  | 0
45 | PIPE SUPPORT | 10 |  |  | 5 | 5 | STOT-10-RD-363-A SH 7 | TERMINAL |  |  | Y |  | S/F |  | 5.5 | 1 | 27.5 | 5.5 | 1 | 27.5 | 200 | 1000
46 | PIPE HANDLING | 10 |  |  | 29.25 | 29.25 | STOT-10-RD-363-A SH 8 | TERMINAL |  |  | Y |  | S/F |  | 0.44 | 1 | 12.87 | 0.66 | 1 | 19.305 | 21 | 614.25
47 | SHOP BUTT WELD | 10 |  |  | 8 |  | STOT-10-RD-363-A SH 8 | TERMINAL |  |  | Y |  | S |  | 3.96 | 1 | 31.68 |  | 1 | 0 |  | 0
48 | FIELD BUTT WELD | 10 |  |  | 1 |  | STOT-10-RD-363-A SH 8 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 5.94 | 1 | 5.94 |  | 0
49 | PIPE HANDLING | 10 |  |  | 2 | 2 | STOT-10-RD-363-A SH 9 | TERMINAL |  |  | Y |  | S/F |  | 0.44 | 1 | 0.88 | 0.66 | 1 | 1.32 | 21 | 42
50 | SHOP BUTT WELD | 10 |  |  | 5 |  | STOT-10-RD-363-A SH 9 | TERMINAL |  |  | Y |  | S |  | 3.96 | 1 | 19.8 |  | 1 | 0 |  | 0
51 | SHOP BUTT WELD | 2 |  |  | 1 |  | STOT-10-RD-363-A SH 9 | TERMINAL |  |  | Y |  | S |  | 1.2 | 1 | 1.2 |  | 1 | 0 |  | 0
52 | BOLT UP | 10 |  | 150 | 4 |  | STOT-10-RD-363-A SH 9 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 1.35 | 1 | 5.4 |  | 0
53 | BOLT UP | 2 |  | 150 | 2 |  | STOT-10-RD-363-A SH 9 | TERMINAL |  |  | Y |  | F |  |  | 1 | 0 | 0.39 | 1 | 0.78 |  | 0
54 | PIPE SUPPORT | 10 |  |  | 1 | 1 | STOT-10-RD-363-A SH 9 | TERMINAL |  |  | Y |  | S/F |  | 5.5 | 1 | 5.5 | 5.5 | 1 | 5.5 | 200 | 200
55 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
56 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
57 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
58 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
59 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
60 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
61 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
62 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
63 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
64 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
65 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
66 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
67 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
68 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
69 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
70 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
71 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
72 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
73 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
74 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
75 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
76 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
77 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
78 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
79 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
80 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
81 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
82 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
83 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
84 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
85 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
86 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
87 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
88 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
89 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
90 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
91 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
92 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
93 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
94 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
95 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
96 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
97 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
98 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
99 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
100 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
101 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
102 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
103 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
104 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
105 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
106 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
107 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
108 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
109 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
110 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
111 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
112 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
113 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
114 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
115 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
116 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
117 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
118 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
119 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
120 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
121 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
122 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
123 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
124 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
125 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
126 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
127 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
128 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
129 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
130 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
131 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
132 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
133 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
134 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
135 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
136 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
137 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
138 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
139 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
140 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
141 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
142 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
143 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
144 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
145 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
146 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
147 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
148 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
149 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
150 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
151 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
152 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
153 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
154 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
155 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
156 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
157 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
158 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
159 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
160 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
161 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
162 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
163 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
164 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
165 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
166 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
167 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
168 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
169 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
170 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
171 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
172 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
173 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
174 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
175 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
176 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
177 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
178 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
179 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
180 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
181 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
182 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
183 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
184 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
185 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
186 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
187 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
188 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
189 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
190 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
191 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
192 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
193 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
194 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
195 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
196 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
197 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
198 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
199 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
200 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
201 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
202 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
203 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
204 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
205 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
206 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
207 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
208 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
209 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
210 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
211 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
212 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
213 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
214 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
215 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
216 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
217 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
218 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
219 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
220 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
221 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
222 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
223 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
224 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
225 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
226 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
227 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
228 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
229 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
230 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
231 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
232 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
233 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
234 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
235 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
236 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
237 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
238 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
239 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
240 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
241 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
242 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
243 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
244 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
245 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
246 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
247 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
248 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
249 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
250 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
251 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
252 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
253 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
254 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
255 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
256 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
257 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
258 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
259 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
260 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
261 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
262 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
263 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
264 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
265 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
266 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
267 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
268 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
269 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
270 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
271 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
272 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
273 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
274 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
275 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
276 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
277 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
278 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
279 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
280 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
281 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
282 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
283 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
284 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
285 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
286 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
287 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
288 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
289 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
290 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
291 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
292 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
293 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
294 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
295 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
296 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
297 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
298 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
299 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
300 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
301 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
302 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
303 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
304 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
305 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
306 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
307 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
308 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
309 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
310 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
311 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
312 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
313 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
314 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
315 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
316 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
317 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
318 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
319 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
320 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
321 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
322 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
323 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
324 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
325 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
326 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
327 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
328 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
329 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
330 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
331 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
332 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
333 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
334 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
335 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
336 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
337 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
338 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
339 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
340 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
341 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
342 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
343 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
344 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
345 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
346 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
347 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
348 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
349 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
350 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
351 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
352 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
353 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
354 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
355 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
356 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
357 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
358 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
359 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
360 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
361 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
362 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
363 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
364 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
365 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
366 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
367 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
368 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
369 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
370 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
371 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
372 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
373 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
374 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
375 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
376 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
377 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
378 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
379 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
380 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
381 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
382 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
383 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
384 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
385 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
386 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
387 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
388 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
389 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
390 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
391 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
392 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
393 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
394 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
395 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
396 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
397 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
398 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
399 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
400 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
401 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
402 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
403 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
404 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
405 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
406 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
407 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
408 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
409 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
410 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
411 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
412 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
413 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
414 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
415 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
416 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
417 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
418 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
419 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
420 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
421 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
422 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
423 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
424 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
425 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
426 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
427 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
428 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
429 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
430 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
431 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
432 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
433 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
434 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
435 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
436 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
437 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
438 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
439 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
440 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
441 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
442 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
443 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
444 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
445 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
446 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
447 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
448 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
449 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
450 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
451 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
452 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
453 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
454 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
455 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
456 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
457 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
458 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
459 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
460 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
461 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
462 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
463 | [15 empty] | 1 | 0 |  | 1 | 120 |  | 0
464 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
465 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
466 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
467 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
468 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
469 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
470 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
471 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
472 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
473 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
474 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
475 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
476 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
477 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
478 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
479 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
480 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
481 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
482 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
483 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
484 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
485 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
486 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
487 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
488 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
489 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
490 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
491 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
492 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
493 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
494 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
495 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
496 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
497 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
498 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
499 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
500 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
501 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
502 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
503 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
504 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
505 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
506 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
507 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
508 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
509 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
510 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
511 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
512 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
513 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
514 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
515 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
516 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
517 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
518 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
519 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
520 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
521 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
522 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
523 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
524 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
525 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
526 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
527 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
528 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
529 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
530 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
531 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
532 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
533 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
534 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
535 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
536 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
537 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
538 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
539 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
540 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
541 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
542 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
543 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
544 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
545 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
546 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
547 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
548 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
549 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
550 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
551 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
552 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
553 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
554 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
555 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
556 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
557 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
558 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
559 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
560 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
561 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
562 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
563 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
564 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
565 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
566 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
567 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
568 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
569 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
570 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
571 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
572 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
573 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
574 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
575 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
576 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
577 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
578 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
579 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
580 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
581 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
582 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
583 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
584 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
585 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
586 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
587 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
588 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
589 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
590 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
591 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
592 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
593 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
594 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
595 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
596 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
597 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
598 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
599 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
600 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
601 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
602 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
603 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
604 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
605 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
606 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
607 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
608 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
609 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
610 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
611 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
612 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
613 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
614 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
615 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
616 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
617 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
618 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
619 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
620 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
621 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
622 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
623 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
624 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
625 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
626 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
627 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
628 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
629 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
630 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
631 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
632 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
633 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
634 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
635 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
636 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
637 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
638 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
639 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
640 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
641 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
642 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
643 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
644 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
645 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
646 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
647 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
648 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
649 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
650 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
651 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
652 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
653 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
654 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
655 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
656 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
657 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
658 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
659 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
660 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
661 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
662 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
663 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
664 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
665 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
666 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
667 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
668 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
669 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
670 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
671 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
672 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
673 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
674 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
675 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
676 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
677 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
678 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
679 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
680 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
681 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
682 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
683 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
684 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
685 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
686 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
687 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
688 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
689 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
690 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
691 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
692 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
693 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
694 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
695 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
696 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
697 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
698 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
699 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
700 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
701 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
702 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
703 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
704 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
705 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
706 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
707 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
708 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
709 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
710 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
711 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
712 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
713 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
714 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
715 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
716 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
717 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
718 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
719 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
720 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
721 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
722 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
723 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
724 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
725 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
726 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
727 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
728 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
729 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
730 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
731 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
732 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
733 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
734 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
735 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
736 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
737 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
738 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
739 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
740 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
741 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
742 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
743 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
744 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
745 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
746 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
747 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
748 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
749 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
750 | [15 empty] | 1 | 0 |  | 1 | 0 |  | 0
1190 | TOTALS | [12 empty] | TOTALS |  |  | 576.0815 |  |  | 649.7985 |  | 13406.975
[14 empty] | Qty Shop Welds | 69
[14 empty] | Qty Field Welds | 16
[14 empty] | Total Welds | 85
[14 empty] | HDD total MH | 0
Note on I1: Rick M. Carpenter: This may help you break down your labor on the Price Proposal Sheet
Note on L1: Steve Kraak: Yes or No? This will help you determine pressure testing hours
Note on N1: Steve Kraak: SHOP OR FIELD ACTIVITY? S=SHOP, F=FIELD, SOME ACTIVITES MAY BE BOTH. S/F=SHOP AND FIELD.
Note on F16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Changed from 5 to 7. I counted 4 butt welds and 3 olet (branchette) welds

## Piping Labor Units
PIPE HANDLING -SHOP | [14 empty] | PIPE HANDLING -FIELD
Dia. In. | Activity | Material | Sch 20 | Sch 30 | Std Wt | Sch 40 | Sch 60 | XS | Sch 80 | Sch 100 | Sch 120 | Sch 140 | Sch 160 | XXS | Dia. In. | Activity | Material | Sch 20 | Sch 30 | Std Wt | Sch 40 | Sch 60 | XS | Sch 80 | Sch 100 | Sch 120 | Sch 140 | Sch 160 | XXS
1/2 | pipe handling | CS |  |  | 0.06 |  |  | 0.062 |  |  |  |  | 0.068 | 0.074 | 1/2 | pipe handling | CS |  |  | 0.09 |  |  | 0.093 |  |  |  |  | 0.102 | 0.111 | 1.25
3/4 | pipe handling | CS |  |  | 0.065 |  |  | 0.069 |  |  |  |  | 0.078 | 0.086 | 3/4 | pipe handling | CS |  |  | 0.0975 |  |  | 0.1035 |  |  |  |  | 0.117 | 0.129
1 | pipe handling | CS |  |  | 0.074 |  |  | 0.08 |  |  |  |  | 0.093 | 0.106 | 1 | pipe handling | CS |  |  | 0.111 |  |  | 0.12 |  |  |  |  | 0.1395 | 0.159
1-1/4 | pipe handling | CS |  |  | 0.083 |  |  | 0.093 |  |  |  |  | 0.108 | 0.131 | 1-1/4 | pipe handling | CS |  |  | 0.1245 |  |  | 0.1395 |  |  |  |  | 0.162 | 0.1965
1-1/2 | pipe handling | CS |  |  | 0.091 |  |  | 0.102 |  |  |  |  | 0.125 | 0.15 | 1-1/2 | pipe handling | CS |  |  | 0.1365 |  |  | 0.153 |  |  |  |  | 0.1875 | 0.225
2 | pipe handling | CS |  |  | 0.107 |  |  | 0.124 |  |  |  |  | 0.167 | 0.192 | 2 | pipe handling | CS |  |  | 0.1605 |  |  | 0.186 |  |  |  |  | 0.2505 | 0.288
2-1/2 | pipe handling | CS |  |  | 0.14 |  |  | 0.164 |  |  |  |  | 0.208 | 0.255 | 2-1/2 | pipe handling | CS |  |  | 0.21 |  |  | 0.246 |  |  |  |  | 0.312 | 0.3825
3 | pipe handling | CS |  |  | 0.168 |  |  | 0.204 |  |  |  |  | 0.258 | 0.29 | 3 | pipe handling | CS |  |  | 0.252 |  |  | 0.306 |  |  |  |  | 0.387 | 0.435
3-1/2 | pipe handling | CS |  |  | 0.192 |  |  | 0.238 | [5 empty] | 0.32 | 3-1/2 | pipe handling | CS |  |  | 0.288 |  |  | 0.357 | [5 empty] | 0.48
4 | pipe handling | CS |  |  | 0.218 |  |  | 0.255 |  |  | 0.291 |  | 0.316 | 0.354 | 4 | pipe handling | CS |  |  | 0.327 |  |  | 0.3825 |  |  | 0.4365 |  | 0.474 | 0.531
5 | pipe handling | CS |  |  | 0.26 |  |  | 0.294 |  |  | 0.349 |  | 0.39 | 0.431 | 5 | pipe handling | CS |  |  | 0.39 |  |  | 0.441 |  | 0 | 0.5235 | 0 | 0.585 | 0.6465
6 | pipe handling | CS |  |  | 0.291 |  |  | 0.346 |  |  | 0.415 |  | 0.477 | 0.524 | 6 | pipe handling | CS |  |  | 0.4365 |  |  | 0.519 |  | 0 | 0.6225 | 0 | 0.7155 | 0.786
8 | pipe handling | CS | 0.314 | 0.331 | 0.358 |  | 0.406 | 0.446 |  | 0.516 | 0.538 | 0.55 | 0.562 | 0.56 | 8 | pipe handling | CS | 0.471 | 0.4965 | 0.537 |  | 0.609 | 0.669 |  | 0.774 | 0.807 | 0.825 | 0.843 | 0.84
10 | pipe handling | CS | 0.355 | 0.398 | 0.441 |  | 0.522 | 0.507 | 0.541 | 0.562 | 0.589 | 0.614 | 0.639 | 0.614 | 10 | pipe handling | CS | 0.5325 | 0.597 | 0.6615 |  | 0.783 | 0.7605 | 0.8115 | 0.843 | 0.8835 | 0.921 | 0.9585 | 0.921
12 | pipe handling | CS | 0.393 | 0.465 | 0.515 | 0.515 | 0.556 | 0.526 | 0.585 | 0.619 | 0.654 | 0.683 | 0.727 | 0.654 | 12 | pipe handling | CS | 0.5895 | 0.6975 | 0.7725 | 0.7725 | 0.834 | 0.789 | 0.8775 | 0.9285 | 0.981 | 1.0245 | 1.0905 | 0.981
14 | pipe handling | CS | 0.48 | 0.526 | 0.526 | 0.539 | 0.581 | 0.537 | 0.62 | 0.666 | 0.702 | 0.745 | 0.788 |  | 14 | pipe handling | CS | 0.72 | 0.789 | 0.789 | 0.8085 | 0.8715 | 0.8055 | 0.93 | 0.999 | 1.053 | 1.1175 | 1.182 | 0
16 | pipe handling | CS | 0.523 | 0.541 | 0.541 | 0.574 | 0.624 | 0.556 | 0.676 | 0.731 | 0.783 | 0.845 | 0.894 |  | 16 | pipe handling | CS | 0.7845 | 0.8115 | 0.8115 | 0.861 | 0.936 | 0.834 | 1.014 | 1.0965 | 1.1745 | 1.2675 | 1.341 | 0
18 | pipe handling | CS | 0.536 | 0.576 | 0.556 | 0.617 | 0.679 | 0.574 | 0.741 | 0.812 | 0.884 | 0.945 | 1.016 |  | 18 | pipe handling | CS | 0.804 | 0.864 | 0.834 | 0.9255 | 1.0185 | 0.861 | 1.1115 | 1.218 | 1.326 | 1.4175 | 1.524 | 0
20 | pipe handling | CS | 0.571 | 0.614 | 0.571 | 0.65 | 0.733 | 0.593 | 0.813 | 0.903 | 0.986 | 1.075 | 1.153 |  | 20 | pipe handling | CS | 0.8565 | 0.921 | 0.8565 | 0.975 | 1.0995 | 0.8895 | 1.2195 | 1.3545 | 1.479 | 1.6125 | 1.7295 | 0
24 | pipe handling | CS | 0.602 | 0.683 | 0.602 | 0.741 | 0.867 | 0.629 | 0.978 | 1.116 | 1.248 | 1.354 | 1.476 |  | 24 | pipe handling | CS | 0.903 | 1.0245 | 0.903 | 1.1115 | 1.3005 | 0.9435 | 1.467 | 1.674 | 1.872 | 2.031 | 2.214 | 0
30 | pipe handling | CS | 0.707 | 0.78 | 0.648 |  |  | 0.684 | [6 empty] | 30 | pipe handling | CS | 1.0605 | 1.17 | 0.972 |  |  | 1.026
36 | pipe handling | CS | 0.766 | 0.853 | 0.694 |  |  | 0.739 | [6 empty] | 36 | pipe handling | CS | 1.149 | 1.2795 | 1.041 |  |  | 1.1085
42 | pipe handling | CS |  |  | 0.74 |  |  | 0.794 | [6 empty] | 42 | pipe handling | CS |  |  | 1.11 |  |  | 1.191
48 | pipe handling | CS |  |  | 0.785 |  |  | 0.85 | [6 empty] | 48 | pipe handling | CS |  |  | 1.1775 |  |  | 1.275
54 | pipe handling | CS |  |  | 0.831 |  |  | 1.115 | [6 empty] | 54 | pipe handling | CS |  |  | 1.2465 |  |  | 1.6725
60 | pipe handling | CS |  |  | 0.877 |  |  | 1.193 | [6 empty] | 60 | pipe handling | CS |  |  | 1.3155 |  |  | 1.7895
PIPE JOINTS-SHOP | [14 empty] | PIPE JOINTS -FIELD
CARBON STEEL | [14 empty] | CARBON STEEL
Dia. In. | Activity | Material | Sch 20 | Sch 30 | Std Wt | Sch 40 | Sch 60 | XS | Sch 80 | Sch 100 | Sch 120 | Sch 140 | Sch 160 | XXS | Dia. In. | Activity | Material | Sch 20 | Sch 30 | Std Wt | Sch 40 | Sch 60 | XS | Sch 80 | Sch 100 | Sch 120 | Sch 140 | Sch 160 | XXS
1/2 | butt weld | CS |  |  | 0.3 |  |  | 0.33 |  |  |  |  | 0.39 | 0.48 | 1/2 | butt weld | CS |  |  | 0.45 |  |  | 0.495 |  |  |  |  | 0.585 | 0.72
3/4 | butt weld | CS |  |  | 0.45 |  |  | 0.5 |  |  |  |  | 0.59 | 0.72 | 3/4 | butt weld | CS |  |  | 0.675 |  |  | 0.75 |  |  |  |  | 0.885 | 1.08
1 | butt weld | CS |  |  | 0.6 |  |  | 0.66 |  |  |  |  | 0.78 | 0.96 | 1 | butt weld | CS |  |  | 0.9 |  |  | 0.99 |  |  |  |  | 1.17 | 1.44
1-1/4 | butt weld | CS |  |  | 0.75 |  |  | 0.83 |  |  |  |  | 0.98 | 1.2 | 1-1/4 | butt weld | CS |  |  | 1.125 |  |  | 1.245 |  |  |  |  | 1.47 | 1.8
1-1/2 | butt weld | CS |  |  | 0.9 |  |  | 0.99 |  |  |  |  | 1.17 | 1.44 | 1-1/2 | butt weld | CS |  |  | 1.35 |  |  | 1.485 |  |  |  |  | 1.755 | 2.16
2 | butt weld | CS |  |  | 1.2 |  |  | 1.32 |  |  |  |  | 1.56 | 1.92 | 2 | butt weld | CS |  |  | 1.8 |  |  | 1.98 |  |  |  |  | 2.34 | 2.88
2-1/2 | butt weld | CS |  |  | 1.5 |  |  | 1.66 |  |  |  |  | 1.94 | 2.49 | 2-1/2 | butt weld | CS |  |  | 2.25 |  |  | 2.49 |  |  |  |  | 2.91 | 3.735
3 | butt weld | CS |  |  | 1.57 |  |  | 1.72 |  |  |  |  | 2.14 | 2.91 | 3 | butt weld | CS |  |  | 2.355 |  |  | 2.58 |  |  |  |  | 3.21 | 4.365
3-1/2 | butt weld | CS |  |  | 1.79 |  |  | 1.96 | [5 empty] | 3.35 | 3-1/2 | butt weld | CS |  |  | 2.685 |  |  | 2.94 |  |  |  |  | 0 | 5.025
4 | butt weld | CS |  |  | 1.94 |  |  | 2.14 |  |  | 2.55 |  | 2.86 | 3.77 | 4 | butt weld | CS |  |  | 2.91 |  |  | 3.21 |  |  | 3.825 |  | 4.29 | 5.655
5 | butt weld | CS |  |  | 2.23 |  |  | 2.42 |  |  | 3.38 |  | 3.76 | 4.59 | 5 | butt weld | CS |  |  | 3.345 |  |  | 3.63 |  |  | 5.07 |  | 5.64 | 6.885
6 | butt weld | CS |  |  | 2.48 |  |  | 2.71 |  |  | 4.33 |  | 4.8 | 5.57 | 6 | butt weld | CS |  |  | 3.72 |  |  | 4.065 |  |  | 6.495 |  | 7.2 | 8.355
8 | butt weld | CS | 2.71 | 2.82 | 3.13 |  | 3.34 | 3.65 |  | 4.38 | 6.16 | 6.58 | 7.1 | 7.31 | 8 | butt weld | CS | 4.065 | 4.23 | 4.695 |  | 5.01 | 5.475 |  | 6.57 | 9.24 | 9.87 | 10.65 | 10.965
10 | butt weld | CS | 3.43 | 3.7 | 3.96 |  | 4.62 | 4.62 | 5.54 | 6.2 | 8.32 | 8.98 | 10.56 | 8.98 | 10 | butt weld | CS | 5.145 | 5.55 | 5.94 |  | 6.93 | 6.93 | 8.31 | 9.3 | 12.48 | 13.47 | 15.84 | 13.47
12 | butt weld | CS | 4.21 | 4.7 | 4.86 | 4.86 | 6.16 | 5.51 | 7.61 | 9.23 | 10.85 | 12.8 | 16.2 | 11.02 | 12 | butt weld | CS | 6.315 | 7.05 | 7.29 | 7.29 | 9.24 | 8.265 | 11.415 | 13.845 | 16.275 | 19.2 | 24.3 | 16.53
14 | butt weld | CS | 5.29 | 5.67 | 5.67 | 5.67 | 7.94 | 6.24 | 9.83 | 12.1 | 13.42 | 17.01 | 20.79 |  | 14 | butt weld | CS | 7.935 | 8.505 | 8.505 | 8.505 | 11.91 | 9.36 | 14.745 | 18.15 | 20.13 | 25.515 | 31.185
16 | butt weld | CS | 6.05 | 6.48 | 6.48 | 7.13 | 10.15 | 7.13 | 12.31 | 15.34 | 18.14 | 22.03 | 25.92 |  | 16 | butt weld | CS | 9.075 | 9.72 | 9.72 | 10.695 | 15.225 | 10.695 | 18.465 | 23.01 | 27.21 | 33.045 | 38.88
18 | butt weld | CS | 6.8 | 7.78 | 7.29 | 9.48 | 12.64 | 8.02 | 15.55 | 19.44 | 23.81 | 27.95 | 32.81 |  | 18 | butt weld | CS | 10.2 | 11.67 | 10.935 | 14.22 | 18.96 | 12.03 | 23.325 | 29.16 | 35.715 | 41.925 | 49.215
20 | butt weld | CS | 8.1 | 8.91 | 8.1 | 11.07 | 15.39 | 8.91 | 19.17 | 24.03 | 29.7 | 35.1 | 40.5 |  | 20 | butt weld | CS | 12.15 | 13.365 | 12.15 | 16.605 | 23.085 | 13.365 | 28.755 | 36.045 | 44.55 | 52.65 | 60.75
24 | butt weld | CS | 9.72 | 12.64 | 9.72 | 15.55 | 21.71 | 10.69 | 27.54 | 35.64 | 45.36 | 51.84 | 59.94 |  | 24 | butt weld | CS | 14.58 | 18.96 | 14.58 | 23.325 | 32.565 | 16.035 | 41.31 | 53.46 | 68.04 | 77.76 | 89.91
30 | butt weld | CS | 12.15 | 15.8 | 12.15 |  |  | 13.37 | [6 empty] | 30 | butt weld | CS | 18.225 | 23.7 | 18.225 |  |  | 20.055
36 | butt weld | CS | 14.58 | 18.95 | 14.58 |  |  | 16.04 | [6 empty] | 36 | butt weld | CS | 21.87 | 28.425 | 21.87 |  |  | 24.06
42 | butt weld | CS |  |  | 17.01 |  |  | 18.71 | [6 empty] | 42 | butt weld | CS |  |  | 25.515 |  |  | 28.065
48 | butt weld | CS |  |  | 19.44 |  |  | 21.38 | [6 empty] | 48 | butt weld | CS |  |  | 29.16 |  |  | 32.07
54 | butt weld | CS |  |  | 21.87 |  |  | 24.06 | [6 empty] | 54 | butt weld | CS |  |  | 32.805 |  |  | 36.09
60 | butt weld | CS |  |  | 24.3 |  |  | 26.73 | [6 empty] | 60 | butt weld | CS |  |  | 36.45 |  |  | 40.095
STAINLES SSTEEL | [14 empty] | STAINLES SSTEEL
Dia. In. | Activity | Material | Sch 10 | Sch 30 | Std Wt | Sch 40 | Sch 60 | XS | Sch 80 | Sch 100 | Sch 120 | Sch 140 | Sch 160 | XXS | Dia. In. | Activity | Material | Sch 10 | Sch 30 | Std Wt | Sch 40 | Sch 60 | XS | Sch 80 | Sch 100 | Sch 120 | Sch 140 | Sch 160 | XXS
3/4 | butt weld | SS 304L | 1.75 | [11 empty] | 3/4 | butt weld | SS 304L | 2.625
1 | butt weld | SS 304L | 1.75 | [11 empty] | 1 | butt weld | SS 304L | 2.625
1-1/4 | butt weld | SS 304L | 1.75 | [11 empty] | 1-1/4 | butt weld | SS 304L | 2.625
1-1/2 | butt weld | SS 304L | 1.75 | [11 empty] | 1-1/2 | butt weld | SS 304L | 2.625
2 | butt weld | SS 304L | 1.75 | [11 empty] | 2 | butt weld | SS 304L | 2.625
THREADED
Dia. In. | Activity | Material | All Sch
1/8 | threaded | N/A | 0.2
1/4 | threaded | N/A | 0.2
3/8 | threaded | N/A | 0.2
1/2 | threaded | N/A | 0.2
3/4 | threaded | N/A | 0.28
1 | threaded | N/A | 0.34
1-1/4 | threaded | N/A | 0.4
1-1/2 | threaded | N/A | 0.44
2 | threaded | N/A | 0.53
2-1/2 | threaded | N/A | 0.89
3 | threaded | N/A | 1.06
3-1/2 | threaded | N/A | 1.24
4 | threaded | N/A | 1.42
5 | threaded | N/A | 2.32
6 | threaded | N/A | 2.78
bolt-up
Dia. In. | Activity | Material | 150# | 300# | 400# | 600# | 900# | 1500# | 2500#
1/2 | bolt up | N/A | 0.24 | 0.26 | 0.26 | 0.26 | 0.29 | 0.34 | 0.42
3/4 | bolt up | N/A | 0.36 | 0.39 | 0.39 | 0.39 | 0.43 | 0.51 | 0.63
1 | bolt up | N/A | 0.36 | 0.39 | 0.39 | 0.39 | 0.45 | 0.54 | 0.72
1-1/4 | bolt up | N/A | 0.36 | 0.39 | 0.39 | 0.39 | 0.49 | 0.58 | 0.75
1-1/2 | bolt up | N/A | 0.36 | 0.43 | 0.43 | 0.43 | 0.51 | 0.62 | 0.79
2 | bolt up | N/A | 0.39 | 0.78 | 0.78 | 0.78 | 0.84 | 0.9 | 1.05
2-1/2 | bolt up | N/A | 0.39 | 0.84 | 0.84 | 0.84 | 0.94 | 1.03 | 1.13
3 | bolt up | N/A | 0.38 | 0.86 | 0.8 | 0.86 | 0.9 | 1.13 | 1.22
3-1/2 | bolt up | N/A | 0.79 | 0.84 | 0.84 | 0.84 | 1.05 | 1.26 | 1.31
4 | bolt up | N/A | 0.78 | 0.84 | 0.9 | 0.9 | 1.14 | 1.38 | 1.5
5 | bolt up | N/A | 0.9 | 0.86 | 0.9 | 1.01 | 1.28 | 1.58 | 1.73
6 | bolt up | N/A | 0.86 | 1.26 | 1.35 | 1.53 | 1.71 | 2.07 | 2.16
8 | bolt up | N/A | 0.84 | 1.38 | 1.56 | 1.74 | 1.92 | 2.4 | 2.46
10 | bolt up | N/A | 1.35 | 2.03 | 2.25 | 2.55 | 2.63 | 3 | 3.15
12 | bolt up | N/A | 1.35 | 2.34 | 2.52 | 3.15 | 3.24 | 3.42 | 3.87
14 | bolt up | N/A | 1.79 | 2.84 | 3.15 | 3.26 | 3.36 | 3.68
16 | bolt up | N/A | 2.04 | 2.52 | 3.24 | 3.24 | 3.48 | 3.84
18 | bolt up | N/A | 2.3 | 3.78 | 4.05 | 4.19 | 4.32 | 4.46
20 | bolt up | N/A | 2.85 | 3.9 | 4.05 | 4.2 | 4.35 | 4.65
24 | bolt up | N/A | 3.24 | 3.96 | 4.14 | 4.32 | 4.5 | 5.76
30 | bolt up | N/A | 4.05 | 4.95
36 | bolt up | N/A | 4.86 | 5.94
42 | bolt up | N/A | 5.67 | 6.93
48 | bolt up | N/A | 6.48 | 7.92
54 | bolt up | N/A | 7.29 | 8.91
60 | bolt up | N/A | 8.1 | 9.9
VALVE HANDLING
Dia. In. | Activity | Material | Std Bore | XS Bore | Sch 160 Bore | XXS Bore
2 | welded valve | N/A | 0.65 | 0.65 | 0.65 | 1.1
2-1/2 | welded valve | N/A | 0.76 | 0.75 | 0.76 | 1.39
3 | welded valve | N/A | 0.93 | 0.93 | 0.93 | 1.83
4 | welded valve | N/A | 1.43 | 1.43 | 1.43 | 2.51
5 | welded valve | N/A | 2.37 | 2.37 | 2.37 | 3.35
6 | welded valve | N/A | 2.76 | 2.76 | 2.76 | 3.66
8 | welded valve | N/A | 3.93 | 3.93 | 3.93 | 4.17
10 | welded valve | N/A | 5.08 | 5.08 | 5.08 | 3.28
12 | welded valve | N/A | 6.18 | 6.18 | 6.18 | 0.42
14 | welded valve | N/A | 6.98 | 6.98 | 6.98
16 | welded valve | N/A | 8.84 | 8.84 | 8.84
18 | welded valve | N/A | 9.28 | 9.28 | 9.28
20 | welded valve | N/A | 9.9 | 9.9 | 9.9
24 | welded valve | N/A | 10.63 | 10.63 | 10.63
30 | welded valve | N/A | 16.44 | 16.44
36 | welded valve | N/A | 18.25 | 18.25
Dia. In. | Activity | Material | 150# | 300# | 600# | 900# | 1500# | 2500#
1/2 | flanged valve | N/A | 0.14 | 0.17 | 0.17 |  | 0.31
3/4 | flanged valve | N/A | 0.16 | 0.22 | 0.23 |  | 0.35
1 | flanged valve | N/A | 0.23 | 0.28 | 0.3 |  | 0.56
1-1/4 | flanged valve | N/A | 0.32 | 0.36 | 0.39
1-1/2 | flanged valve | N/A | 0.39 | 0.49 | 0.5 |  | 0.79
2 | flanged valve | N/A | 0.75 | 1.17 | 1.5 | 2.6 | 3.35 | 4.15
2-1/2 | flanged valve | N/A | 0.92 | 1.36 | 2.06 |  | 4.11 | 5.04
3 | flanged valve | N/A | 1.16 | 1.74 | 2.69 | 3.9 | 4.77 | 6.42
4 | flanged valve | N/A | 1.73 | 2.69 | 4.35 | 5.27 | 6.47 | 8.95
5 | flanged valve | N/A | 2.6 | 3.73 | 5.81 | 6.66
6 | flanged valve | N/A | 3.09 | 4.19 | 6.84 | 8.44 | 9.86 | 11.26
8 | flanged valve | N/A | 4.14 | 5.86 | 9.41 | 10.21 | 11.9 | 14.57
10 | flanged valve | N/A | 5.25 | 7.47 | 10.22 | 11.48 | 14.74 | 18.89
12 | flanged valve | N/A | 6.74 | 9.16 | 11.6 | 13.34 | 19.36 | 26.35
14 | flanged valve | N/A | 8.29 | 10.44 | 13.07 | 15.48 | 20.15
16 | flanged valve | N/A | 9.6 | 11.68 | 14.68 | 17.3 | 21.01
18 | flanged valve | N/A | 9.96 | 12.35 | 17.6 | 21
20 | flanged valve | N/A | 10.64 | 13.83 | 19.08 | 23.7
24 | flanged valve | N/A | 11.65 | 17.3 | 22.58 | 28.55
30 | flanged valve | N/A | 16.16 | 24.93 | 47.54
36 | flanged valve | N/A | 17.91 | 33.44 | 47.35
42 | flanged valve | N/A | 25.44 | 37.22 | 60.27
48 | flanged valve | N/A | 31.04
54 | flanged valve | N/A
60 | flanged valve | N/A
Pipe Support
Dia. In. | Activity | Fabriacte | Install
1/2 | Pipe Support | 2 | 2
3/4 | Pipe Support | 2 | 2
1 | Pipe Support | 2 | 2
1-1/4 | Pipe Support | 2 | 2
1-1/2 | Pipe Support | 2 | 2
2 | Pipe Support | 2 | 2
2-1/2 | Pipe Support | 2 | 2
3 | Pipe Support | 3 | 3
4 | Pipe Support | 3.5 | 3.5
5 | Pipe Support | 4 | 4
6 | Pipe Support | 4.5 | 4.5
8 | Pipe Support | 5 | 5
10 | Pipe Support | 5.5 | 5.5
12 | Pipe Support | 6 | 6
14 | Pipe Support | 6.5 | 6.5
16 | Pipe Support | 7 | 7
18 | Pipe Support | 7.5 | 7.5
20 | Pipe Support | 8 | 8
24 | Pipe Support | 8.5 | 8.5
Notes:
all rates based on MCAA's work activity method estimating units
valve rates are only the handling of the valve. The joining method will need to be captured separately
if any new units are created by your team need to be noted by highlighting the cell yellow

## Equipment Installation
Equipment ID | Foundation Material Cost | Foundation Manhours | Foundation Crew Mix Rate | Foundation Labor Cost | Foundation Total Cost | Equipment Setting Manhours | Equip. Setting Crew Mix Rate | Equip Setting Labor Cost | Equip. Setting Total Cost | Total Cost
Pump # 43 |  |  | 95 | 0 | 0 | 16 |  | 0 | 0 | 0
Pump # 43 Containment |  |  | 95 | 0 | 0 |  |  |  | 0 | 0
Pump # 45 |  |  | 95 | 0 | 0 | 16 |  | 0 | 0 | 0
Pump # 46 |  |  | 95 | 0 | 0 | 16 |  | 0 | 0 | 0
Pump # 45/46 Containment |  |  | 95 | 0 | 0 |  |  |  | 0 | 0
Electrical Building (PH-02) |  |  | 95 | 0 | 0 | by others | by others |  | by others | 0
Transformer |  | 10 | 95 | 950 | 950 | by others | by others |  | by others | 950
SWBD 8 |  |  | 95 | 0 | 0 | by others | by others |  | by others | 0
Totals | 0 | 10 |  | 950 | 950 | 48 |  | 0 | 0 | 950

## NDE
Qty of Welds | # of 8-hr shifts | Cost on 8-hrs | # of 10-hr shifts | Cost on 10-hrs | # of 12-hr shifts | Cost on 12-hrs
| 0 | 0 | 0 | 0 | 0 | 0 | Weekdays
| 0 | 0 | 0 | 0 | 0 | 0 | Weekends

## Material Pricing & civil
Material Pricing by the Foot
Carbon Steel |  | Civil/Foundations
Dia. In. | $/FT | Description | Material Cost | UOM | Manhours | UOM | Notes
1/2 | 5 | Excav/Place/Finish Conc. | 350 | per CY | 8 | per CY | used for Equipment Installation Only
3/4 | 6 | PS Foundation Type 1 | 650 | each | 15 | each | used for pipe supports
1 | 6.5 | PS Foundation Type 2 | 400 | each | 10 | each | used for pipe supports
1-1/4 | 7
1-1/2 | 8
2 | 9.5
2-1/2 | 10 | Pipe Supports Mat'l
3 | 10.75 | Dia. In. | Activity | Material Cost
3-1/2 | 11.5 | 1/2 | Pipe Support | 10
4 | 13.75 | 3/4 | Pipe Support | 15
5 | 15 | 1 | Pipe Support | 20
6 | 16.5 | 1-1/4 | Pipe Support | 25
8 | 18 | 1-1/2 | Pipe Support | 30
10 | 21 | 2 | Pipe Support | 40
12 | 24 | 2-1/2 | Pipe Support | 50
14 | 26 | 3 | Pipe Support | 60
16 | 29 | 4 | Pipe Support | 80
18 | 34 | 5 | Pipe Support | 100
20 | 40 | 6 | Pipe Support | 120
24 | 48 | 8 | Pipe Support | 160
|  | 10 | Pipe Support | 200
|  | 12 | Pipe Support | 240
|  | 14 | Pipe Support | 280
|  | 16 | Pipe Support | 320
|  | 18 | Pipe Support | 360
|  | 20 | Pipe Support | 400
|  | 24 | Pipe Support | 480

## Pipe Support Foundation
PS Foundation Type | Quantity | Material Unit Cost | Foundation Material Cost | Foundation Labor Unit | Foundation Manhours | Foundation Crew Mix Rate | Foundation Labor Cost | Foundation Total Cost
Type I |  |  | 0 |  | 0 | 90 | 0 | 0
Type II |  |  | 0 |  | 0 | 90 | 0 | 0
Totals | 0 |  | 0 |  | 0 |  | 0 | 0

## Painting Pricing
Painting by the Foot
Dia. In. | $/FT | LF | Ext.$
.5 | 15 | 0 | 0
0.75 | 20 | 0 | 0
1 | 25 | 0.25 | 6.25
1.25 | 30 | 0 | 0
1.5 | 35 | 0 | 0
2 | 40 | 0 | 0
2.5 | 45 | 0 | 0
3 | 50 | 0 | 0
3.5 | 55 | 0 | 0
4 | 60 | 0 | 0
5 | 65 | 0 | 0
6 | 70 | 3 | 210
8 | 75 | 0 | 0
10 | 80 | 408.85 | 32708
12 | 85 | 0 | 0
14 | 90 | 0 | 0
16 | 95 | 0 | 0
18 | 100 | 0 | 0
20 | 105 | 0 | 0
24 | 110 | 0 | 0
|  | Total Cost | 32924.25

## Crew Rates
Pipe Fitter - SHOP
Crew Mix No. 2 | Sacramento Fabrication Shop
| PRE |  | FM | GEN | SUPT. | 4th | 5th | 6th | 7th
| APPR | JNYMN |  | FM |  | APR | APR | APR | APR
# of Man |  | 5 | 1 |  |  |  | 1 |  | 2 | These quantities are for reference only. Teams should create the crew mix based upon the project dynamics
Straight Time |  | 100.7136 | 108.2876 | 111.1234 | 115.838 | 77.1393 | 86.4345 | 88.7977 | 91.1609
Overtime (1-1/2) |  | 123.7451 | 135.0099 | 139.2276 | 146.2396 | 92.8007 | 102.5566 | 106.0713 | 109.5861
Double Time (2) |  | 146.7766 | 161.7322 | 167.3318 | 176.6412 | 108.4621 | 118.6786 | 123.345 | 128.0113
SHOP CREW MIX | 97.8458 |  | OVERTIME + |  | 21.6503 |  | DOUBLE TIME + |  | 43.3005
Pipe Fitter - FIELD
Crew Mix No. 3
| PRE |  | Local 447 | Local 447 | SUPT. | 4th | 5th | 6th | 7th
| APPR | JNYMN | FM | GEN FM |  | APR | APR | APR | APR
# of Man |  | 4 | 1 |  |  |  |  | 1 | 1 | These quantities are for reference only. Teams should create the crew mix based upon the project dynamics
Straight Time |  | 97.7703 | 105.5876 | 108.4234 | 111.9422 | 72.2142 | 75.32 | 78.4358 | 81.5298
Overtime (1-1/2) |  | 119.2653 | 132.3099 | 136.5276 | 142.3459 | 84.6277 | 88.7694 | 92.9211 | 97.0452
Double Time (2) |  | 140.7602 | 159.0322 | 164.6318 | 172.7496 | 97.0412 | 102.2188 | 107.4064 | 112.5607
CREW MIX : | 93.8049 |  | OVERTIME + |  | 20.3861 |  | DOUBLE TIME + |  | 40.7722
Note: Be sure to provide Crew mix rates to the management team

## Contractor Supplied Equipment
Project Name: New Standard Renewables Terminal Expansion
Project Description: Piping Installation
Project Location: Stockton, CA
Description | UNIT | Quantity | Duration | Total Duration | Rate | TOTAL $ | IMPORTANT NOTES
Pickup Truck | wk |  |  | 0 | 480 | 0
Gator | wk |  |  | 0 | 250 | 0
Fork Lift 5 Ton Gradall | wk |  |  | 0 | 1210 | 0
Scissor Lift (30 ft) | mo |  |  | 0 | 1250 | 0
Scissor Lift (50 ft) | mo |  |  | 0 | 2400 | 0
JLG - 40 ft 4WD | mo |  |  | 0 | 2015 | 0
JLG - 60 ft 4WD | mo |  |  | 0 | 2550 | 0
250 amp Diesel Weld Machine | wk |  |  | 0 | 350 | 0
Flat-bed Truck & Trailer | ea |  |  | 0 | 1200 | 0
535 Pipe Machine (threader) | wk |  |  | 0 | 225 | 0
Chain Hoists - 2 ton | wk |  |  | 0 | 50 | 0
Compressor - 125 cfm | wk |  |  | 0 | 365 | 0
Generator - Honda / Yamaha | wk |  |  | 0 | 260 | 0
Test Pump (Gas - Hi Power) | wk |  |  | 0 | 255 | 0
Office Trailer (40'x10') | mo |  |  | 0 | 900 | 0
Storage Container | mo |  |  | 0 | 300 | 0
Other | [6 empty] | Please list any additional equipment you are including
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
TOTAL | [5 empty] | 0