Date: 1/22/23

Job: NER Dock 10/11 Project

Quote # 412

Price: See below

Hank’s Directional Drilling is pleased to provide pricing for your upcoming project:

Provide all labor, material, equipment, and tooling to complete the horizontal directional drill scope per contract documents: approx. 2,733 LF of drilling for a 12-inch pipeline

Pricing Breakdown

Drill and install approximately 2,733 12” pipeline	$400/ft

Mobilization/Demobilization				$25,000 ea.

Schedule based upon working a 6x10’s schedule Monday – Saturday. Estimated days to complete from start of mobilization is 40 days. Pull-back duration is 2 days.

Quotation Terms:

- Proposal includes:

  - All submittals per requirements of contract documents

  - Drilling rig(s), drill cab(s) and power unit(s)

  - Mud pumping units

  - Vacuum and dump trucks

  - Tool Containers

  - Gyro steering tool system & tracer wire.

  - Provide all in-hole tooling required to complete the project

  - Provide pipe rollers and rolling cradles for pull back

  - Provide and install surface casing

  - Provide all labor required for drill operations

  - Provide pull head

- Proposal excludes:

  - All permitting

  - Locating of entry and exit locations

  - Potholing existing utilities

  - Permanent pipeline, welding, and test of the pipe

  - Equipment and manpower to handle the pipeline during pullback

  - All traffic control measures

  - All SWPPP plan engineering, execution and maintenance

- All work stoppages that arise through no fault to Hank’s Directional Drilling, will be billed at $25,000 per calendar day (no crew onsite).