## Cover
[DATE]
Top Pick Contracting
110 Elite Road
Only the Best, CA 67899
Attention: | Chloe Taylor
Reference: | [PROJECT NAME]
Subject: | [MCE-XX] | Rev. 0 | [CHANGE ESTIMATE REFERENCE]
Dear | Chloe Taylor,
We are in receipt of the above subject document and herein notify you of our cost impact. Our cost estimate to complete this work is:
Lump Sum Proposal |  | #VALUE!
We propose to:
We have attached a copy of the cost estimate backup for your review. This proposal is valid for 30 days after which time it is subject to reevaluation.
This proposal is based on [ ] straight time or [ ] premium time basis.
We are quoting a time extension of ___ working day(s) to perform the change installation once direction to proceed with the change work is received.
Exclusions:
[INPUT AS NECESSARY FROM LIST BELOW]
Please issue the appropriate change order for this amount to our contract.
Sincerely,
MURRAY COMPANY
[PROJECT MANAGER NAME]
Project Manager
2090 Farallon Drive • San Leandro, CA 94577 • Ph 510.962.9459 • www.murraycompany.com • CA Lic. #162382
Design Build • Biopharmaceutical • Semiconductor • Underground Utilities • Industrial • Plumbing & HVAC • Healthcare
EXCLUSIONS
All Exclusions in accordance with original contract
Indirect impacts such as: weather delays/out of sequence work/trade stacking/ripple effect/restricted access.
3rd Party QAQC
Analytical Testing
Any scope not specifically listed within above inclusions.
Architectural Cutting/Patching
Architectural sheet metal, including flashing, counter flashing and louvers
Auxiliary structural steel
BIM Modeling or Clash Coordination
Boiler flues
Bolts and Gaskets for installation
Bonds
Central Debris Facilities and Debris Boxes
Composite Cleanup
Concrete cutting and/or pour back
Consequential or Liquidated Damages
Controls, Control Wiring and Devices
Coring
Costs for storage of owner furnished equipment
Cranes and Rigging
Cross connection testing
Cutting and patching of the building
Dedicated QAQC Manager/Administrator
Design, materials, and fabrication of seismic restraints for equipment provided by others
Dewatering
Disconnects and motor starters
Dishwashers
Dust control, containment or HEPA
Electrical power
Electrical Wiring, Conduit
Engineering
Detailing and spool drawings
Equipment Startup and Assistance
Escalation
Evacuation, charging & startup of refrigerant systems
Excavation and site work
Factory source inspections
Fire protection
Furnishing of Gas Manifolds for bulk systems
Hazardous Material Abatement
Heat tracing and power for heat tracing
Hot Taps or Line Freezes
Inspector Costs
Installation
Installation of access doors
Instrumentation and controls
Insulation of owner provided equipment
Insurance - General Liability
Insurance - Worker's Compensation
Labor for pre-commissioning and commissioning assistance
Low Voltage Wiring, Conduit, and Accessories
Materials
Meters and fees
Mock-ups
Monitoring and life safety systems or controls
NDE Testing (X-ray, Hydrotesting, Welding)
Nuts, Bolts and Gaskets
Offsets, fittings, pipe, etc. necessary to route all systems after the MEP coordination process (we have included offsets as reasonably inferable from the contract documents)
Pipe Insulation
Painting; including prime, finished touch-up, and identification stencil
Parking Fees
Parking Labor (is to be provided within 4th of mile from the work area at no cost)
Permits and Plan Check Fees
Pipe stress analysis
Piping below grade
Plywood backboards
Protection or Repair of Landscaping
Radio equipment rental
Refurbishing of existing equipment
Removal or Replacement of Ceiling Tiles
Roof cut and patch
SBE and DVBE
Seismic bracing or upgrade of existing systems
Seismic calculations or anchor details for owner furnished equipment
Setting/Anchoring of Emission benches and devices (see allowance above)
Sewer assessments and acreage fees
Shipping Cost
Shower pans and enclosures
Sleeves at Partitions
Standby Time, Overtime, Double Time, Shift Rate
Start-up and commissioning of owner provided equipment
Supply of Solenoid panels or valves of any nature
Temp Services
Temporary Electrical, Water and Sanitary Facilities
Testing, adjusting and balancing of air, water and steam systems
Umbilical supports at lab benches
Upgrade of Existing
Variable frequency drives and motor control centers
Warranty beyond one (1) year from beneficial occupancy

## Recap
PROJECT NAME: | [PROJECT NAME] | [5 empty] | DATE: | [DATE]
FIXTURES & EQUIPMENT |  |  |  | QTY | PRICE EACH |  | WARRANTY
TAG | DESCRIPTION |  |  |  |  | FREIGHT | 3% | TOTAL $
0
0
0
0
0
0
0
[7 empty] | TOTAL: | 0
PIPING - SHOP |  | Hrs (ST) | Hrs (OT) | Hrs (DT) | Hrs (Shift) | Labor Rate | Material $ | TOTAL $
Fabrication Labor [Straight Time] | [5 empty] | 123 | 0 | 0
Fabrication Labor [Overtime] | [5 empty] | 174 |  | 0
Fabrication Labor [Doubletime] | [5 empty] | 234 |  | 0
Fabrication Labor [Shift Time] | [5 empty] | 140 |  | 0
Shop General Foreman [20% of Labor] | [7 empty] | 0
Consumables | [6 empty] | 0 | 0
Piping Shop Totals: |  | 0 | 0 | 0 | 0 |  | 0 | 0
PIPING - FIELD |  | Hrs (ST) | Hrs (OT) | Hrs (DT) | Hrs (Shift) | Labor Rate | Material $ | TOTAL $
Piping System Install Labor [Straight Time] |  | 0 |  |  |  |  | 0 | #VALUE!
Piping System Install Labor [Overtime]
Piping System Install Labor [Doubletime]
Piping System Install Labor [Shift Time]
Consumables | [6 empty] | 0 | 0
Cartage | [6 empty] | 0 | 0
Rentals | [7 empty] | 0
Foreman | [7 empty] | 0
General Foreman | [7 empty] | 0
Piping Field Totals: |  | 0 | 0 | 0 | 0 |  | 0 | #VALUE!
PROJECT MANAGEMENT |  | Hrs (ST) | Hrs (OT) | Hrs (DT) | Hrs (Shift) | Labor Rate |  | TOTAL $
Project Executive | [5 empty] | 250 |  | 0
Project Manager | [5 empty] | 210 |  | 0
Project Engineer | [5 empty] | 100 |  | 0
Superintendent | [5 empty] | 175 |  | 0
Safety Professional | [5 empty] | 110 |  | 0
QAQC Manager | [5 empty] | 125 |  | 0
Project Mgmt Totals: |  | 0 | 0 | 0 | 0 |  |  | 0
SUBCONTRACTS | [7 empty] | TOTAL $
[SCOPE]
[SCOPE]
[SCOPE]
[SCOPE]
[SCOPE]
[SCOPE]
[SCOPE]
[SCOPE]
[SCOPE]
[SCOPE]
[SCOPE]
[SCOPE]
[SCOPE]
[SCOPE]
[SCOPE]
[SCOPE]
[SCOPE]
[SCOPE]
[SCOPE]
[SCOPE]
[6 empty] | Subcontract Total: |  | 0
[5 empty] | Tax: |  | 10% | 0
[5 empty] | Subtotal Costs: |  |  | #VALUE!
[5 empty] | Subcontractor OH+Fee: |  | 5% | 0
[5 empty] | Material/Tax Overhead + Fee: |  | 15% | 0
[5 empty] | Labor Overhead + Fee: |  | 15% | #VALUE!
[5 empty] | Warranty: |  | 1% | #VALUE!
[5 empty] | Submitted Total: |  |  | #VALUE!
Note on C21: Stuart Campbell: Take off hours populate here. Move hours from here to Piping Shop, OT/DT/SHIFT columns as necessary

## Takeoff
PROJECT NAME: | [PROJECT NAME] |  |  |  |  | DATE: | [DATE]
PIPING |  |  |  | PRICE PER UNIT | LABOR PER UNIT | EXTENDED | EXTENDED
SYSTEM | QTY | SIZE | DESCRIPTION |  |  | MATERIAL PRICE | LABOR HRS
|  | 2 | Pipe - Cast Iron NoHub | 6.08 | 0.07 | 0 | 0
|  | 3 | Pipe - Cast Iron NoHub | 8.4 | 0.08 | 0 | 0
|  | 4 | Pipe - Cast Iron NoHub | 12.4 | 0.1 | 0 | 0
|  | 2 | Pipe - Carbon Steel | 9.05 | 0.1 | 0 | 0
|  | 4 | Pipe - Carbon Steel | 13.5 | 0.14 | 0 | 0
|  | 6 | Pipe - Carbon Steel | 23.74 | 0.2 | 0 | 0
|  | 8 | Pipe - Carbon Steel | 35.73 | 0.25 | 0 | 0
|  | 10 | Pipe - Carbon Steel | 50.65 | 0.32 | 0 | 0
|  | 1/2 | Pipe - Copper Type L | 2.68 | 0.04 | 0 | 0
|  | 3/4 | Pipe - Copper Type L | 4.38 | 0.06 | 0 | 0
|  | 1 | Pipe - Copper Type L | 6.24 | 0.07 | 0 | 0
|  | 1-1/2 | Pipe - Copper Type L | 7.24 | 0.08 | 0 | 0
|  | 2 | Pipe - Copper Type L | 12.24 | 0.1 | 0 | 0
|  | 3 | Pipe - Copper Type L | 69.43 | 0.14 | 0 | 0
|  | 2 | Fitting - Cast Iron NoHub - Coupling | 6.26 | 0.24 | 0 | 0
|  | 3 | Fitting - Cast Iron NoHub - Coupling | 7.55 | 0.27 | 0 | 0
|  | 4 | Fitting - Cast Iron NoHub - Coupling | 4.5 | 0.35 | 0 | 0
|  | 2 | Fitting - Cast Iron NoHub - 1/4 Bend Long Sweep | 9 | 0.45 | 0 | 0
|  | 2 | Fitting - Cast Iron NoHub - 1/4 Bend Medium Sweep | 9 | 0.45 | 0 | 0
|  | 2 | Fitting - Cast Iron NoHub - 1/4 Bend Short Sweep | 12.5 | 0.45 | 0 | 0
|  | 3 | Fitting - Cast Iron NoHub - 1/4 Bend Short Sweep | 16 | 0.75 | 0 | 0
|  | 3 | Fitting - Cast Iron NoHub - 1/8 Bend | 10.5 | 0.75 | 0 | 0
|  | 2 | Fitting - Cast Iron NoHub - Combination | 13 | 0.65 | 0 | 0
|  | 3 | Fitting - Cast Iron NoHub - Combination | 17 | 0.89 | 0 | 0
|  | 3x3x2 | Fitting - Cast Iron NoHub - Combination Reducing | 16 | 0.95 | 0 | 0
|  | 4x4x2 | Fitting - Cast Iron NoHub - Combination Reducing | 21 | 1.1 | 0 | 0
|  | 2 | Fitting - Cast Iron NoHub - Wye | 11.33 | 0.65 | 0 | 0
|  | 3 | Fitting - Cast Iron NoHub - Wye | 14.55 | 0.75 | 0 | 0
|  | 2" x 8 | Fitting - Carbon Steel - Thread-o-Let | 31.92 | 1.33 | 0 | 0
|  | 2" x 10 | Fitting - Carbon Steel - Thread-o-Let | 31.92 | 1.33 | 0 | 0
|  | 6 | Fitting - Carbon Steel - Tee | 286.95 | 9.41 | 0 | 0
|  | 8 | Fitting - Carbon Steel - Tee | 493.78 | 12 | 0 | 0
|  | 10 | Fitting - Carbon Steel - Tee | 951.57 | 15.21 | 0 | 0
|  | 4x4x3 | Fitting - Carbon Steel - Tee Reducing | 164.56 | 6.64 | 0 | 0
|  | 8x8x6 | Fitting - Carbon Steel - Tee Reducing | 632.74 | 11.38 | 0 | 0
|  | 10x10x8 | Fitting - Carbon Steel - Tee Reducing | 1156 | 14.64 | 0 | 0
|  | 2 | Fitting - Carbon Steel - Cap | 18.08 | 1.58 | 0 | 0
|  | 3 | Fitting - Carbon Steel - Cap | 22.89 | 1.95 | 0 | 0
|  | 4 | Fitting - Carbon Steel - Cap | 33.48 | 2.41 | 0 | 0
|  | 1/2 | Fitting - Copper - 90 Deg Elbow | 1.08 | 0.24 | 0 | 0
|  | 3/4 | Fitting - Copper - 90 Deg Elbow | 2.5 | 0.31 | 0 | 0
|  | 1 | Fitting - Copper - 90 Deg Elbow | 6 | 0.35 | 0 | 0
|  | 1-1/2 | Fitting - Copper - 90 Deg Elbow | 8 | 0.45 | 0 | 0
|  | 2 | Fitting - Copper - 90 Deg Elbow | 12.34 | 0.74 | 0 | 0
|  | 1/2 | Fitting - Copper - Cap | 0.83 | 0.11 | 0 | 0
|  | 1/2 | Fitting - Copper - Coupling | 0.66 | 0.24 | 0 | 0
|  | 3/4 | Fitting - Copper - Coupling | 1.5 | 0.31 | 0 | 0
|  | 1 | Fitting - Copper - Coupling | 3.23 | 0.35 | 0 | 0
|  | 1-1/2 | Fitting - Copper - Coupling | 4.56 | 0.45 | 0 | 0
|  | 2 | Fitting - Copper - Coupling | 5.78 | 0.69 | 0 | 0
|  | 3 | Fitting - Copper - Coupling | 34.4 | 1.71 | 0 | 0
|  | 1/2 | Fitting - Copper - Tee | 2 | 0.39 | 0 | 0
|  | 1 | Fitting - Copper - Tee | 13.5 | 0.53 | 0 | 0
|  | 1-1/2 | Fitting - Copper - Tee | 19.3 | 0.78 | 0 | 0
|  | 2 | Fitting - Copper - Tee | 24.46 | 1.1 | 0 | 0
|  | 3/4x3/4x1/2 | Fitting - Copper - Tee Reducing | 4 | 0.47 | 0 | 0
|  | 1x1x1/2 | Fitting - Copper - Tee Reducing | 16 | 0.5 | 0 | 0
|  | 3 | Flange - Carbon Steel - Weld Neck | 31.1 | 0.2 | 0 | 0
|  | 4 | Flange - Carbon Steel - Weld Neck | 37.39 | 0.25 | 0 | 0
|  | 6 | Flange - Carbon Steel - Weld Neck | 54.5 | 0.47 | 0 | 0
|  | 8 | Flange - Carbon Steel - Weld Neck | 96.08 | 0.62 | 0 | 0
|  | 10 | Flange - Carbon Steel - Weld Neck | 154.38 | 0.75 | 0 | 0
|  | 3 | Flange - Carbon Steel - Blind | 50.95 | 0.2 | 0 | 0
|  | 4 | Flange - Carbon Steel - Blind | 71.61 | 0.25 | 0 | 0
|  | 6 | Flange - Carbon Steel - Blind | 108.99 | 0.27 | 0 | 0
|  | 8 | Flange - Carbon Steel - Blind | 177.29 | 0.32 | 0 | 0
|  | 10 | Flange - Carbon Steel - Blind | 341.13 | 0.48 | 0 | 0
|  | 2 | Valve - Ball - Threaded | 203.89 | 1.65 | 0 | 0
|  | 2 | Valve - Ball - Welded | 233.595 | 2.57 | 0 | 0
|  | 3 | Valve - Butterfly - Flanged | 790.59 | 1.03 | 0 | 0
|  | 3 | Valve - Ball - Welded | 632.472 | 3.48 | 0 | 0
|  | 4 | Valve - Butterfly - Flanged | 914.66 | 1.91 | 0 | 0
|  | 4 | Valve - Ball - Welded | 731.728 | 4.58 | 0 | 0
|  | 6 | Valve - Butterfly - Flanged | 1568.4 | 2.22 | 0 | 0
|  | 8 | Valve - Butterfly - Flanged | 2255.2 | 2.45 | 0 | 0
|  | 10 | Valve - Butterfly - Flanged | 3834.8 | 3.99 | 0 | 0
|  | 1/2 | Specialties - Pipe ID | 0.12 | 0.01 | 0 | 0
|  | 3/4 | Specialties - Pipe ID | 0.12 | 0.01 | 0 | 0
|  | 1 | Specialties - Pipe ID | 0.12 | 0.01 | 0 | 0
|  | 2 | Specialties - Pipe ID | 0.12 | 0.01 | 0 | 0
|  | 3 | Specialties - Pipe ID | 0.15 | 0.01 | 0 | 0
|  | 4 | Specialties - Pipe ID | 0.15 | 0.01 | 0 | 0
|  | 6 | Specialties - Pipe ID | 0.17 | 0.01 | 0 | 0
|  | 8 | Specialties - Pipe ID | 0.28 | 0.01 | 0 | 0
|  | 10 | Specialties - Pipe ID | 0.28 | 0.01 | 0 | 0
|  | VARIOUS | Specialties - Clevis Seismic Bracing | 12.5 | 0.15 | 0 | 0
|  | 3/8 | Structural Attachment - Anchors | 2.56 | 0.25 | 0 | 0
|  | 1/2 | Structural Attachment - Anchors | 4.31 | 0.25 | 0 | 0
|  | 1/2 | Supports - Aluminum - Saddles & Shields | 4.16 | 0.1 | 0 | 0
|  | 1 | Supports - Aluminum - Saddles & Shields | 4.41 | 0.1 | 0 | 0
|  | 3/8 | Supports - Bolts, Nuts, Washers | 0.42 | 0.02 | 0 | 0
|  | 1/2 | Supports - Bolts, Nuts, Washers | 0.6 | 0.02 | 0 | 0
|  | 3/8 | Supports - Hanger Rod | 1.54 | 0.05 | 0 | 0
|  | 1/2 | Supports - Hanger Rod | 3.2 | 0.05 | 0 | 0
|  | 2 | Supports - Carbon Steel Hangers - Galvanized | 6.84 | 0.6 | 0 | 0
|  | 3 | Supports - Carbon Steel Hangers - Galvanized | 13.8 | 0.6 | 0 | 0
|  | 4 | Supports - Carbon Steel Hangers - Galvanized | 25.63 | 0.7 | 0 | 0
|  | 10 | Supports - Carbon Steel Hangers - Galvanized | 136.92 | 1 | 0 | 0
|  | 12 | Supports - Carbon Steel Hangers - Galvanized | 173.49 | 1 | 0 | 0
|  | 16 | Supports - Carbon Steel Hangers - Galvanized | 256.33 | 1.11 | 0 | 0
|  | 1/2 | Supports - Carbon Steel Hangers - Copper | 3.09 | 0.4 | 0 | 0
|  | 3/4 | Supports - Carbon Steel Hangers - Copper | 3.09 | 0.4 | 0 | 0
|  | 1 | Supports - Carbon Steel Hangers - Copper | 4.09 | 0.5 | 0 | 0
|  | 1-1/2 | Supports - Carbon Steel Hangers - Copper | 5.65 | 0.56 | 0 | 0
|  | 2 | Supports - Carbon Steel Hangers - Copper | 6.25 | 0.58 | 0 | 0
|  | 2-1/2 | Supports - Carbon Steel Hangers - Copper | 9 | 0.6 | 0 | 0
|  | 3 | Supports - Carbon Steel Hangers - Copper | 11.08 | 0.6 | 0 | 0
|  | 2-1/2 | Supports - Carbon Steel Saddles & Shields | 24.66 | 0.07 | 0 | 0
|  | 3 | Supports - Carbon Steel Saddles & Shields | 26.55 | 0.07 | 0 | 0
|  | 4 | Supports - Carbon Steel Saddles & Shields | 45.21 | 0.07 | 0 | 0
|  | 10 | Supports - Carbon Steel Saddles & Shields | 116.26 | 0.07 | 0 | 0
|  | 12 | Supports - Carbon Steel Saddles & Shields | 159.44 | 0.07 | 0 | 0
|  | 16 | Supports - Carbon Steel Saddles & Shields | 291.2 | 0.09 | 0 | 0
|  | 3 | Cut & Prep Pipe - Carbon Steel (only use on existing pipe) | 10 | 0.5 | 0 | 0
|  | 4 | Cut & Prep Pipe - Carbon Steel (only use on existing pipe) | 10 | 0.5 | 0 | 0
|  | 6 | Cut & Prep Pipe - Carbon Steel (only use on existing pipe) | 15 | 0.5 | 0 | 0
|  | 8 | Cut & Prep Pipe - Carbon Steel (only use on existing pipe) | 20 | 0.5 | 0 | 0
|  | 10 | Cut & Prep Pipe - Carbon Steel (only use on existing pipe) | 20 | 0.5 | 0 | 0
|  | 3 | Cut & Prep Pipe - Copper (only use on existing pipe) | 10 | 0.5 | 0 | 0
|  | 4 | Cut & Prep Pipe - Copper (only use on existing pipe) | 10 | 0.5 | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
PIPING TOTALS: | [5 empty] | 0 | 0

## Rentals
EQUIPMENT RENTAL
Project: | [PROJECT NAME]
Date: | [DATE]
Description: | [CHANGE ESTIMATE REFERENCE]
Qty | Description | Hours | Weeks | Months | Hourly Rate | Weekly Rate | Monthly Rate | TOTAL
VEHICLES
| Pick-up Truck 2 X 4 |  |  |  | 9 | 288 | 864 | 0
| Crew Tool truck 3/4 ton |  |  |  | 22 | 704 | 2640 | 0
| Crew Tool Truck F550 |  |  |  | 46 | 1472 | 5520 | 0
| Flat bed truck 2 ton |  |  |  | 46 | 1472 | 5520 | 0
| UTV/Mule, Golf Cart |  |  |  | 9 | 288 | 1080 | 0
LIGHT EQUIPMENT
| Roto Hammers, Kit W/ Chuck |  |  |  | 6 | 192 | 720 | 0
| Band saw (porta-band) |  |  |  | 5 | 160 | 600 | 0
| Circular Saw, 5 HP |  |  |  | 14 | 448 | 1680 | 0
| Core Drill Machine |  |  |  | 15 | 480 | 1800 | 0
| GPR concrete rebar |  |  |  | 21 | 672 | 2520 | 0
| Laser Levels |  |  |  | 8 | 256 | 960 | 0
| Light tower |  |  |  | 24 | 768 | 2880 | 0
| Tube Squaring Machine |  |  |  | 8 | 256 | 960 | 0
| Tubing Bender |  |  |  | 15 | 480 | 1800 | 0
| Tubing Flange Former, Sanitech |  |  |  | 21 | 672 | 2520 | 0
| Fusion Machine GSR FU-1200 |  |  |  | 7 | 224 | 840 | 0
| PEX/Propress Tool |  |  |  | 4 | 128 | 480 | 0
| Weld machine, 250A, lead/stinger |  |  |  | 25 | 800 | 3000 | 0
| Smog Hog |  |  |  | 20 | 640 | 2400 | 0
| Orbital Welding Machine |  |  |  | 81 | 2592 | 9720 | 0
| Orbital Weld Head |  |  |  | 24 | 768 | 2880 | 0
| Acetylene Rigs Complete |  |  |  | 4 | 128 | 480 | 0
| Threading Machine/Power Vice |  |  |  | 13 | 416 | 1560 | 0
| Pump, Test, 150 psi |  |  |  | 28 | 896 | 3360 | 0
| Pump Trash, 3"-4" |  |  |  | 10 | 320 | 1200 | 0
| Pump, 1" electric |  |  |  | 8 | 256 | 960 | 0
| Pump Flushing Skid |  |  |  | 22 | 704 | 2640 | 0
| Compressor, 175 cfm |  |  |  | 32 | 1024 | 3840 | 0
| wet dry vacuum |  |  |  | 8 | 256 | 960 | 0
| Roust-A-Bout Material Lift |  |  |  | 15 | 480 | 1800 | 0
| Scissor Lift |  |  |  | 15 | 480 | 1800 | 0
| Boom Lift (<50' articulating) |  |  |  | 38 | 1216 | 3648 | 0
| Generator 3500 Watt |  |  |  | 10 | 320 | 1200 | 0
HEAVY EQUIPMENT
| Forklift 8K all terrain |  |  |  | 72 | 2304 | 8640 | 0
| Forklift 5K all terrain |  |  |  | 32 | 1024 | 3840 | 0
| Forklift 2K warehouse |  |  |  | 20 | 640 | 2400 | 0
MISC
| Office trailer |  |  |  | 15 | 480 | 1800 | 0
| Storage container |  |  |  | 8 | 256 | 960 | 0
| Movin Cool |  |  |  | 21 | 672 | 2520 | 0
| [PLUG] | [6 empty] | 0
| [PLUG] | [6 empty] | 0
| [PLUG] | [6 empty] | 0
| [PLUG] | [6 empty] | 0
TOTAL | [7 empty] | 0

## Labor Rates
| STRAIGHT TIME |  | OVERTIME |  | DOUBLETIME |  | SHIFT |  | SHIFT OVERTIME |  | SHIFT DOUBLETIME
| CREW MEMBERS | LABOR RATE | CREW MEMBERS | LABOR RATE | CREW MEMBERS | LABOR RATE | CREW MEMBERS | LABOR RATE | CREW MEMBERS | LABOR RATE | CREW MEMBERS | LABOR RATE
APPRENTICE | 0 | 125 | 0 | 170 | 0 | 210 | 0 | 140 | 0 | 190 | 0 | 230
JOURNEYMAN | 0 | 170 | 0 | 230 | 0 | 290 | 0 | 190 | 0 | 260 | 0 | 320
FOREMAN | 0 | 200 | 0 | 270 | 0 | 330 | 0 | 220 | 0 | 300 | 0 | 370
GENERAL FOREMAN | 0 | 210 | 0 | 290 | 0 | 360 | 0 | 235 | 0 | 320 | 0 | 400
CREW RATE
PROJECT EXECUTIVE |  | 250
PROJECT MANAGER |  | 210
PROJECT ENGINEER |  | 100
SUPERINTENDENT |  | 175
SAFETY PROFESSIONAL |  | 110
QA/QC MANAGER |  | 125
1. Labor rates above do not include 10% Overhead & 5% Profit. 2. First 8 hours worked is straight time. Overtime is defined as first 2 hours in excess of an 8 hour shift. Doubletime is defined as all work hours after 10 hours. 3. Saturdays are Overtime pay for first 10 hours, doubletime pay there-after. 4. Sundays are Doubletime pay. 5. Straight time normal work hours are 6 AM - 2:30 PM and include one 40 minute (unpaid) lunch break. Shift is defined as an 8 hour shift starting at anytime that is not normal work hours. Shift Overtime and Shift Doubletime apply the same as regular overtime and doubletime rates. 6. An additional 30 minute break (paid at applicable overtime / doubletime / shift rate) shall be allowed after 2 hours of overtime is worked, and every 4 hours thereafter.