## Owner Contract Evaluation
Contractor Responsibilities
If the project is NOT Design-Build, is Contractor responsible for the impacts of errors and omissions in the CDs that are not apparent and discoverable by Contractor?
If the Project is not Design Build, is Contractor obligated to provide only what is indicated on the Construction Documents, not what is intended from the Construction Documents? ("reasonably inferable" is o.k.)
If the Project is not Design Build, does Contractor have to "represent" or "warrant" that the Construction Documents are complete and constructible?
Is Contractor required to agree not to disclose confidential Owner information? (this could be via contract language, or a separate Nondisclosure Agreement)
Does Owner have unreasonable restrictions on subcontracting or unreasonable pass-through requirements for subcontracts?
Does the Contract expressly state that Contractor has a "fiduciary" relationship with the Owner?
Owner Responsibilities
Does the Owner disclaim responsibility for, and prevent Contractor from relying on the accuracy of, the Soils Report, other Reports, or information they furnish?
If the project is not Design-Build, does Owner disclaim responsibility for accuracy of the Drawings & Specifications?
If Owner is a Special Purpose Entity (SPE), do we have a parent guaranty from an upstream owner with sufficient assets and cash flow?
Does the contract require us to seek recovery for impacts by Owner's Separate Contractors directly from those contractors (rather than through the Owner)?
Does the contract give Owner ownership rights to proprietary Contractor or subcontractor intellectual property or technology?
Scope
If the project is not design build, are conflicts in quantity or quality resolved by requiring the higher quantity or better quality without an equitable adjustment in Contract Sum or Time?
Is an Order of precedence of the Contract Documents stipulated?
Time
Does definition of Substantial Completion require a final certificate of occupancy or other unrealistic requirements?
Are all of the following delays considered Excusable Delays (eligible for time extensions): (i) labor disputes not resolvable by dual gate; (ii) unusual or severe weather; (iii) force majeure events; (iv) acts of governmental authorities for which Contractor or subs are not responsible?
Are all delay costs for Owner-responsible delays compensable via Change Order? (There should be no indication that time is the sole remedy for delays.)
Is Contractor obligated to meet all activity dates in our schedule, instead of just the Contract Substantial Completion and/or Milestone dates?
Budget/GMP/Contract Sum
Is the Contract Sum qualified by a Contractor Basis of Contract/GMP (Basis of Estimate)?
Are individual GMP line items, other than General Conditions, separately guaranteed?
Is there a fair definition for allowable uses of contingency for Contractor?
Can Contractor use project contingency without Owner's prior consent?
Cost Reimbursement & Billings
If Owner audits Labor Rates, do they have the right to adjust them and pay less than agreed Contractor rates?
Are Lump Sum costs auditable?
Does the contract require use of Owner custom Lien Waiver forms with Pay Apps, instead of Contractor's state-compliant forms?
Is Contractor's obligation to remove liens relieved if Owner is in default of payments obligations to Contractor?
Are any of the following required prior to Owner's Final Payment: (1) expiration of lien rights at all tiers; (2) unconditional lien & claim waivers/releases; or (3) payment of all costs, including to subcontractors?
Does Contractor have to waive all claims as a prerequisite to receipt of Progress Payments?
Is payment due within 30 days or sooner of Owner's receipt of Contractor's Pay Application?
Is the Owner allowed to hold retainage until Final Completion (rather than Substantial Completion)?
Does Interest accrue on late Owner payments?
Does Contractor have the right to stop work if Owner fails to pay per the Contract?
For cost-reimbursable contracts (including GMP): is the definition of reimbursable costs (Cost of the Work) reasonable and complete?
If Owner terminates for convenience, are we entitled to be paid our incurred costs due to the termination in addition to payment of costs & fee for Work completed up thru termination?
Indemnification/Insurance
Does the Owner indemnify Contractor for existing Hazardous Materials?
Is Contractor responsible for risk of loss to the Work other than due to the negligence of Contractor or our subs?
If the Owner is providing Builder's Risk coverage, has their policy been reviewed by our broker?
If Contractor is providing Builder's Risk, do we have verification from our broker that the coverage is in effect?
If required by Contractor’s policy on subcontractor default insurance (i.e., Subguard), will the project be enrolled in the program?
Changes
Do Change Orders take precedence over the Agreement?
Does Contract allow a change in Contract Price/GMP and Contract Time for undisclosed or concealed subsurface or physical conditions?
Is a reasonable Change Order Fee percentage stipulated?
Is a Construction Change Directive process (or similar) allowed for performing change work prior to Change Order?
Is our Fee reduced for deductive change orders?
Does the Owner have the right to issue Change Orders that can change Contractor's Contract Sum or Contract Time unilaterally (with only their signature)?
Damages/Disputes
Is there a mutual waiver of Consequential Damages clause?
Are Liquidated Damages the sole remedy stipulated for late performance by Contractor?
Are Attorneys fees payable to the Prevailing Party in a dispute under the Contract?
Design-Build - if applicable
Is this a Design-Build Project/Contract?
Is the Owner's Program attached as Contract Document?
Are the Owner's Design requirements clearly defined?
Other
Is Contractor's obligation to correct defective work limited to 1 year after substantial completion?
Does Contractor's warranty exclude damage by others, failure to properly maintain, and wear and tear under normal or excessive usage?
Does Owner have the right to take assignment of our subcontracts in a termination for convenience?