## INSTRUCTIONS
General Conditions Estimate Module
| Description | Notes
1 | In this portion of the problem, you will be required to provide a general conditions estimate for your project. The General Conditions are a useful tool when determining whether or not the potential project is worth the risk.
2 | Labor Projection Worksheet: Use this sheet to determine the Project Management team, as well as durations of the personnel. The template only shows a three week schedule. Remember to tie this to the schedule you will be creating. Determine how you will staff the team. There is no right or wrong answer to how you staff your project. You must be able to defend how you will staff the project and the justify the costs to the owner. You do NOT need to utilize each line, or each type of staff member | **add and subtract as many personnel as needed for job completion. Project as far as the schedule determines**
3 | The sheet labeled GCs is what you will use to calculate your general conditions. Be sure to note the duration of your project, to accurately forecast your cost. Note the loaded cells pull values from the Hourly Rates page. Make adjustments as necessary. Be sure to use the comments section for items that may need justification. For example, some items may be excluded due to the owner providing that item. Add and subtract as many line items you may need. | ***Some formulas may be incorrect or incomplete. It is Best Practice to always double check formulas when using an Excel Template***
4 | Hourly Rates sheet is used to populate your GCs.
5 | General Expenses Sheet is used for examples of standard items that are generally incorporated in a General Conditions estimate. Many times all will be used, and often less well be used. Use your judgement based off the scope of work. | **You may incorporate items that are not listed on the General expense sheet.
6 | Please use the Labor Projection Worksheet to determine durations of personnel on your project. Be sure they are shown on the "GC's Full Project" Template
7 | Once the General Conditions are populated. Please format and provide the GCs sheet in PDF and Excel format.

## Labor Projection Worksheet
Need to Add G&A to Date/ Site Req F/C
Preconstruction Services?
| Labor Cost Projection Worksheet |  | 2016-04-01 | 2016-04-08 | 2016-04-15 | Total Hours | Rate | Subtotals | mPower Budget | Delta
Labor Cost Projection Sheet COLOR KEY
| 15-0101 | Project Executive - TBD | 4 | 4 | 4 | 12 | 135 | 1620 |  | -1620
| 15-0102 | Project Manager - TBD | 40 | 40 | 40 | 120 | 100 | 12000 |  | -12000
| 15-0103 | Superintendent - TBD | 40 | 40 | 40 | 120 | 100 | 12000 |  | -12000
| 15-010X | Asst Superintendent - TBD | 40 | 40 | 40 | 120 | 65 | 7800
| 15-0105 | Project Engineer - TBD | 40 | 40 | 40 | 120 | 65 | 7800 |  | -7800
| 15-0105 | Project Engineer - TBD | 40 | 40 | 40 | 120 | 65 | 7800 |  | -7800
| 15-0105 | Project Engineer - TBD | 40 | 40 | 40 | 120 | 65 | 7800 |  | -7800
| 15-0106 | Project Accountant - TBD | 8 | 8 | 8 | 24 | 50 | 1200 |  | -1200
| 15-0107 | FOC - TBD | 40 | 40 | 40 | 120 | 42 | 5040 |  | -5040
| 15-0124 | MEP Coordinator - TBD | 16 | 16 | 16 | 48 | 95 | 4560 |  | -4560
| 16-0320 | Safety Coordinator - TBD |  |  |  | 0 | 65 | 0
| Totals | Projected Weekly Hours | 308 | 308 | 308 | 924 |  | 67620 | 0 | -59820
Inser
Means that the cell has a formula in it. Do not type in these cells
Note on H3: Sam Reid: Make sure you check your actual labor rates in your owner contract AND on your labor transaction report
Note on C55: Sam Reid: Safety Coordinator time entered in this row should reflect time that will be charged to the direct work codes (Not division 16)
Note on C62: Sam Reid: Determine your actual weekly hours by running a 1 week query in the Labor Transaction Report - This field must be entered manually every week
Note on C63: Sam Reid: If you see a negative number in this row it means you are UNDER budget
Note on C68: Sam Reid: If you see a negative number in this row it means you are UNDER budget
Note on C70: Sam Reid: Enter your total estimated hour from your labor cost report (Including changes)
Note on C71: Sam Reid: Current Projected Total Hours = Actual Hours to Date + Remaining Projected Hours
Note on C72: Sam Reid: If you see a negative number in this row it means you are UNDER budget

## GCs - Full Project
Name
Location
General Conditions Estimate
PROJECT: |  | Name | [7 empty] | DPR JOB NO: | TBD
LOCATION: |  | Location |  | Mo | Weeks |  |  |  |  | ESTIMATE NO: | GMP Estimate
ARCHITECT: |  | Name | Duration | 8 | 34.64 |  |  |  |  | DATE:
CLIENT: |  | Name | [7 empty] | ESTIMATOR:
SYS
NO. | DESCRIPTION |  | QUANTITY | UNIT | UNIT COST | SUBTOTAL | ## | hours | tot hrs | TOTAL | COMMENTS
15 | JOBSITE MANAGEMENT
Management
|  | Project Manager | 34.64 | wk | 600 | 20784 | 20784 | 4 | 4
|  | Superintendent | 34.64 | wk | 4600 | 159344 | 159344 | 40 | 1385.6
|  |  | 34.64 | wk | 0 | 0 | 0 |  | 0
|  |  | 34.64 | wk | 0 | 0 | 0 |  | 0
|  |  | 34.64 | wk | 0 | 0 | 0 |  | 0
|  |  | 34.64 | wk | 0 | 0 | 0 |  | 0
|  |  | 34.64 | wk | 0 | 0 | 0 |  | 0
|  |  | 34.64 | wk | 0 | 0 | 0 |  | 0
| SUBTOTAL: Management |  |  |  |  | 180128 |  |  | 1385.6
Jobsite Office
|  | Office Trailer | 8 | mo | 600 | 4800 | 4800
|  | Jobsite Set-up and Demobilization | 1 | ls | 6250 | 6250 | 3000
|  | Copy/Scanner/Fax Machine | 8 | mo | 225 | 1800 | 1800
|  | Internet | 8 | mo | 350 | 2800 | 2800
| SUBTOTAL: Jobsite Office |  |  |  |  | 15650
Vehicles/Travel
|  | Truck Rental, Large | 8 | mo | 850 | 6800 | 6800
|  | Fuel-Trucks/Cars | 8 | mo | 750 | 6000 | 6000 | 2
| SUBTOTAL: Vehicles/Travel |  |  |  |  | 12800
Jobsite Office Eq/Servcs
|  | Subsistence / Petty Cash | 8 | mo | 0 | 0 | 0
|  | Office Supplies | 8 | mo | 200 | 1600 | 1600 | 2
|  | Drinking Water | 8 | mo | 50 | 400 | 400
|  | Progress Photos - Digital | 0 | ls | 500 | 0 | 0
| SUBTOTAL: Jobsite Office Eq/Servcs |  |  |  |  | 2000
| SUBTOTAL: 15 - JOBSITE MANAGEMENT | [8 empty] | 207328
16 | PROJECT REQUIREMENTS
Safety/Cleanup
|  | Safety Manager | 34.64 | wks | 0 | 0 | 0 | 0 | 0 |  | Cost of the Work
|  | Jobsite Safety |  | wks | 0 | 0 | 0 | 0 |  |  | Cost of the Work
|  | Fire Protection / First Aid / Equip. |  | ls |  | 0 | 0 |  |  |  | Cost of the Work
|  | Interim Cleanup |  | wks | 0 | 0 | 0 |  |  |  | Cost of the Work
|  | Debris Boxes |  | exch |  | 0 | 0 |  |  |  | Cost of the Work
|  | Trailer Security | 0 | mo | 80 | 0 | 0
| SUBTOTAL: Safety/Cleanup |  |  |  |  | 0
Temporary Services
|  | Temp. Electrical Set-up (New) |  | ls | 0 | 0 | 0 |  |  |  | Cost of the Work
|  | Temporary Signage |  | ls |  | 0 | 0 |  |  |  | Cost of the Work
|  | Temporary Lighting Maintenance |  | wk | 0 | 0 | 0 |  |  |  | By Electrical
|  | Construction Power Costs |  | mo | 0 | 0 | 0
|  | Temp. Water - Set-up (New) |  | ls | 0 | 0 | 0
|  | Construction Water Costs |  | mo | 0 | 0 | 0
|  | Parking |  | mo | 0 | 0 | 0
|  | Temporary Toilets | 0 | wks |  | 0 | 0
| SUBTOTAL: Temporary Services |  |  |  |  | 0
Misc Project Requirements
|  |  | 0 | lf | 12 | 0 | 0
|  |  |  | mo | 1500 | 0 | 0
|  | Temporary Partitions | 0 | lf | 25 | 0 | 0
|  |  | 0 | lf | 50 | 0 | 0
|  | Hoisting Equipment | 0 | wk |  | 0 | 0
|  | Elevator Protection | 0 | ls | 1000 | 0 | 0
| SUBTOTAL: Misc Project Requirements |  |  |  |  | 0
Blueprinting/Reproduction
|  | FTP Site | 0 | allw | 0 | 0 | 0 |  |  |  | EXCLUDED; by Others
|  | Printing Allowance - Bid Sets/Const. Sets | 0 | allw | 0 | 0 | 0 |  |  |  | Reimbursable
|  | Printing Allowance - Shop Drawings/As-Builts | 0 | allw | 1500 | 0 | 0 |  |  |  | Electronic
| SUBTOTAL: Blueprinting/Reproduction |  |  |  |  | 0
| SUBTOTAL: 16 - PROJECT REQUIREMENTS | [8 empty] | 0
Subtotal | [6 empty] | 207328 |  |  | 207328
TOTAL | [9 empty] | 207328 |  | 5985.2194

## Hourly Rates
Contractor's Fixed Rates
Classification | Rates | Overtime Rates | Double-time Rates
General Conditions
Project Manager | 130 | NA | NA
Project Superintendent | 110 | NA | NA
Assistant Superintendent | 85 | NA | NA
Project Engineer | 70 | NA | NA
Field Office Coordinator | 48 | NA | NA
Project Executive | 160 | NA | NA
Project Accountant | 50 | NA | NA
Start-Up / Commissioning Support / Coord. | 95 | NA | NA
Safety Manager | 65 | NA | NA
Jobsite Safety | 65 | NA | NA
Project Intern | 28 | NA | NA
PreConstruction
Project Executive | 160 | NA | NA
Project Manager | 130 | NA | NA
Project Superintendent | 110 | NA | NA
Project Estimator | 95 | NA | NA
MEP Estimator | 105 | NA | NA
Estimating Assistant | 35 | NA | NA
Self-Performed Work
Laborer | 51 | 76.5 | 102
Laborer Foreman | 57 | 85.5 | 114
Carpenter | 68 | 102 | 136
Carpenter Foreman | 71 | 106.5 | 142
Drywaller/Taper | 56 | 84 | 112
Drywaller/Taper Foreman | 60 | 90 | 120
These fixed labor rates shall be used to calculate Cost of Work for the purpose of billings, change order pricing, and overall Contract compensation and being fixed in nature, the rates themselves, for each labor classification, are not subject to audit.
***These fixed labor rates are subject to differ from one Contractor/State to the next. For the pruposes of this module, use these provided rates to populate your GC's. ***

## Jobsite Operations
GATTACA
Unit Rate Sheet General Expense
|  | UNIT OF | UNIT
ITEM |  | MEASURE | RATE | COMMENTS
Pickup rental |  | MO | 800
Pickup fuel & maintenance |  | MO | 500
Small forklift |  | MO | 960
Small tools and misc equip rental |  | MO | 900
12'x60' Office Trailer Rental |  | MO | 1250 | Provide 160sf of space per staff
Temp office build out |  |  |  | A Carpenter can build out 14sf of office per hour.
Temp office build out material |  | SF | 4
Mobilization/Trucking |  | EA | 6250
Temp toilets/wash stations |  | MO | 135 | Assume one per ten workers per month
Temp water-drinking |  | MO | 50
Parking |  | DAY | 8 | Allow for parking of each jobsite staff member for their duration
Project signs |  | EA | 1300
Courier/express service |  | MO | 500
Telephone system install |  | LS | 2000
Office supplies |  | MO | 800
Office furniture/equipment |  | LS | 7500
Copier |  | MO | 650
Photos |  | MO | 125
Medical equip/supplies |  | LS | 125
Warning/safety signs |  | LS | 2000
Stairs and ladders |  | VLF | 20
Stairs and ladders install |  |  |  | Allow for a Laborer 1 hr/vlf for set-up and takedown
Housekeeping |  |  |  | Allow for 2 Laborers for 3 hrs per day for project duration
Trash disposal |  | WK | 2080
As-built drawings |  | LS | 5500
Drawing reproduction |  | LS | 10000
Construction drawings |  | EA | 350
Material for protecting finishes |  | SF | 0.1
Note: | If your plan requires a unit rate that is not found above establish a rate based upon appropriate information (such as Means, etc.)
You may not need all of these items. Base these inclusions off of the project, and how it will be set up.