Build a Schedule

Instructions:

- Start date is Monday, October 8, 2018

- Owner wants to be 100% moved in & operational by end of Summer, 2021

- Sequence and include the below milestones in your schedule – Add any other milestones you see necessary

- Schedules need to be at least 200 different line items (I.E. L2 overhead MEP & L3 overhead MEP are not 2 different line items, so they count as 1).

- We are grading based on quality not quantity of line items in your schedule

- This schedule should be built using the information found on the plans provided. Understand the type of structure this is and what elements go into the building to develop a project specific schedule.

- Please turn in your schedule by printing to PDF!

  - Use “Smartsheet” to build your schedule, see the attached instructions for how to access and use the program.

  - The following columns are to be shown in your PDF:

    - Activity Names

    - Durations

    - Start & Finish Dates

    - Activity Bars

Milestones:

- Steam System Tie In Complete

- Remove Manhoist

- Skin System Complete

- Start TI’s

- Basement Walls Complete

- TI Permit

- Set Roof Mechanical Equipment

- Structural Steel Material Release

- Commissioning Starts

- Complete Shoring

- Elevator Fabrication Released

- Complete SOMD Pours

- Substantial Completion

- Install Manhoist

- Elevator Inspections

- TAB Report

- Start Curtainwall System

- Erect Structural Steel

- Release AHUs

- Pneumatic Tube Deferred Submittal Approved

- Tunnel to Adjacent Building Complete

- Core & Shell Permit

- Steel Topping Out

- Utility Tie In Complete