## Contract Evaluation
Owner Contract Evaluation | [7 empty] | Grade |  | INDEX | ROLE | DESIGN STATUS | GMP N/A | Comp Basis | Contract Form
[8 empty] | 0% | F |  | GC | Unknown |  | Stipulated (Lump) Sum | DPR's AIA Form
| Contract A or B: | [6 empty] | 70% | B |  | Design/Builder | Full CDs - GMP |  | Other | Other
| Owner: | [6 empty] | 80% | A |  |  | 0%
| ASC School Name: | [10 empty] | 30%
Prepared Date:
[8 empty] | #REF! |  |  |  | 60%
No. | Risk Description | Yes | No | Other | Contract Reference | Comments | Unit Value
A | DPR Responsibilities | x | x
1 | If the project is NOT Design-Build, is DPR responsible for the impacts of errors and omissions in the CDs that are not apparent and discoverable by DPR? | [5 empty] | 0
2 | If the Project is not Design Build, is DPR's role in reviewing Construction Documents limited to that of Contractor & not as design professional? | [5 empty] | 0
3 | Does Owner have unreasonable restrictions on subcontracting or unreasonable pass-through requirements for subcontracts? | [5 empty] | 0
B | Owner Responsibilities
1 | Does the Owner disclaim responsibility for, and prevent DPR from relying on the accuracy of, the Soils Report, other Reports, or information they furnish? | [5 empty] | 0
2 | If the project is not Design-Build, does Owner disclaim responsibility for accuracy of the Drawings & Specifications? | [5 empty] | 0
3 | Is there a clause requiring the Owner to provide proof of project financing upon our request? | [5 empty] | 0
4 | Does the contract give Owner ownership rights to proprietary DPR or subcontractor intellectual property or technology? | [5 empty] | 0
C | Scope
1 | If the project is not design build, are conflicts in quantity or quality resolved by requiring the higher quantity or better quality without an equitable adjustment in Contract Sum or Time? | [5 empty] | 0
2 | Is an Order of precedence of the Contract Documents stipulated? | [5 empty] | 0
D | Time
1 | Does definition of Substantial Completion require a final certificate of occupancy or other unrealistic requirements? | [5 empty] | 0
2 | Is there a "grace period" before DPR is entitled to additional time/costs for excusable delay? (Example: Contractor is entitled to no time/costs for delays unless the delay exceeds ten workdays.) | [5 empty] | 0
3 | Are all of the following delays considered Excusable Delays (eligible for time extensions): (i) labor disputes not resolvable by dual gate; (ii) unusual or severe weather; (iii) force majeure events; (iv) acts of governmental authorities for which DPR or subs are not responsible? | [5 empty] | 0
4 | Are all of the following delays considered Compensable Delays (eligible for time extensions and additional costs): (i) acts of the Owner or its separate contractors/AE's; (ii) Scope Changes; or (iii) hidden, concealed or differing conditions? (There should be no indication that time is the sole remedy for these types of delays.) | [5 empty] | 0
5 | Is DPR obligated to meet all activity dates in our schedule, instead of just the Contract Substantial Completion and/or Milestone dates? | [5 empty] | 0
E | Budget/GMP/Contract Sum
1 | Does the contract allow labor costs to be included in Allowance amounts? (Note: Our Allowance estimates need to be consistent with the contract's requirements for Allowance cost composition.) | [5 empty] | 0
2 | Is there a fair definition for allowable uses of contingency for DPR? | [5 empty] | 0
3 | Can DPR use project contingency without Owner's prior consent? | [5 empty] | 0
F | Cost Reimbursement & Billings
1 | Are Lump Sum costs auditable? | [5 empty] | 0
2 | Is DPR's obligation to remove liens relieved if Owner is in default of payments obligations to DPR? | [5 empty] | 0
3 | Are any of the following required prior to Owner's Final Payment: (1) expiration of lien rights at all tiers; (2) unconditional lien & claim waivers/releases; or (3) payment of all costs, including to subcontractors? | [5 empty] | 0
4 | Are Unconditional Waivers required only on previously paid amounts? | [5 empty] | 0
5 | Is payment due within 30 days or sooner of Owner's receipt of DPR's Pay Application? | [5 empty] | 0
6 | Is the Owner allowed to hold retainage until Final Completion (rather than Substantial Completion)? | [5 empty] | 0
7 | Does Interest accrue on late Owner payments? | [5 empty] | 0
8 | Does DPR have the right to stop work if Owner fails to pay per the Contract? | [5 empty] | 0
9 | For cost-reimbursable contracts (including GMP): is the definition of reimbursable costs (Cost of the Work) reasonable and complete? | [5 empty] | 0
10 | Does Owner have unreasonable rights to withhold payment from DPR? | [5 empty] | 0
G | Indemnification/Insurance
1 | Is DPR's Indemnification (General Indemnity) of Owner limited to third-party claims for bodily injury and property damage (other than to Work itself)? | [5 empty] | 0
2 | Is DPR's Indemnification (General Indemnity) of Owner limited "to the extent of DPR's negligence"? | [5 empty] | 0
3 | Does the Owner indemnify DPR for existing Hazardous Materials? | [5 empty] | 0
4 | Is DPR responsible for risk of loss to the Work other than due to the negligence of DPR or our subs? | [5 empty] | 0
5 | Is DPR's deductible liability for builder's risk insurance greater than $50K? If yes, what is the amount? | [5 empty] | 0
6 | If Owner is providing the builder's risk insurance, are DPR AND the Subcontractors required by contract to be named as Additional Named Insureds? | [5 empty] | 0
H | Changes
1 | Do Change Orders take precedence over the Agreement? | [5 empty] | 0
2 | Does Contract allow a change in Contract Price/GMP and Contract Time for undisclosed or concealed subsurface or physical conditions? | [5 empty] | 0
3 | Is a reasonable Change Order Fee percentage stipulated? | [5 empty] | 0
4 | Is our Fee reduced for deductive change orders? | [5 empty] | 0
I | Damages/Disputes
1 | Are Liquidated Damages the sole remedy stipulated for late performance by DPR? | [5 empty] | 0
2 | Does DPR have a right to cure problems with sufficient time before Owner exercises remedies for default? | [5 empty] | 0
3 | Are Attorneys fees payable to the Prevailing Party in a dispute under the Contract? | [5 empty] | 0
K | Other
1 | Does DPR's warranty exclude damage by others, failure to properly maintain, and wear and tear under normal or excessive usage? | [5 empty] | 0
2 | Is the stipulated governing law the law where the project is located? (for example, if the project is in Texas, is the governing law Texas law?) | [5 empty] | 0
3 | Is Self Perform Work allowed without competition? | [5 empty] | 0