## Labor Projection Worksheet
Need to Add G&A to Date/ Site Req F/C
Preconstruction Services?
| Labor Cost Projection Worksheet |  | 2016-04-01 | 2016-04-08 | 2016-04-15 | Total Hours | Rate | Subtotals | mPower Budget | Delta
Labor Cost Projection Sheet COLOR KEY
| 15-0101 | Project Executive - TBD | 4 | 4 | 4 | 12 | 135 | 1620 |  | -1620
| 15-0102 | Project Manager - TBD | 40 | 40 | 40 | 120 | 100 | 12000 |  | -12000
| 15-0103 | Superintendent - TBD | 40 | 40 | 40 | 120 | 100 | 12000 |  | -12000
| 15-010X | Asst Superintendent - TBD | 40 | 40 | 40 | 120 | 65 | 7800
| 15-0105 | Project Engineer - TBD | 40 | 40 | 40 | 120 | 65 | 7800 |  | -7800
| 15-0105 | Project Engineer - TBD | 40 | 40 | 40 | 120 | 65 | 7800 |  | -7800
| 15-0105 | Project Engineer - TBD | 40 | 40 | 40 | 120 | 65 | 7800 |  | -7800
| 15-0106 | Project Accountant - TBD | 8 | 8 | 8 | 24 | 50 | 1200 |  | -1200
| 15-0107 | FOC - TBD | 40 | 40 | 40 | 120 | 42 | 5040 |  | -5040
| 15-0124 | MEP Coordinator - TBD | 16 | 16 | 16 | 48 | 95 | 4560 |  | -4560
| 16-0320 | Safety Coordinator - TBD |  |  |  | 0 | 65 | 0
| Totals | Projected Weekly Hours | 308 | 308 | 308 | 924 |  | 67620 | 0 | -59820
Inser
Means that the cell has a formula in it. Do not type in these cells
Note on H3: Sam Reid: Make sure you check your actual labor rates in your owner contract AND on your labor transaction report
Note on C55: Sam Reid: Safety Coordinator time entered in this row should reflect time that will be charged to the direct work codes (Not division 16)
Note on C62: Sam Reid: Determine your actual weekly hours by running a 1 week query in the Labor Transaction Report - This field must be entered manually every week
Note on C63: Sam Reid: If you see a negative number in this row it means you are UNDER budget
Note on C68: Sam Reid: If you see a negative number in this row it means you are UNDER budget
Note on C70: Sam Reid: Enter your total estimated hour from your labor cost report (Including changes)
Note on C71: Sam Reid: Current Projected Total Hours = Actual Hours to Date + Remaining Projected Hours
Note on C72: Sam Reid: If you see a negative number in this row it means you are UNDER budget

## GCs - Full Project
SenSys Diagnostics
0
General Conditions Estimate
PROJECT: |  | SenSys Diagnostics | [7 empty] | DPR JOB NO: | TBD
LOCATION: |  |  |  | Mo | Weeks |  |  |  |  | ESTIMATE NO: | GMP Estimate
ARCHITECT: |  | Name | Duration | 10 | 43.3 |  |  |  |  | DATE:
CLIENT: |  | Name | [7 empty] | ESTIMATOR:
SYS
NO. | DESCRIPTION |  | QUANTITY | UNIT | UNIT COST | SUBTOTAL | ## | hours | tot hrs | TOTAL | COMMENTS
15 | JOBSITE MANAGEMENT
Management
|  | Project Executive | 43.3 | wk | 300 | 12990 | 12990 | 2 | 4
|  | Project Manager | 43.3 | wk | 3680 | 159344 | 159344 | 32 | 1385.6
|  |  | 43.3 | wk |  | 0 | 0 |  | 0
|  |  | 43.3 | wk |  | 0 | 0 |  | 0
|  |  | 43.3 | wk |  | 0 | 0 |  | 0
|  |  | 43.3 | wk |  | 0 | 0 |  | 0
|  |  | 43.3 | wk |  | 0 | 0 |  | 0
|  |  | 43.3 | wk |  | 0 | 0 |  | 0
|  |  | 43.3 | wk |  | 0 | 0 |  | 0
| SUBTOTAL: Management |  |  |  |  | 172334 |  |  | 1385.6
Jobsite Office
|  | Office Trailer (24x60) |  | mo | 1200 | 0 | 0
|  | Conference Trailer (10x30) |  | mo | 352 | 0 | 0
|  | Tool Trailer |  | mo | 325 | 0 | 0
|  | Jobsite Set-up |  | ls | 13380 | 0 | 0
| SUBTOTAL: Jobsite Office |  |  |  |  | 0
Vehicles/Travel
|  | Truck Rental, Large |  | mo | 925 | 0 | 0
|  | Travel Expenses/Tolls |  | mo | 500 | 0
| SUBTOTAL: Vehicles/Travel |  |  |  |  | 0
Jobsite Office Eq/Servcs
|  | Office Supplies | 10 | mo | 200 | 2000 | 2000
|  | Progress Photos - Digital | 0 | mo | 17.86 | 0 | 0
|  | Guard Service/Security | 0 | mo | 0 | 0 | 0
|  | Blueprinting | 0 | mo | 500 | 0 | 0 |  |  |  | Submittals Only
| SUBTOTAL: Jobsite Office Eq/Servcs |  |  |  |  | 2000
| SUBTOTAL: 15 - JOBSITE MANAGEMENT | [8 empty] | 174334
16 | PROJECT REQUIREMENTS
Equipment & Tools
|  |  |  | ls |  | 0 | 0 |  | 0
|  | Expendable Tools |  | ls |  | 0 | 0
|  |  |  | mo |  | 0 | 0
|  |  |  | mo |  | 0 | 0
| SUBTOTAL: Equipment & Tools |  |  |  |  | 0
Safety/Cleanup
|  | Safety Manager |  | wks |  | 0 | 0 |  | 0
|  |  |  | wks |  | 0 | 0
|  | Debris Boxes |  | ea |  | 0 | 0
|  | Site Fencing |  | lf |  | 0 | 0
| SUBTOTAL: Safety/Cleanup |  |  |  |  | 0
Temporary Services
|  |  |  | mo |  | 0 | 0
|  | Hand Washing Station - One Station per 20 people |  | mo |  | 0 | 0
| SUBTOTAL: Temporary Services |  |  |  |  | 0
Site Conditions
|  |  |  | ls |  | 0 | 0
|  | Winterize Site |  | ls |  | 0 | 0
|  |  |  | ea |  | 0 | 0
|  | Flagman/Traffic Control |  | mh |  | 0 | 0
| SUBTOTAL: Site Conditions |  |  |  |  | 0
| SUBTOTAL: 16 - PROJECT REQUIREMENTS | [8 empty] | 0
Subtotal | [6 empty] | 174334 |  |  | 174334
TOTAL | [9 empty] | 174334 |  | 4026.1894

## Hourly Rates
Contractor's Fixed Rates
Classification | Rates | Overtime Rates | Double-time Rates
General Conditions
Project Manager | 130 | NA | NA
Project Superintendent | 110 | NA | NA
Assistant Superintendent | 85 | NA | NA
Project Engineer | 70 | NA | NA
Field Office Coordinator | 48 | NA | NA
Project Executive | 160 | NA | NA
Project Accountant | 50 | NA | NA
MEP Coordinator | 95 | NA | NA
Safety Manager | 65 | NA | NA
Jobsite Safety | 65 | NA | NA
Project Intern | 28 | NA | NA
PreConstruction
Project Executive | 160 | NA | NA
Project Manager | 130 | NA | NA
Project Superintendent | 110 | NA | NA
Project Estimator | 95 | NA | NA
MEP Estimator | 105 | NA | NA
Estimating Assistant | 35 | NA | NA
Self-Performed Work
Laborer | 51 | 76.5 | 102
Laborer Foreman | 57 | 85.5 | 114
Carpenter | 68 | 102 | 136
Carpenter Foreman | 71 | 106.5 | 142
Drywaller/Taper | 56 | 84 | 112
Drywaller/Taper Foreman | 60 | 90 | 120
These fixed labor rates shall be used to calculate Cost of Work for the purpose of billings, change order pricing, and overall Contract compensation and being fixed in nature, the rates themselves, for each labor classification, are not subject to audit.
***These fixed labor rates are subject to differ from one Contractor/State to the next. For the purposes of this module, use these provided rates to populate your GC's. ***

## Jobsite Operations
SenSys Diagnostics
Unit Rate Sheet General Expense
|  | UNIT OF | UNIT
ITEM |  | MEASURE | RATE | COMMENTS
Pickup rental |  | MO | 800
Pickup fuel & maintenance |  | MO | 500
Small forklift |  | MO | 960
Small tools and misc equip rental |  | MO | 900
12'x60' Office Trailer Rental |  | MO | 1250 | Provide 160sf of space per staff
24'x60' Office Trailer Rental |  | MO | 2500 | Provide 160sf of space per staff
Temp office build out |  |  |  | A Carpenter can build out 14sf of office per hour.
Temp office build out material |  | SF | 4
Mobilization/Trucking |  | EA | 6250
Temp toilets/wash stations |  | MO | 135 | Assume one per ten workers per month
Temp water-drinking |  | MO | 50
Parking |  | DAY | 8 | Allow for parking of each jobsite staff member for their duration
Project signs |  | EA | 1300
Courier/express service |  | MO | 500
Telephone system install |  | LS | 2000
Office supplies |  | MO | 800
Office furniture/equipment |  | LS | 7500
Copier |  | MO | 650
Photos |  | MO | 125
Medical equip/supplies |  | LS | 125
Warning/safety signs |  | LS | 2000
Stairs and ladders/Scaffolding |  | VLF | 20 | Monthly Cost per VLF
Stairs and ladders install |  |  |  | Allow for a Laborer 1 hr/vlf for set-up and takedown
Housekeeping |  |  |  | Allow for 2 Laborers for 3 hrs per day for project duration
Trash disposal |  | WK | 2080
As-built drawings |  | LS | 5500
Drawing reproduction |  | LS | 10000
Construction drawings |  | EA | 350
Material for protecting finishes |  | SF | 0.1
Note: | If your plan requires a unit rate that is not found above, establish a rate based upon appropriate information (such as Means, etc.)
You may not need all of these items. Base these inclusions off of the project, and how it will be set up.