## Labor Projection Worksheet
Need to Add G&A to Date/ Site Req F/C
Preconstruction Services?
| Labor Cost Projection Worksheet |  | 2016-04-01 | 2016-04-08 | 2016-04-15 | Total Hours | Rate | Subtotals | mPower Budget | Delta
| Project Executive - TBD |  | 0 | 0 | 0 | 0 | 135 | 0 |  | 0
| Project Manager - TBD |  | 0 | 0 | 0 | 0 | 100 | 0 |  | 0
| Superintendent - TBD |  | 0 | 0 | 0 | 0 | 100 | 0 |  | 0
| Asst Superintendent - TBD |  | 0 | 0 | 0 | 0 | 65 | 0
| Project Engineer - TBD |  | 0 | 0 | 0 | 0 | 65 | 0 |  | 0
| TBD |  | 0 | 0 | 0 | 0 | 65 | 0 |  | 0
| TBD |  | 0 | 0 | 0 | 0 | 65 | 0 |  | 0
| Project Accountant - TBD |  | 0 | 0 | 0 | 0 | 50 | 0 |  | 0
| FOC - TBD |  | 0 | 0 | 0 | 0 | 42 | 0 |  | 0
| MEP Coordinator - TBD |  | 0 | 0 | 0 | 0 | 95 | 0 |  | 0
| Safety Coordinator - TBD |  | 0 | 0 | 0 | 0 | 65 | 0
| TBD |  | 0 | 0 | 0 |  | 65
|  |  | 0 | 0 | 0 |  | 66
| Totals | Projected Weekly Hours | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Means that the cell has a formula in it.
Note on H3: Sam Reid: Make sure you check your actual labor rates in your owner contract AND on your labor transaction report

## GCs - Full Project
SoundWave Studios
555 Decibels CT.
General Conditions Estimate
PROJECT: |  | SoundWave Studios | [7 empty] | DPR JOB NO: | TBD
LOCATION: |  | 555 Decibels CT. |  | Mo | Weeks |  |  |  |  | ESTIMATE NO: | GMP Estimate
ARCHITECT: |  | Name | Duration |  | 0 |  |  |  |  | DATE:
CLIENT: |  | Name | [7 empty] | ESTIMATOR:
SYS
NO. | DESCRIPTION |  | QUANTITY | UNIT | UNIT COST | SUBTOTAL | ## | hours | tot hrs | TOTAL | COMMENTS
15 | JOBSITE MANAGEMENT
Management
|  | Projejct Executive | 0 | wk | 0 | 0 | 0 |  | 4
|  |  | 0 | wk | 0 | 0 | 0 |  | 0
|  |  | 0 | wk | 0 | 0 | 0 |  | 0
|  |  | 0 | wk | 0 | 0 | 0 |  | 0
|  |  | 0 | wk | 0 | 0 | 0 |  | 0
|  |  | 0 | wk | 0 | 0 | 0 |  | 0
|  |  | 0 | wk | 0 | 0 | 0 |  | 0
|  |  | 0 | wk | 0 | 0 | 0 |  | 0
|  |  | 0 | wk | 0 | 0 | 0 |  | 0
| SUBTOTAL: Management |  |  |  |  | 0 |  |  | 0
Jobsite Office
|  | Office Trailer (24x60) | 0 | mo | 0 | 0 | 0
|  |  | 0 | mo | 0 | 0 | 0
|  |  | 0 | mo | 0 | 0 | 0
|  | Jobsite Set-up | 0 | ls | 0 | 0 | 0
| SUBTOTAL: Jobsite Office |  |  |  |  | 0
Vehicles/Travel
|  | Travel Expenses/Tolls | 0 | mo | 0 | 0 | 0
|  |  | 0 | mo | 0 | 0 | 0
|  |  | 0 | mo | 0 | 0 | 0
|  |  | 0 | mo | 0 | 0
| SUBTOTAL: Vehicles/Travel |  |  |  |  | 0
Jobsite Office Eq/Servcs
|  | Office Supplies | 0 | mo | 0 | 0 | 0
|  |  | 0 | mo | 0 | 0 | 0
|  |  | 0 | mo | 0 | 0 | 0
|  |  | 0 | mo | 0 | 0 | 0
| SUBTOTAL: Jobsite Office Eq/Servcs |  |  |  |  | 0
| SUBTOTAL: 15 - JOBSITE MANAGEMENT | [8 empty] | 0
16 | PROJECT REQUIREMENTS
Equipment & Tools
|  |  | 0 | ls |  | 0 | 0 |  | 0
|  | Expendable Tools | 0 | ls |  | 0 | 0
|  |  | 0 | mo |  | 0 | 0
|  |  | 0 | mo |  | 0 | 0
| SUBTOTAL: Equipment & Tools |  |  |  |  | 0
Safety/Cleanup
|  | Safety Manager | 0 | wks |  | 0 | 0 |  | 0
|  |  | 0 | wks |  | 0 | 0
|  | Debris Boxes | 0 | ea |  | 0 | 0
|  | Site Fencing | 0 | lf |  | 0 | 0
| SUBTOTAL: Safety/Cleanup |  |  |  |  | 0
| Temporary Services |  | 0
|  |  | 0 | mo |  | 0 | 0
|  | Hand Washing Station - One Station per 20 people | 0 | mo |  | 0 | 0
| SUBTOTAL: Temporary Services |  |  |  |  | 0
Site Conditions
|  |  | 0 | ls |  | 0 | 0
|  | Winterize Site | 0 | ls |  | 0 | 0
|  |  | 0 | ea |  | 0 | 0
|  | Flagman/Traffic Control |  | mh |  | 0 | 0
| SUBTOTAL: Site Conditions |  |  |  |  | 0
| SUBTOTAL: 16 - PROJECT REQUIREMENTS | [8 empty] | 0
Subtotal | [6 empty] | 0 |  |  | 0
TOTAL | [9 empty] | 0 | Total/Weeks | #DIV/0!

## Labor Mgmt Hourly Rates
Contractor's Fixed Rates
Classification | Rates | Overtime Rates | Double-time Rates
General Conditions
Project Manager | 130 | NA | NA
Project Superintendent | 110 | NA | NA
Assistant Superintendent | 85 | NA | NA
Project Engineer | 70 | NA | NA
Field Office Coordinator | 48 | NA | NA
Project Executive | 160 | NA | NA
Project Accountant | 50 | NA | NA
MEP Coordinator | 95 | NA | NA
Safety Manager | 65 | NA | NA
Jobsite Safety | 65 | NA | NA
Project Intern | 28 | NA | NA
PreConstruction
Project Executive | 160 | NA | NA
Project Manager | 130 | NA | NA
Project Superintendent | 110 | NA | NA
Project Estimator | 95 | NA | NA
MEP Estimator | 105 | NA | NA
Estimating Assistant | 35 | NA | NA
Self-Performed Work
Laborer | 51 | 76.5 | 102
Laborer Foreman | 57 | 85.5 | 114
Carpenter | 68 | 102 | 136
Carpenter Foreman | 71 | 106.5 | 142
Drywaller/Taper | 56 | 84 | 112
Drywaller/Taper Foreman | 60 | 90 | 120
These fixed labor rates shall be used to calculate Cost of Work for the purpose of billings, change order pricing, and overall Contract compensation and being fixed in nature, the rates themselves, for each labor classification, are not subject to audit.
***These fixed labor rates are subject to differ from one Contractor/State to the next. For the purposes of this module, use these provided rates to populate your GC's. ***

## Jobsite Operations
SoundWave Studios
Unit Rate Sheet General Expense
|  | UNIT OF | UNIT
ITEM |  | MEASURE | RATE | COMMENTS
Pickup rental |  | MO | 800
Pickup fuel & maintenance |  | MO | 500
Small forklift |  | MO | 960
Small tools and misc equip rental |  | MO | 900
12'x60' Office Trailer Rental |  | MO | 1250 | Provide 160sf of space per staff
24'x60' Office Trailer Rental |  | MO | 2500 | Provide 160sf of space per staff
Temp office build out |  |  |  | A Carpenter can build out 14sf of office per hour.
Temp office build out material |  | SF | 4
Mobilization/Trucking |  | EA | 6250
Temp toilets/wash stations |  | MO | 135 | Assume one per ten workers per month
Temp water-drinking |  | MO | 50
Parking |  | DAY | 8 | Allow for parking of each jobsite staff member for their duration
Project signs |  | EA | 1300
Courier/express service |  | MO | 500
Telephone system install |  | LS | 2000
Office supplies |  | MO | 800
Office furniture/equipment |  | LS | 7500
Copier |  | MO | 650
Photos |  | MO | 125
Medical equip/supplies |  | LS | 125
Warning/safety signs |  | LS | 2000
Stairs and ladders/Scaffolding |  | VLF | 20 | Monthly Cost per VLF
Stairs and ladders install |  |  |  | Allow for a Laborer 1 hr/vlf for set-up and takedown
Housekeeping |  |  |  | Allow for 2 Laborers for 3 hrs per day for project duration
Trash disposal |  | WK | 2080
As-built drawings |  | LS | 5500
Drawing reproduction |  | LS | 10000
Construction drawings |  | EA | 350
Material for protecting finishes |  | SF | 0.1
Crane mobilization |  | EA | 10000
Crane rental |  | DAY | 2000
Note: | If your plan requires a unit rate that is not found above, establish a rate based upon appropriate information (such as Means, etc.)
You may not need all of these items. Base these inclusions off of the project, and how it will be set up.