## SUMMARY (hidden)
Initial Financial Status
School | Rep | Direct Cost | Fee % | Fee | Contingency |  | Sum
Arizona State University | Kaitlin | 123010221 | 1.5% | 1845153.315 | 1438400.823 |  | 3283554.138
Boise State University | Brittany | 122173905 | 2% | 2443478.1 | 1694790.99 |  | 4138269.09
Brigham Young University | Erin | 122587436.83 | 1.5% | 1838811.5524 | 1876828.0073 |  | 3715639.5597
California Polytechnic State University, SLO | Dan | 123074443.83 | 1.2% | 1476893.326 | 1741025.0798 |  | 3217918.4057
California State University, Sacramento | Todd | 123621860 | 1.34% | 1656532.924 | 1001926.156 |  | 2658459.08
Oregon State University | Brieann | 121845771 | 1% | 1218457.71 | 3255164.328 |  | 4473622.038
University of Washington | Chris | 121845771 | 1% | 1218457.71 | 3255164.328 |  | 4473622.038
Utah Valley University | Nick | 122433915.83 | 2% | 2448678.3166 | 1423859.7051 |  | 3872538.0217
Final Scoring
|  | Contract |  |  | Financial Results | [5 empty] | Schedule Results |  |  |  | Reputation Results |  |  | Presentation |  |  | Total
|  | Critical | Innovative | Negotiation | Remaining |  |  | Fee |  |  | Liquidated | Schedule | [5 empty] | Content | Style
|  | Issues | Issues | Skills | Contingency |  |  | Position |  |  | Damages | Impacts
|  | 8 | 2 | 10 | 25% |  | 10 |  |  | 10 |  |  |  | 20 |  |  | 20 | 10 | 10 |  | 100
Rank:
Average |  | 3.75 | 1.125 | 6.375 | 874080.3688 |  |  | 1958872.4923 |  |  | 14625 | 6.5 |  |  | 25.125 |  |  | 14.875 | #DIV/0!
Arizona State University | Kaitlin | 3.5 | 2 | 6 | 634855.823 | 2 | 462.0441 | 1852769.2707 | 3 | 12.5359 | 5000 | 4 | days | 8 | 27 | 13 | 60 | 17 |  |  | 54.5
Boise State University | Brittany | 4 | 2 | 6 | 859912.99 | 3 | 625.8393 | 2507358.3475 | 10 | 16.9649 | 20000 | 5 | days | 9 | 33 | 18 | 73.3333 | 14 |  |  | 66
Brigham Young University | Erin | 4.5 | 1 | 5.5 | 666891.0073 | 2 | 485.3591 | 1858534.3043 | 3 | 12.5749 | 20000 | 1 | days | 1 | 17 | 7 | 37.7778 | 15 |  |  | 39
California Polytechnic State University, SLO | Dan | 4.5 | 0 | 8 | 998499.0798 | 3 | 726.7014 | 1592920.0959 | 1 | 10.7778 | 20000 | 16 | days | 20 | 28 | 14 | 62.2222 | 19 |  |  | 69.5
California State University, Sacramento | Todd | 4 | 1 | 5.5 | 13740.156 | 1 | 10 | 1477967.963 | 1 | 10 | 7000 | 9 | days | 15 | 9 | 0 | 20 | 10 |  |  | 37.5
Oregon State University | Brieann | 1 | 2 | 7 | 2719523.328 | 10 | 1979.2521 | 1584740.542 | 1 | 10.7224 | 5000 | 5 | days | 9 | 28 | 14 | 62.2222 | 11 |  |  | 55
University of Washington | Chris | 3 | 0 | 7 | 661711.7051 | 2 | 481.5897 | 2453008.2429 | 9 | 16.5972 | 20000 | 2 | days | 3 | 24 | 12 | 53.3333 | 13 |  |  | 49
Utah Valley University | Nick | 5.5 | 1 | 6 | 437508.8611 | 1 | 318.4162 | 2343681.1719 | 8 | 15.8575 | 20000 | 10 | days | 16 | 35 | 20 | 77.7778 | 20 |  |  | 77.5
Presentation | Kaitlin |  | Nick |  | Mike |  |  | Dan |  |  | Todd |  | Brittany |  | Brieann |  |  | SUM |  | Score
| Content | Style | Content | Style | Content |  | Style | Content |  | Style | Content | Style | Content | Style | Content |  | Style | Content | Style | Content | Style
Arizona State University | 3 |  | 3 |  | 3 |  |  | 4 |  |  | 3 |  | 4 |  | 4 |  |  | 24 | 0 | 10 | 9 | 24 | 17
Boise State University | 4 |  | 7 |  | 6 |  |  | 3 |  |  | 6 |  | 3 |  | 6 |  |  | 35 | 0 | 9 | 7 | 35 | 14
Brigham Young University | 5 |  | 4 |  | 4 |  |  | 5 |  |  | 5 |  | 5 |  | 3 |  |  | 31 | 0 | 8 | 8 | 31 | 15
California Polytechnic State University, SLO | 2 |  | 2 |  | 2 |  |  | 2 |  |  | 2 |  | 1 |  | 2 |  |  | 13 | 0 | 7 | 10 | 13 | 19
California State University, Sacramento | 8 |  | 8 |  | 8 |  |  | 8 |  |  | 7 |  | 8 |  | 8 |  |  | 55 | 0 | 6 | 4 | 55 | 10
Oregon State University | 7 |  | 6 |  | 7 |  |  | 7 |  |  | 8 |  | 7 |  | 7 |  |  | 49 | 0 | 5 | 6 | 49 | 11
University of Washington | 6 |  | 5 |  | 5 |  |  | 6 |  |  | 4 |  | 6 |  | 5 |  |  | 37 | 0 | 4 | 5 | 37 | 13
Utah Valley University | 1 |  | 1 |  | 1 |  |  | 1 |  |  | 1 |  | 2 |  | 1 |  |  | 8 | 0 | 3 | 3 | 8 | 20
|  | Critical | Innovative | Negotiation | Remaining |  |  | Fee |  |  | Liquidated | Schedule |  |  | Reputation |  |  | Content | Style
|  | Issues | Issues | Skills | Contingency |  |  | Position |  |  | Damages | Impacts
Arizona State University |  | -6.667% | 77.78% | -5.882% | -27.37% |  |  | -5.417% |  |  | -65.81% | 61.54% |  |  | 7.463% |  |  | 14.29% | #DIV/0!
Boise State University |  | 6.667% | 77.78% | -5.882% | -1.621% |  |  | 28% |  |  | 36.75% | 76.92% |  |  | 31.34% |  |  | -5.882% | #DIV/0!
Brigham Young University |  | 20% | -11.11% | -13.73% | -23.7% |  |  | -5.122% |  |  | 36.75% | 15.38% |  |  | -32.34% |  |  | 0.8403% | #DIV/0!
California Polytechnic State University, SLO |  | 20% | -100% | 25.49% | 14.23% |  |  | -18.68% |  |  | 36.75% | 246.2% |  |  | 11.44% |  |  | 27.73% | #DIV/0!
California State University, Sacramento |  | 6.667% | -11.11% | -13.73% | -98.43% |  |  | -24.55% |  |  | -52.14% | 138.5% |  |  | -64.18% |  |  | -32.77% | #DIV/0!
Oregon State University |  | -73.33% | 77.78% | 9.804% | 211.1% |  |  | -19.1% |  |  | -65.81% | 76.92% |  |  | 11.44% |  |  | -26.05% | #DIV/0!
University of Washington |  | -20% | -100% | 9.804% | -24.3% |  |  | 25.23% |  |  | 36.75% | 30.77% |  |  | -4.478% |  |  | -12.61% | #DIV/0!
Utah Valley University |  | 46.67% | -11.11% | -5.882% | -49.95% |  |  | 19.64% |  |  | 36.75% | 153.8% |  |  | 39.3% |  |  | 34.45% | #DIV/0!

## Score Template (hidden)
Scenario Scoring
Schedule
| S# | School | Contract | Contingency | Float | Weather | Reputation | Comments
1 | Interior Rough In
2 | IR# | ASU | 0 | 0 | 0 | 0 | 0
3 | IR# | Boise State | 0 | 0 | 0 | 0 | 0
4 | IR# | BYU | 0 | 0 | 0 | 0 | 0
5 | IR# | Cal Poly | 0 | 0 | 0 | 0 | 0
6 | IR# | Sac State | 0 | 0 | 0 | 0 | 0
7 | IR# | Oregon State | 0 | 0 | 0 | 0 | 0
8 | IR# | Washington | 0 | 0 | 0 | 0 | 0
| IR# | UVU | 0 | 0 | 0 | 0 | 0
11 | IR# | ASU | 0 | 0 | 0 | 0 | 0
12 | IR# | Boise | 0 | 0 | 0 | 0 | 0
13 | IR# | BYU | 0 | 0 | 0 | 0 | 0
14 | IR# | Cal Poly | 0 | 0 | 0 | 0 | 0
15 | IR# | Sac State | 0 | 0 | 0 | 0 | 0
16 | IR# | Oregon State | 0 | 0 | 0 | 0 | 0
17 | IR# | Washington | 0 | 0 | 0 | 0 | 0
18 | IR# | UVU | 0 | 0 | 0 | 0 | 0
20 | Finishes
21 | FN# | ASU | 0 | 0 | 0 | 0 | 0
22 | FN# | Boise State | 0 | 0 | 0 | 0 | 0
23 | FN# | BYU | 0 | 0 | 0 | 0 | 0
24 | FN# | Cal Poly | 0 | 0 | 0 | 0 | 0
25 | FN# | Sac State | 0 | 0 | 0 | 0 | 0
26 | FN# | Oregon State | 0 | 0 | 0 | 0 | 0
27 | FN# | Washington | 0 | 0 | 0 | 0 | 0
29 | FN# | UVU | 0 | 0 | 0 | 0 | 0
30 | FN# | ASU | 0 | 0 | 0 | 0 | 0
31 | FN# | Boise | 0 | 0 | 0 | 0 | 0
32 | FN# | BYU | 0 | 0 | 0 | 0 | 0
33 | FN# | Cal Poly | 0 | 0 | 0 | 0 | 0
34 | FN# | Sac State | 0 | 0 | 0 | 0 | 0
35 | FN# | Oregon State | 0 | 0 | 0 | 0 | 0
36 | FN# | Washington | 0 | 0 | 0 | 0 | 0
37 | FN# | UVU | 0 | 0 | 0 | 0 | 0
39 | Equipment & Commissioning
40 | EQ# | ASU | 0 | 0 | 0 | 0 | 0
41 | EQ# | Boise State | 0 | 0 | 0 | 0 | 0
42 | EQ# | BYU | 0 | 0 | 0 | 0 | 0
43 | EQ# | Cal Poly | 0 | 0 | 0 | 0 | 0
44 | EQ# | Sac State | 0 | 0 | 0 | 0 | 0
45 | EQ# | Oregon State | 0 | 0 | 0 | 0 | 0
46 | EQ# | Washington | 0 | 0 | 0 | 0 | 0
47 | EQ# | UVU | 0 | 0 | 0 | 0 | 0
49 | EQ# | ASU | 0 | 0 | 0 | 0 | 0
50 | EQ# | Boise | 0 | 0 | 0 | 0 | 0
51 | EQ# | BYU | 0 | 0 | 0 | 0 | 0
52 | EQ# | Cal Poly | 0 | 0 | 0 | 0 | 0
53 | EQ# | Sac State | 0 | 0 | 0 | 0 | 0
54 | EQ# | Oregon State | 0 | 0 | 0 | 0 | 0
55 | EQ# | Washington | 0 | 0 | 0 | 0 | 0
56 | EQ# | UVU | 0 | 0 | 0 | 0 | 0
58 | Closeout
59 | CO# | ASU | 0 | 0 | 0 | 0 | 0
60 | CO# | Boise State | 0 | 0 | 0 | 0 | 0
61 | CO# | BYU | 0 | 0 | 0 | 0 | 0
62 | CO# | Cal Poly | 0 | 0 | 0 | 0 | 0
63 | CO# | Sac State | 0 | 0 | 0 | 0 | 0
64 | CO# | Oregon State | 0 | 0 | 0 | 0 | 0
65 | CO# | Washington | 0 | 0 | 0 | 0 | 0
66 | CO# | UVU | 0 | 0 | 0 | 0 | 0
68 | CO# | ASU | 0 | 0 | 0 | 0 | 0
69 | CO# | Boise | 0 | 0 | 0 | 0 | 0
70 | CO# | BYU | 0 | 0 | 0 | 0 | 0
71 | CO# | Cal Poly | 0 | 0 | 0 | 0 | 0
72 | CO# | Sac State | 0 | 0 | 0 | 0 | 0
73 | CO# | Oregon State | 0 | 0 | 0 | 0 | 0
74 | CO# | Washington | 0 | 0 | 0 | 0 | 0
75 | CO# | UVU | 0 | 0 | 0 | 0 | 0

## ASU (hidden)
ASU Sun Devils
Schedule
Baseline |  | Contract | Contingency | Float | Weather | Reputation | Comments | Fee
|  | 131000000 | 1438400.823 | 14 | 0 | 25 |  | 1845153.315
Lean Planning |  |  |  | 0 |  | 3 |  | -151098
Interior Rough In | [7 empty] | 1694055.315
IR#1 | Chris |  | -20000 | 0 |  | 0
IR#2 | Kaitlin |  | -5000 | 0 |  | -2
IR#3 | Todd |  | 0 | -1 |  | -1
IR#4 | Brittany |  | 0 | 0 |  | 0
IR#5 | Brieann |  | -12500 | -2 |  | -1
IR#6 | Dan |  | 0 | -2 |  | 0
Bonus
IR Status |  | 131000000 | 1400900.823 | 9 | 0 | 24
Team Status |  | 131000000
Delta |  | 0 | 1400900.823 | 9 |  | -
Finishes
FN#1 | Chris |  | 0 | 0 |  | -1
FN#2 | Brittany |  | -27000 | -1 |  | -2
FN#3 | Dan |  | -30000 | -3 |  | 1
FN#4 | Kaitlin |  | 0 | 0 |  | 2
FN#5 | Brianne |  | -40000 | -1 |  | -1
FN#6 | Brittany |  | 0 | 0 |  | -1
FN#7 | Dan | 40000 | 0 | 0 |  | -1 | Did not include added contract amount
FN#8 | Kaitlin |  | 0 | 0 |  | -1 |  | -17500
FN#9 | Brianne | [6 empty] | -133598
Bonus
FN Status |  | 131040000 | 1303900.823 | 4 | 0 | 20 | 3K off in contingency
Team Status | [6 empty] | Float is off by 6 days.
Delta |  | 131040000 | 1303900.823 | 4 |  | 20
Equipment & Commissioning
EC#1 | Dan |  | -225000 | 0 |  | 0
EC#2 | Chris |  | -200000 | 0 |  | 0
EC#3 | Brittany |  | -27712 | 0 |  | 1
EC#4 | Todd |  | 0 | 0 |  | -3
EC#5 | Dan |  | -40000 | 0 |  | 0
EC#6 | Kaitlin |  | 0 | 0 |  | 2
EC#7 | Brianne |  | -25000 | 0 |  | 0
EC#8 | Brittany |  | -85333 | 0 |  | 2
EC#10 | Kaitlin |  | 0 | 0 |  | 1
E&C Status |  | 131040000 | 700855.823 | 4 | 0 | 23
Team Status
Delta |  | 131040000 | 700855.823 | 4 |  | -
Closeout
CO#1 | Chris |  | -35500 | 0 |  | 2
CO#2 | Dan |  | -10000 | 0 |  | 0
CO#3 | Brianne |  | -8000 | 0 |  | 0
CO#4 | Brittany |  | -2500 | 0 |  | 0
CO#5 | Chris
CO#6 | Todd |  | -10000 | 0 |  | 2
Bonus
CO Status |  | 131040000 | 634855.823 | 4 | 0 | 27
Team Status |  |  |  | 0 | 0
Delta |  | 131040000 | 634855.823 | 4 |  | -

## Boise (hidden)
Boise St Broncos
Schedule
Baseline |  | Contract | Contingency | Float | Weather | Reputation | Comments | Fee
|  | 131000000 | 1694790.99 | 14 | 0 | 25 |  | 2443478.1
Lean Planning |  |  |  | 0 |  | 3 |  | -151098
Interior Rough In | [7 empty] | 2292380.1
IR#1 | Chris |  | 0 | 0 |  | -1
IR#2 | Kaitlin |  | -12500 | 0 |  | -1
IR#3 | Todd |  | -12000 | 0 |  | -1
IR#4 | Brittany |  | 0 | 0 |  | 0
IR#5 | Brieann |  | 0 | -2 |  | 0
IR#6 | Dan |  | 0 | 0 |  | 1
Bonus
IR Status |  | 131000000 | 1670290.99 | 12 | 0 | 26
Team Status |  | 131000000
Delta |  | 0 | 1670290.99 | 12 |  | -
Finishes
FN#1 | Chris |  | 0 | 0 |  | -1
FN#2 | Brittany |  | -7000 | -1 |  | 2
FN#3 | Dan |  | -25000 | 0 |  | 0 | recorded 25 k
FN#4 | Kaitlin |  | 0 |  | 0 | 3
FN#5 | Brianne |  | -80000 | -1 |  | 2
FN#6 | Brittany |  | 0 | 0 |  | -1
FN#7 | Dan | 45000 | 0 | -3 |  | -3
FN#8 | Kaitlin |  | 0 | 0 |  | -1 |  | -17500
FN#9 | Brianne | [6 empty] | -133598
Bonus
FN Status |  | 131045000 | 1558290.99 | 7 | 0 | 27 | overll contingency off by 4k
Team Status | [6 empty] | overall float off by 2 days
Delta |  | 131045000 | 1558290.99 | 7 |  | 27
Equipment & Commissioning
EC#1 | Dan |  | -225000 | 0 |  | -1
EC#2 | Chris |  | -200000 | 0 |  | 0
EC#3 | Brittany |  | -27712 | 0 |  | 1
EC#4 | Todd |  | -50000 | -2 |  | 1
EC#5 | Dan |  | -50000 | 0 |  | 0
EC#6 | Kaitlin |  | -22500 | 0 |  | 0
EC#7 | Brianne |  | -10000 | 0 |  | 0
EC#8 | Brittany |  | -42666 | 0 |  | 2
EC#10 | Kaitlin |  | 0 | 0 |  | 1
E&C Status |  | 131045000 | 930412.99 | 5 | 0 | 31
Team Status
Delta |  | 131045000 | 930412.99 | 5 |  | -
Closeout
CO#1 | Chris |  | -40000 | 0 |  | 1
CO#2 | Dan |  | -10000 | 0 |  | 0
CO#3 | Brianne |  | -8000 | 0 |  | 0
CO#4 | Brittany |  | -2500 | 0 |  | 0
CO#5 | Chris
CO#6 | Todd |  | -10000 | 0 |  | 1
Bonus
CO Status |  | 131045000 | 859912.99 | 5 | 0 | 33
Team Status |  |  |  | 0 | 0
Delta |  | 131045000 | 859912.99 | 5 |  | -

## BYU (hidden)
BYU Cougars
Schedule
Baseline |  | Contract | Contingency | Float | Weather | Reputation | Comments | Fee
|  | 131000000 | 1876828.0073 | 14 | 0 | 25 |  | 1838811.5524
Lean Planning |  |  |  | 0 |  | 1 |  | -147000
Interior Rough In | [7 empty] | 1691811.5524
IR#1 | Chris |  | -20000 | 0 |  | 1
IR#2 | Kaitlin |  | -16250 | 0 |  | -3
IR#3 | Todd |  | -12500 | -1 |  | 0
IR#4 | Brittany |  | 0 | 0 |  | -1
IR#5 | Brieann |  | -25000 | -2 |  | -1
IR#6 | Dan |  | 0 | -2 |  | -1
Bonus
IR Status |  | 131000000 | 1803078.0073 | 9 | 0 | 21
Team Status |  | 131000000
Delta |  | 0 | 1803078.0073 | 9 |  | -
Finishes
FN#1 | Chris |  | 0 | 0 |  | -2
FN#2 | Brittany |  | -27000 | -1 |  | 0 | welker floor coverings
FN#3 | Dan |  | -30000 | -3 |  | 1
FN#4 | Kaitlin |  | 0 | 0 |  | -2
FN#5 | Brianne |  | -40000 | 2 |  | 1
FN#6 | Brittany |  | -12687 | -1 |  | 0
FN#7 | Dan | 45000 | 0 | -3 |  | 0
FN#8 | Kaitlin |  | 0 | 0 |  | -2 |  | -15000
FN#9 | Brianne | [6 empty] | -132000
Bonus
FN Status |  | 131045000 | 1693391.0073 | 3 | 0 | 17 | Contingecny Erosion is correct
Team Status | [6 empty] | Float is off by 6 days
Delta |  | 131045000 | 1693391.0073 | 3 |  | 17
Equipment & Commissioning
EC#1 | Dan |  | -225000 | 0 |  | -1
EC#2 | Chris |  | -600000 | 0 |  | -2
EC#3 | Brittany |  | -3500 | 0 |  | 0
EC#4 | Todd |  | -50000 | -2 |  | 1
EC#5 | Dan |  | -50000 | 0 |  | -1
EC#6 | Kaitlin |  | 0 | 0 |  | 2
EC#7 | Brianne |  | -5000 | 0 |  | 0
EC#8 | Brittany |  | 0 | 0 |  | -2
EC#10 | Kaitlin |  | 0 | 0 |  | -2
E&C Status |  | 131045000 | 759891.0073 | 1 | 0 | 12
Team Status
Delta |  | 131045000 | 759891.0073 | 1 |  | -
Closeout
CO#1 | Chris |  | -35500 | 0 |  | 1
CO#2 | Dan |  | -5000 | 0 |  | 0
CO#3 | Brianne |  | 0 | 0 |  | 1
CO#4 | Brittany |  | -2500 | 0 |  | 0
CO#5 | Chris
CO#6 | Todd |  | -50000 | 0 |  | 3
Bonus
CO Status |  | 131045000 | 666891.0073 | 1 | 0 | 17
Team Status |  |  |  | 0 | 0
Delta |  | 131045000 | 666891.0073 | 1 |  | -

## Cal Ploy (hidden)
Cal Poly Mustangs
Schedule
Baseline |  | Contract | Contingency | Float | Weather | Reputation | Comments | Fee
|  | 131000000 | 1741025.0798 | 14 | 0 | 25 |  | 1476893.326
Lean Planning |  |  |  | 0 |  | 3 |  | -133598
Interior Rough In | [7 empty] | 1343295.326
IR#1 | Chris |  | -20000 | 0 |  | 0
IR#2 | Kaitlin |  | -12500 | 0 |  | -1
IR#3 | Todd |  | -30000 | 0 |  | 0
IR#4 | Brittany |  | 0 | 0 |  | 0
IR#5 | Brieann |  | -10000 | -2 |  | 0
IR#6 | Dan |  | 0 | 0 |  | 0
Bonus
IR Status |  | 131000000 | 1668525.0798 | 12 | 0 | 27
Team Status |  | 131000000
Delta |  | 0 | 1668525.0798 | 12 |  | -
Finishes
FN#1 | Chris |  | 0 | 0 |  | -1
FN#2 | Brittany |  | -5000 | 0 |  | 0
FN#3 | Dan | 30000 | 0 | 3 |  | -2
FN#4 | Kaitlin |  | 0 | 0 |  | 2
FN#5 | Brianne |  | -40000 | -1 |  | 1
FN#6 | Brittany |  | -10348 | 0 |  | 1
FN#7 | Dan | 45000 | 0 | 3 |  | -1
FN#8 | Kaitlin |  | 0 | 0 |  | 3 |  | 0
FN#9 | Brianne | [6 empty] | -133598
Bonus
FN Status |  | 131075000 | 1613177.0798 | 17 | 0 | 30 | Float is off by 2 days
Team Status
Delta |  | 131075000 | 1613177.0798 | 17 |  | 30
Equipment & Commissioning
EC#1 | Dan |  | -225000 | 0 |  | -1
EC#2 | Chris |  | -200000 | 0 |  | 0
EC#3 | Brittany |  | -27712 | 0 |  | 1
EC#4 | Todd |  | -30000 | -1 |  | 1
EC#5 | Dan |  | -40000 | 0 |  | 0
EC#6 | Kaitlin |  | 0 | 0 |  | -3
EC#7 | Brianne |  | -5000 | 0 |  | 0
EC#8 | Brittany |  | -42666 | 0 |  | 2
EC#10 | Kaitlin |  | 0 | 0 |  | -2
E&C Status |  | 131075000 | 1042799.0798 | 16 | 0 | 28
Team Status
Delta |  | 131075000 | 1042799.0798 | 16 |  | -
Closeout
CO#1 | Chris |  | -20500 | 0 |  | -3
CO#2 | Dan |  | -5800 | 0 |  | 1
CO#3 | Brianne |  | -8000 | 0 |  | 0
CO#4 | Brittany |  | 0 | 0 |  | 1
CO#5 | Chris
CO#6 | Todd |  | -10000 | 0 |  | 1
Bonus
CO Status |  | 131075000 | 998499.0798 | 16 | 0 | 28
Team Status |  |  |  | 0 | 0
Delta |  | 131075000 | 998499.0798 | 16 |  | -

## Sac State (hidden)
Sac State
Schedule
Baseline |  | Contract | Contingency | Float | Weather | Reputation | Comments | Fee
|  | 131000000 | 1001926.156 | 14 | 0 | 25 |  | 1656532.924
Lean Planning |  |  |  | 0 |  | 0 |  | -182000
Interior Rough In | [7 empty] | 1474532.924
IR#1 | Chris |  | -20000 | 0 |  | 0
IR#2 | Kaitlin |  | -10000 | 0 |  | 1
IR#3 | Todd |  | -12500 | -1 |  | 0
IR#4 | Brittany |  | 0 | 0 |  | 0
IR#5 | Brianne |  | -25000 | -2 |  | -3
IR#6 | Dan |  | 0 | 0 |  | 1 | off by 30k- Contingency
Bonus
IR Status |  | 131000000 | 934426.156 | 11 | 0 | 24
Team Status |  | 131000000
Delta |  | 0 | 934426.156 | 11 |  | -
Finishes
FN#1 | Chris |  | 0 | 0 |  | -1
FN#2 | Brittany |  | -27000 | -1 |  | -1
FN#3 | Dan | 25000 | 0 | 3 |  | -2
FN#4 | Kaitlin |  | 0 | 0 |  | -2
FN#5 | Brianne |  | -80000 | -2 |  | 0
FN#6 | Brittany |  | -5000 | 0 |  | 0
FN#7 | Dan | 45000 | 0 | 3 |  | -2
FN#8 | Kaitlin |  | 0 | 0 |  | -3 |  | 0
FN#9 | Brianne | [6 empty] | -132000
Bonus
FN Status |  | 131070000 | 822426.156 | 14 | 0 | 13 | contingecy is off by 1M
Team Status
Delta |  | 131070000 | 822426.156 | 14 |  | 13
Equipment & Commissioning
EC#1 | Dan |  | -225000 | 0 |  | 0
EC#2 | Chris |  | -200000 | 0 |  | 0
EC#3 | Brittany |  | 27712 | 0 |  | -2
EC#4 | Todd |  | -50000 | 0 |  | 1
EC#5 | Dan |  |  | 0 |  | -1 | Under Dispute | -50000
EC#6 | Kaitlin |  | 0 | 0 |  | 2
EC#7 | Brianne |  | -25000 | 0 |  | 0
EC#8 | Brittany |  | -301398 | -5 |  | -3
EC#10 | Kaitlin |  | 0 | 0 |  | -2
E&C Status |  | 131070000 | 48740.156 | 9 | 0 | 8 | recording 3 day gian via todd
Team Status
Delta |  | 131070000 | 48740.156 | 9 |  | -
Closeout
CO#1 | Chris |  | -15000 | 0 |  | -1
CO#2 | Dan |  | -10000 | 0 |  | 0
CO#3 | Brianne |  | 0 | 0 |  | 0
CO#4 | Brittany |  | 0 | 0 |  | 1
CO#6 | Todd |  | -10000 | 0 |  | 1
Bonus
CO Status |  | 131070000 | 13740.156 | 9 | 0 | 9
Team Status |  |  |  | 0 | 0
Delta |  | 131070000 | 13740.156 | 9 |  | -

## Oregon (hidden)
Oregon
Schedule
Baseline |  | Contract | Contingency | Float | Weather | Reputation | Comments | Fee
|  | 131000000 | 3255164.328 | 14 | 0 | 25 |  | 1218457.71
Lean Planning |  |  |  | 0 |  | 0 |  | -313598
Interior Rough In | [7 empty] | 904859.71
IR#1 | Chris |  | -10000 | 0 |  | 0
IR#2 | Kaitlin |  | -12500 | 0 |  | -2 | didn’t even try to debate
IR#3 | Todd |  | 0 | 0 |  | 1
IR#4 | Brittany |  | 0 | 0 |  | 0
IR#5 | Brianne |  | 0 | -2 |  | -1
IR#6 | Dan |  | 0 | 0 |  | 1
Bonus
IR Status |  | 131000000 | 3232664.328 | 12 | 0 | 24
Team Status |  | 131000000
Delta |  | 0 | 3232664.328 | 12 |  | -
Finishes
FN#1 | Chris |  | 0 | 0 |  | -1
FN#2 | Brittany |  | -7000 | 0 |  | 2
FN#3 | Dan |  | -30000 | -3 |  | -1
FN#4 | Kaitlin |  | 0 | 0 |  | -2
FN#5 | Brianne |  | -80000 | -1 |  | 2
FN#6 | Brittany |  | -6343 | 0 |  | 2
FN#7 | Dan | 45000 | 0 | -3 |  | -1
FN#8 | Kaitlin |  | 0 | 0 |  | -1 |  | -17500
FN#9 | Brianne | [6 empty] | -133598
Bonus
FN Status |  | 131045000 | 3109321.328 | 5 | 0 | 24
Team Status
Delta |  | 131045000 | 3109321.328 | 5 |  | 24
Equipment & Commissioning
EC#1 | Dan |  | 112500 | 0 |  | 1 |  | -112500
EC#2 | Chris |  | -200000 | 0 |  | 0
EC#3 | Brittany |  | -8632 | 0 |  | 1
EC#4 | Todd |  | -50000 | 0 |  | 1
EC#5 | Dan |  | -50000 | 0 |  | 0
EC#6 | Kaitlin |  | -45000 | 0 |  | 1
EC#7 | Brianne |  | -25000 | 0 |  | 0
EC#8 | Brittany |  | -42666 | 0 |  | 3
EC#10 | Kaitlin |  | 0 | 0 |  | -2 |  | -50000
E&C Status |  | 131045000 | 2800523.328 | 5 | 0 | 29
Team Status
Delta |  | 131045000 | 2800523.328 | 5 |  | -
Closeout
CO#1 | Chris |  | -51000 | 0 |  | -1
CO#2 | Dan |  | -9500 | 0 |  | 0
CO#3 | Brianne |  | -8000 | 0 |  | -1
CO#4 | Brittany |  | -2500 | 0 |  | 0
CO#5 | Chris
CO#6 | Todd |  | -10000 | 0 |  | 1
Bonus
CO Status |  | 131045000 | 2719523.328 | 5 | 0 | 28
Team Status |  |  |  | 0 | 0
Delta |  | 131045000 | 2719523.328 | 5 |  | -

## Washington (hidden)
U of W Huskies
Schedule
Baseline |  | Contract | Contingency | Float | Weather | Reputation | Comments | Fee
|  | 131000000 | 1423859.7051 | 14 | 0 | 25 |  | 2448678.3166
Lean Planning |  |  |  | 0 |  | 1 |  | -161098
Interior Rough In | [7 empty] | 2287580.3166
IR#1 | Chris |  | -20000 | 0 |  | -1
IR#2 | Kaitlin |  | -12500 | 0 |  | -1
IR#3 | Todd |  | 0 | 0 |  | 1
IR#4 | Brittany |  | -24582 | -2 |  | -1
IR#5 | Brianne |  | -25000 | -2 |  | 0
IR#6 | Dan |  | 0 | 0 |  | 1
Bonus
IR Status |  | 131000000 | 1341777.7051 | 10 | 0 | 25
Team Status |  | 131000000
Delta |  | 0 | 1341777.7051 | 10 |  | -
Finishes
FN#1 | Chris |  | 0 | 0 |  | -3
FN#2 | Brittany |  | -27000 | -1 |  | 0
FN#3 | Dan | 12500 | -12500 | -3 |  | -1
FN#4 | Kaitlin |  | 0 | 0 |  | 3
FN#5 | Brianne |  | -20000 | -1 |  | -1
FN#6 | Brittany |  | -12687 | 0 |  | 0 | Claiming Fee
FN#7 | Dan | 45000 | 0 | -3 |  | -2
FN#8 | Kaitlin |  | 0 | 0 |  | -1 |  | -17500
FN#9 | Brianne | [5 empty] | 133,598 Loss in Fee | -133598
Bonus
FN Status |  | 131057500 | 1269590.7051 | 2 | 0 | 20
Team Status
Delta |  | 131057500 | 1269590.7051 | 2 |  | 20
Equipment & Commissioning
EC#1 | Dan |  | -225000 | 0 |  | 0
EC#2 | Chris |  | -200000 | 0 |  | 0
EC#3 | Brittany |  | -27712 | 0 |  | 1
EC#4 | Todd |  | -50000 | 0 |  | 1
EC#5 | Dan |  | -50000 | 0 |  | 0
EC#6 | Kaitlin |  | -45000 | 0 |  | -1
EC#7 | Brianne |  | -25000 | 0 |  | 0
EC#8 | Brittany |  | 85333 | 0 |  | 2
EC#10 | Kaitlin |  | 0 | 0 |  | 1 |  | -10000
E&C Status |  | 131057500 | 732211.7051 | 2 | 0 | 24
Team Status
Delta |  | 131057500 | 732211.7051 | 2 |  | -
Closeout
CO#1 | Chris |  | -40000 | 0 |  | -1
CO#2 | Dan |  | -10000 | 0 |  | 0
CO#3 | Brianne |  | -8000 | 0 |  | 0
CO#4 | Brittany |  | -2500 | 0 |  | 0
CO#5 | Chris
CO#6 | Todd |  | -10000 | 0 |  | 1
Bonus
CO Status |  | 131057500 | 661711.7051 | 2 | 0 | 24
Team Status |  |  |  | 0 | 0
Delta |  | 131057500 | 661711.7051 | 2 |  | -

## UVU (hidden)
UVU Wolveries
Schedule
Baseline |  | Contract | Contingency | Float | Weather | Reputation | Comments | Fee
|  | 131000000 | 1287063.8611 | 20 | 0 | 25 |  | 2451303.9566
Lean Planning |  |  |  | 0 |  | 1 |  | -217000
Interior Rough In | [7 empty] | 2234303.9566
IR#1 | Chris |  | -11000 | 0 |  | 0
IR#2 | Kaitlin |  | -25000 | 0 |  | 1
IR#3 | Todd |  | -12500 | -1 |  | 0
IR#4 | Brittany |  | 0 | 0 |  | 0
IR#5 | Brianne |  | 0 | -2 |  | 0
IR#6 | Dan |  | 0 | 0 |  | -1
Bonus
IR Status |  | 131000000 | 1238563.8611 | 17 | 0 | 26
Team Status |  | 131000000
Delta |  | 0 | 1238563.8611 | 17 |  | -
Finishes
FN#1 | Chris |  | 0 | 0 |  | -1
FN#2 | Brittany |  | -5000 | 0 |  | 0
FN#3 | Dan |  | -30000 | -3 |  | -1
FN#4 | Kaitlin |  | 0 | 0 |  | 2
FN#5 | Brianne |  | -80000 | -2 |  | 0
FN#6 | Brittany |  | -6343 | 0 |  | 1
FN#7 | Dan | 45000 | 0 | 0 |  | 1
FN#8 | Kaitlin |  | 0 | 0 |  | -2 |  | -35000
FN#9 | Brianne | [6 empty] | -132000
Bonus
FN Status |  | 131045000 | 1117220.8611 | 12 | 0 | 26
Team Status
Delta |  | 131045000 | 1117220.8611 | 12 |  | 26
Equipment & Commissioning
EC#1 | Dan |  | -225000 | 0 |  | 1
EC#2 | Chris |  | -200000 | 0 |  | 0
EC#3 | Brittany |  | -27712 | 0 |  | 1
EC#4 | Todd |  | -16000 | -2 |  | 2
EC#5 | Dan |  | -50000 | 0 |  | 0
EC#6 | Kaitlin |  | -22500 | 0 |  | 0
EC#7 | Brianne |  | -12500 | 0 |  | 0
EC#8 | Brittany |  | -70000 | 0 |  | 3
EC#10 | Kaitlin |  | 0 | 0 |  | -2 |  | -50000
E&C Status |  | 131045000 | 493508.8611 | 10 | 0 | 31
Team Status
Delta |  | 131045000 | 493508.8611 | 10 |  | -
Closeout
CO#1 | Chris |  | -35500 | 0 |  | 1
CO#2 | Dan |  | -10000 | 0 |  | 0
CO#3 | Brianne |  | -8000 | 0 |  | 0
CO#4 | Brittany |  | -2500 | 0 |  | 0
CO#5 | Chris
CO#6 | Todd |  | 0 | 0 |  | 3
Bonus
CO Status |  | 131045000 | 437508.8611 | 10 | 0 | 35
Team Status |  |  |  | 0 | 0
Delta |  | 131045000 | 437508.8611 | 10 |  | -

## SOV
SCHEDULE OF VALUES
PROJECT: | SoundWave Studios | ESTIMATE NO: | 1
DATE:
|  | ESTIMATOR: | Your School
DURATION:
SPEC | TRADE | SUB/SELF-PERFORM | TOTAL | COMMENTS
1 | DEMOLITION
| Rough Carpentry |  | 1191295
| Millwork |  | 615980
| Miscellaneous Metals |  |  | Must include comments for why this subcontractor was selected
| Glazing |  | 202335
| Sheet Metal/Flashing |  | 129318
| Roofing & Waterproofing |  | 181486
| Casework |  | 615980
| Doors, Frames & Hardware |  |  | Must include comments for why this subcontractor was selected
Drywall
| Epoxy Flooring |  | 10875
| Ceramic Tile |  |  | Must include comments for why this subcontractor was selected
| Carpeting |  | 688715
| Interior Painting |  | 310001
| Acoustical Ceiling Tile |  | 340675
| Toilet Partitions & Accessories |  | 52775
| Window Treatments |  | 314522
| Demountable Partitions |  | 883950
| Low Voltage |  |  | Must include comments for why this subcontractor was selected
| Fire Protection |  |  | Must include comments for why this subcontractor was selected
| HVAC & Plumbing |  | 5674247
| Electrical |  |  | Must include comments for why this subcontractor was selected
14 | GENERAL CONDITIONS
| Jobsite Management & Site Requirements |  |  | SHOULD ALIGN WITH THE TOTAL IN YOUR GC MODULE
| SUBTOTAL |  | 11212154 | (Auto Calcs)
| Contractors Insurance & Bonds | <SET YOUR INSURANCE RATE> | #VALUE! | (Auto Calcs)
| Fee | <SET YOUR FEE%> | #REF! | (Auto Calcs)
| Construction Contingency | <SET YOUR CONTINGENCY %> | #REF! | (Auto Calcs)
| Design Contingency | <SET YOUR CONTINGENCY %> | #VALUE! | (Auto Calcs)
| TOTAL PROJECT COST |  | 0
0

## TEAM SOV (hidden)
SCHEDULE OF VALUES
PROJECT: | Sutter Medical Center |  | DPR JOB NO: | 020912-Y4
LOCATION: | Castro Valley San Francisco |  | ESTIMATE NO: | Target Cost
CLIENT: | Sutter Medical Group |  | DATE: | 02/09/12
ARCHITECT: | Devenney Group |  | ESTIMATOR: |  |  | <-- Enter Team Name
AREA SUMMARY:
| CONSTRUCTION AREA | 230000 | sf | BUILDING TYPE | Hospital
|  |  |  | DURATION | 24 | mo
SYSTEMS | DESCRIPTION | POINT OF CONTACT | SUBCONTRACTOR NAME | TOTAL | 569.5652 | Comments
NUMBER
8 | INTERIOR CONSTRUCTION
| Metal Studs, Drywall, Taping & Insulation | Nick |  |  | 0
| Casework | Brieann | were the best | 776590 | 3.3765
| Doors, Frames & Hardware | Dan |  |  | 0
| Carpeting, Rubber & Tile Flooring | Chris |  |  | 0
| Acoustical Ceiling | Brieann |  |  | 0
| Painting & Caulking | Todd |  |  | 0
| Toilet Accessories, Fire Extinguishers & Window Treatments | Todd |  |  | 0
| Fire Caulking | Brittany |  |  | 0
| Rough Carpentry | Nick |  |  | 0
| Wall/Column Coverings - Corner Guards & Bumpers | Nick |  |  | 0
| Interior Signage | Todd |  |  | 0
| Lockers | Brittany |  |  | 0
9 | CONVEYING
| Elevators | Dan |  |  | 0
10 | SPECIAL CONSTRUCTION
| Lab Equipment | Chris |  |  | 0
| P-Tube | Nick |  |  | 0
| Radiation Shielding | Brittany |  |  | 0
| Food Serivce | Dan |  |  | 0
12 | FIRE PROTECTION
| Fire Sprinklers | Brieann |  |  | 0
13 | MECHANICAL
| HVAC | Kaitlin |  |  | 0
| Piping | Kaitlin |  |  | 0
| Controls | Kaitlin |  |  | 0
14 | ELECTRICAL
| Electrical | Chris |  |  | 0
| Fire Alarm | Dan |  |  | 0
| Data | Nick |  |  | 0
GENERAL CONDITIONS
| Jobsite Management & Site Requirements | DPR Construction |  |  | 0
| SUBTOTAL |  |  | 776590 | 3.3765
| Contractors Insurance & Bonds | 2.2% |  | 17084.98 | 0.074283
| Fee | 2.5% | <-- Enter Fee % in Cell | 19414.75 | 0.084412
| Design & Construction Contingency | 99.37% |  | 128186910.27 | 557.3344
| PROJECTED CONSTRUCTION COSTS |  |  | 129000000 | 560.8696
| DESIGN COST |  |  | 1000000
| Meeting Target Proect Costs |  |  | 1000000
| TOTAL PROJECT COST |  |  | 131000000

## ASU SOV (hidden)
SCHEDULE OF VALUES
PROJECT: | Sutter Medical Center |  | DPR JOB NO: | 020912-Y4
LOCATION: | Castro Valley San Francisco |  | ESTIMATE NO: | Target Cost
CLIENT: | Sutter Medical Group |  | DATE: | 02/09/12
ARCHITECT: | Devenney Group |  | ESTIMATOR: |  |  | <-- Enter Team Name
AREA SUMMARY:
| CONSTRUCTION AREA | 230000 | sf | BUILDING TYPE | Lab
|  |  |  | DURATION | 24 | mo
SYSTEMS | DESCRIPTION | POINT OF CONTACT | SUBCONTRACTOR NAME | TOTAL | 569.5652 | Comments
NUMBER
8 | INTERIOR CONSTRUCTION
| Metal Studs, Drywall, Taping & Insulation | Nick | DPR | 13219332 | 57.4754
| Casework | Brieann | Cal Casework | 4994891 | 21.7169 | Lowest price
| Doors, Frames & Hardware | Dan | Platinum Puertes | 3620000 | 15.7391 | Door Protections, shop drawings
| Carpeting, Rubber & Tile Flooring | Chris | Carpeteria and Tileria | 4620995 | 20.0913 | Best Value
| Acoustical Ceiling | Brieann | T-Bar | 2042120 | 8.8788 | Acoustical Metal Pan
| Painting & Caulking | Todd | Stony Stainers | 409887 | 1.7821 | Submittals
| Toilet Accessories, Fire Extinguishers & Window Treatments | Todd | Tough Tim's Bathroom Inc | 650333 | 2.8275 | Field Verification
| Fire Caulking | Brittany | Squawking Caulking | 659061 | 2.8655 | Inclusions
| Rough Carpentry | Nick | Redwood Original Cuts | 506623 | 2.2027 | Value
| Wall/Column Coverings - Corner Guards & Bumpers | Nick | CH & G Protection | 450360 | 1.9581 | Value
| Interior Signage | Todd | World Specialties Direct | 54667 | 0.23768 | Clean-up, LEED
| Lockers | Brittany | Bare Down Contractors | 33000 | 0.14348 | Best Value
9 | CONVEYING
| Elevators | Dan | Easy Lifts | 2630000 | 11.4348 | Lowest price
10 | SPECIAL CONSTRUCTION
| Lab Equipment | Chris | Lab Geek Equipment | 387995 | 1.6869 | Lowest Price
| P-Tube | Nick | Quick Shot System | 725664 | 3.1551 | Warranty
| Radiation Shielding | Brittany | Knight | 254211 | 1.1053 | Inclusions
| Food Serivce | Dan | West Coast Restaurant Supply | 54112 | 0.23527 | Lowest price
12 | FIRE PROTECTION
| Fire Sprinklers | Brieann | West Coast Fire Protection | 2079200 | 9.04 | Temporary Protection
13 | MECHANICAL
| HVAC | Kaitlin | Fitter and Sheet Mechanical | 12877990 | 55.9913 | Lowest EMR
| Piping | Kaitlin | Pergo Engineered Systems | 25234561 | 109.7155 | Inclusions
| Controls | Kaitlin | ModBus Controls | 8164197 | 35.4965 | Lowest Price, Inclusions
14 | ELECTRICAL
| Electrical | Chris | Tiered Electric | 23439799 | 101.9122 | Lowest Price
| Fire Alarm | Dan | Blazer Electrical | 5450000 | 23.6957 | Testing
| Data | Nick | White Panda Communication | 10451223 | 45.4401 | Low Voltage Inclusions
GENERAL CONDITIONS
| Jobsite Management & Site Requirements | DPR Construction |  |  | 0
| SUBTOTAL |  |  | 123010221 | 534.827
| Contractors Insurance & Bonds | 2.2% |  | 2706224.862 | 11.7662
| Fee | 1.5% |  | 1845153.315 | 8.0224
| Design & Construction Contingency | 1.115% |  | 1438400.823 | 6.2539
| PROJECTED CONSTRUCTION COSTS |  |  | 129000000 | 560.8696
| DESIGN COST |  |  | 1000000
| Meeting Target Proect Costs |  |  | 1000000
| TOTAL PROJECT COST |  |  | 131000000

## Boise_SOV (hidden)
SCHEDULE OF VALUES
PROJECT: | Sutter Medical Center |  | DPR JOB NO: | 020912-Y4
LOCATION: | Castro Valley San Francisco |  | ESTIMATE NO: | Target Cost
CLIENT: | Sutter Medical Group |  | DATE: | 02/09/12
ARCHITECT: | Devenney Group |  | ESTIMATOR: |  |  | <-- Enter Team Name
AREA SUMMARY:
| CONSTRUCTION AREA | 230000 | sf | BUILDING TYPE | Lab
|  |  |  | DURATION | 24 | mo
SYSTEMS | DESCRIPTION | POINT OF CONTACT | SUBCONTRACTOR NAME | TOTAL | 569.5652 | Comments
NUMBER
8 | INTERIOR CONSTRUCTION
| Metal Studs, Drywall, Taping & Insulation | Nick | DPR Self Perform | 13219332 | 57.4754
| Casework | Brieann | Cal Casework | 4994891 | 21.7169
| Doors, Frames & Hardware | Dan | Open Wide | 3575000 | 15.5435
| Carpeting, Rubber & Tile Flooring | Chris | Carpeteria and Tileria | 4620995 | 20.0913
| Acoustical Ceiling | Brieann | Orville Redenbacher Ceilings | 1984231 | 8.6271
| Painting & Caulking | Todd | Stony Stainers | 409887 | 1.7821
| Toilet Accessories, Fire Extinguishers & Window Treatments | Todd | Omega Bathrooms | 642406 | 2.7931
| Fire Caulking | Brittany | Squawking Caulking | 659061 | 2.8655
| Rough Carpentry | Nick | Redwood Original Cuts | 506623 | 2.2027
| Wall/Column Coverings - Corner Guards & Bumpers | Nick | CH & G Protection | 450360 | 1.9581
| Interior Signage | Todd | Magic Signs | 52000 | 0.22609
| Lockers | Brittany | Bear Down Contractors | 33000 | 0.14348
9 | CONVEYING
| Elevators | Dan | Easy Lifts | 2630000 | 11.4348
10 | SPECIAL CONSTRUCTION
| Lab Equipment | Chris | Shiny Equipment Inc. | 507907 | 2.2083
| P-Tube | Nick | Quick Shot System | 725664 | 3.1551
| Radiation Shielding | Brittany | Knight | 254221 | 1.1053
| Food Serivce | Dan | West Coast Restaurant Supply | 54112 | 0.23527
12 | FIRE PROTECTION
| Fire Sprinklers | Brieann | Arrowhead Fire Protection | 1564000 | 6.8
13 | MECHANICAL
| HVAC | Kaitlin | Fitter and Sheet Mechanical | 12877990 | 55.9913
| Piping | Kaitlin | Prime That Trap Plumbing | 24925641 | 108.3724
| Controls | Kaitlin | Modbus Controls | 8164197 | 35.4965
14 | ELECTRICAL
| Electrical | Chris | High Voltage Electric | 23515600 | 102.2417
| Fire Alarm | Dan | Blazer Electric Inc. | 5450000 | 23.6957
| Data | Nick | Pretty Lights Fiver Mash Up Co. | 10356787 | 45.0295
GENERAL CONDITIONS
| Jobsite Management & Site Requirements | DPR Construction |  |  | 0
| SUBTOTAL |  |  | 122173905 | 531.1909
| Contractors Insurance & Bonds | 2.2% |  | 2687825.91 | 11.6862
| Fee | 2% |  | 2443478.1 | 10.6238 | <-- Enter Fee % in Cell
| Design & Construction Contingency | 1.314% |  | 1694790.99 | 7.3687
| PROJECTED CONSTRUCTION COSTS |  |  | 129000000 | 560.8696
| DESIGN COST |  |  | 1000000
| Meeting Target Proect Costs |  |  | 1000000
| TOTAL PROJECT COST |  |  | 131000000

## BYU_SOV (hidden)
SCHEDULE OF VALUES
PROJECT: | Sutter Medical Center |  | DPR JOB NO: | 020912-Y4
LOCATION: | Castro Valley San Francisco |  | ESTIMATE NO: | Target Cost
CLIENT: | Sutter Medical Group |  | DATE: | 02/09/12
ARCHITECT: | Devenney Group |  | ESTIMATOR: |  |  | <-- Enter Team Name
AREA SUMMARY:
| CONSTRUCTION AREA | 230000 | sf | BUILDING TYPE | Lab
|  |  |  | DURATION | 24 | mo
SYSTEMS | DESCRIPTION | POINT OF CONTACT | SUBCONTRACTOR NAME | TOTAL | 569.5652 | Comments
NUMBER
8 | INTERIOR CONSTRUCTION
| Metal Studs, Drywall, Taping & Insulation | Nick | Self Preformed | 13219332 | 57.4754
| Casework | Brieann | NorCon Builders | 5740621.83 | 24.9592
| Doors, Frames & Hardware | Dan | Open Wide | 3575000 | 15.5435
| Carpeting, Rubber & Tile Flooring | Chris | Carpeteria and Tileria | 4620995 | 20.0913
| Acoustical Ceiling | Brieann | T-Bar | 2042120 | 8.8788
| Painting & Caulking | Todd | Stony Stainers | 409887 | 1.7821
| Toilet Accessories, Fire Extinguishers & Window Treatments | Todd | E-Z Does It Construction | 634578 | 2.759
| Fire Caulking | Brittany | Squawking Caulking | 659061 | 2.8655
| Rough Carpentry | Nick | Redwood Original Cuts | 506623 | 2.2027
| Wall/Column Coverings - Corner Guards & Bumpers | Nick | CH & G Protection | 450360 | 1.9581
| Interior Signage | Todd | World Specialties Direct, Inc. | 54667 | 0.23768
| Lockers | Brittany | Bear Down Contractors | 33000 | 0.14348
9 | CONVEYING
| Elevators | Dan | Raiser Technologies | 2660000 | 11.5652
10 | SPECIAL CONSTRUCTION
| Lab Equipment | Chris | Lab Geek Equipment | 387995 | 1.6869
| P-Tube | Nick | Quick Shot System | 725664 | 3.1551
| Radiation Shielding | Brittany | A. Taylor Building Solutions | 248191 | 1.0791
| Food Serivce | Dan | West Coast Restaurant Supply | 54112 | 0.23527
12 | FIRE PROTECTION
| Fire Sprinklers | Brieann | Arrowhead Fire Protection | 1564000 | 6.8
13 | MECHANICAL
| HVAC | Kaitlin | Fremont HVAC | 12664806 | 55.0644
| Piping | Kaitlin | Prime That Trap Plumbing | 24925641 | 108.3724
| Controls | Kaitlin | ModBus Controls | 8164197 | 35.4965
14 | ELECTRICAL
| Electrical | Chris | Tiered Electric | 23439799 | 101.9122
| Fire Alarm | Dan | Blazer Electric, Inc. | 5450000 | 23.6957
| Data | Nick | Pretty Lights Fiber Mash Up Co. | 10356787 | 45.0295
GENERAL CONDITIONS
| Jobsite Management & Site Requirements | DPR Construction |  |  | 0
| SUBTOTAL |  |  | 122587436.83 | 532.9889
| Contractors Insurance & Bonds | 2.2% |  | 2696923.6103 | 11.7258
| Fee | 1.5% |  | 1838811.5524 | 7.9948 | <-- Enter Fee % in Cell
| Design & Construction Contingency | 1.455% |  | 1876828.0073 | 8.1601
| PROJECTED CONSTRUCTION COSTS |  |  | 129000000 | 560.8696
| DESIGN COST |  |  | 1000000
| Meeting Target Proect Costs |  |  | 1000000
| TOTAL PROJECT COST |  |  | 131000000

## Cal Poly SOV (hidden)
SCHEDULE OF VALUES
PROJECT: | Sutter Medical Center |  | DPR JOB NO: | 020912-Y4
LOCATION: | Castro Valley San Francisco |  | ESTIMATE NO: | Target Cost
CLIENT: | Sutter Medical Group |  | DATE: | 02/09/12
ARCHITECT: | Devenney Group |  | ESTIMATOR: |  |  | <-- Enter Team Name
AREA SUMMARY:
| CONSTRUCTION AREA | 230000 | sf | BUILDING TYPE | Lab
|  |  |  | DURATION | 24 | mo
SYSTEMS | DESCRIPTION | POINT OF CONTACT | SUBCONTRACTOR NAME | TOTAL | 569.5652 | Comments
NUMBER
8 | INTERIOR CONSTRUCTION
| Metal Studs, Drywall, Taping & Insulation | Nick | DPR Self Perform | 13219332 | 57.4754
| Casework | Brieann | Billy's Base and More | 5374621.83 | 23.3679
| Doors, Frames & Hardware | Dan | Platinum PUERTAS | 3620000 | 15.7391
| Carpeting, Rubber & Tile Flooring | Chris | Capeteria and Tileria | 4620995 | 20.0913
| Acoustical Ceiling | Brieann | ABCeilings | 1956410 | 8.5061
| Painting & Caulking | Todd | Splish Splash | 404000 | 1.7565
| Toilet Accessories, Fire Extinguishers & Window Treatments | Todd | Omega Bathrooms | 642406 | 2.7931
| Fire Caulking | Brittany | Squaking Caulking | 659061 | 2.8655
| Rough Carpentry | Nick | Janet Island | 500212 | 2.1748
| Wall/Column Coverings - Corner Guards & Bumpers | Nick | Soaring Eagle | 447885 | 1.9473
| Interior Signage | Todd | Magic Signs | 52000 | 0.22609
| Lockers | Brittany | Hammertime | 40888 | 0.17777
9 | CONVEYING
| Elevators | Dan | Raiser Technologies | 2660000 | 11.5652
10 | SPECIAL CONSTRUCTION
| Lab Equipment | Chris | Shiny Equipment | 507907 | 2.2083
| P-Tube | Nick | Quick Shot Systems | 725664 | 3.1551
| Radiation Shielding | Brittany | Knight | 254221 | 1.1053
| Food Serivce | Dan | Sporkers | 56447 | 0.24542
12 | FIRE PROTECTION
| Fire Sprinklers | Brieann | Arrowhead Fire Protection | 1564000 | 6.8
13 | MECHANICAL
| HVAC | Kaitlin | Fitter and Sheet Mechanical | 12877990 | 55.9913
| Piping | Kaitlin | Pergo Engineered Systems | 25234561 | 109.7155
| Controls | Kaitlin | Snowden Technologies | 8333456 | 36.2324
14 | ELECTRICAL
| Electrical | Chris | High Voltage Electric | 23515600 | 102.2417
| Fire Alarm | Dan | Blazer Electric | 5450000 | 23.6957
| Data | Nick | Pretty Lights Fiber Mash Up | 10356787 | 45.0295
GENERAL CONDITIONS
| Jobsite Management & Site Requirements | DPR Construction |  |  | 0
| SUBTOTAL |  |  | 123074443.83 | 535.1063
| Contractors Insurance & Bonds | 2.2% |  | 2707637.7643 | 11.7723
| Fee | 1.2% |  | 1476893.326 | 6.4213 | <-- Enter Fee % in Cell
| Design & Construction Contingency | 1.35% |  | 1741025.0798 | 7.5697
| PROJECTED CONSTRUCTION COSTS |  |  | 129000000 | 560.8696
| DESIGN COST |  |  | 1000000
| Meeting Target Proect Costs |  |  | 1000000
| TOTAL PROJECT COST |  |  | 131000000

## Sac State SOV (hidden)
SCHEDULE OF VALUES
PROJECT: | Sutter Medical Center |  | DPR JOB NO: | 020912-Y4
LOCATION: | Castro Valley San Francisco |  | ESTIMATE NO: | Target Cost
CLIENT: | Sutter Medical Group |  | DATE: | 02/09/12
ARCHITECT: | Devenney Group |  | ESTIMATOR: |  |  | <-- Enter Team Name
AREA SUMMARY:
| CONSTRUCTION AREA | 230000 | sf | BUILDING TYPE | Lab
|  |  |  | DURATION | 24 | mo
SYSTEMS | DESCRIPTION | POINT OF CONTACT | SUBCONTRACTOR NAME | TOTAL | 569.5652 | Comments
NUMBER
8 | INTERIOR CONSTRUCTION
| Metal Studs, Drywall, Taping & Insulation | Nick | DPR | 13219332 | 57.4754
| Casework | Brieann | Bill's Base and More | 5374622 | 23.3679
| Doors, Frames & Hardware | Dan | Open Wide | 3575000 | 15.5435
| Carpeting, Rubber & Tile Flooring | Chris | Slippery Slope Tile | 4860250 | 21.1315
| Acoustical Ceiling | Brieann | AB Ceilings | 1956410 | 8.5061
| Painting & Caulking | Todd | Slick Nick | 400212 | 1.7401
| Toilet Accessories, Fire Extinguishers & Window Treatments | Todd | Omega Bathrooms | 642406 | 2.7931
| Fire Caulking | Brittany | Squawking Caulking | 659061 | 2.8655
| Rough Carpentry | Nick | Redwood Original Cuts | 506623 | 2.2027
| Wall/Column Coverings - Corner Guards & Bumpers | Nick | CH&G Protection | 450360 | 1.9581
| Interior Signage | Todd | Wolrd Specialties Direct | 54667 | 0.23768
| Lockers | Brittany | Hammer Time contractos | 40888 | 0.17777
9 | CONVEYING
| Elevators | Dan | Raiser tech | 2660000 | 11.5652
10 | SPECIAL CONSTRUCTION
| Lab Equipment | Chris | Shiny Equipment nc | 507907 | 2.2083
| P-Tube | Nick | Quick shot Systems | 725664 | 3.1551
| Radiation Shielding | Brittany | Pepper Tech | 239551 | 1.0415
| Food Serivce | Dan | Sporkers | 56447 | 0.24542
12 | FIRE PROTECTION
| Fire Sprinklers | Brieann | West Coast Fire Protection | 2079200 | 9.04
13 | MECHANICAL
| HVAC | Kaitlin | Fitter and Sheet Mechanical | 12877990 | 55.9913
| Piping | Kaitlin | Pergo Engineered Systems | 25234561 | 109.7155
| Controls | Kaitlin | Belimo Plus | 8254123 | 35.8875
14 | ELECTRICAL
| Electrical | Chris | Tiered Electrical | 23439799 | 101.9122
| Fire Alarm | Dan | Blazer Electric Inc | 5450000 | 23.6957
| Data | Nick | Pretty Lights Fiber | 10356787 | 45.0295
GENERAL CONDITIONS
| Jobsite Management & Site Requirements | DPR Construction |  |  | 0
| SUBTOTAL |  |  | 123621860 | 537.4863
| Contractors Insurance & Bonds | 2.2% |  | 2719680.92 | 11.8247
| Fee | 1.34% |  | 1656532.924 | 7.2023 | <-- Enter Fee % in Cell
| Design & Construction Contingency | 0.7767% |  | 1001926.156 | 4.3562
| PROJECTED CONSTRUCTION COSTS |  |  | 129000000 | 560.8696
| DESIGN COST |  |  | 1000000
| Meeting Target Proect Costs |  |  | 1000000
| TOTAL PROJECT COST |  |  | 131000000
01-29000-00

## Oregon SOV (hidden)
SCHEDULE OF VALUES
PROJECT: | Sutter Medical Center |  | DPR JOB NO: | 020912-Y4
LOCATION: | Castro Valley San Francisco |  | ESTIMATE NO: | Target Cost
CLIENT: | Sutter Medical Group |  | DATE: | 02/09/12
ARCHITECT: | Devenney Group |  | ESTIMATOR: |  |  | <-- Enter Team Name
AREA SUMMARY:
| CONSTRUCTION AREA | 230000 | sf | BUILDING TYPE | Lab
|  |  |  | DURATION | 24 | mo
SYSTEMS | DESCRIPTION | POINT OF CONTACT | SUBCONTRACTOR NAME | TOTAL | 569.5652 | Comments
NUMBER
8 | INTERIOR CONSTRUCTION
| Metal Studs, Drywall, Taping & Insulation | Nick | DPR | 13219332 | 57.4754
| Casework | Brieann | NorCon Builders | 5074621 | 22.0636
| Doors, Frames & Hardware | Dan | Platinum PUERTAS | 3620000 | 15.7391
| Carpeting, Rubber & Tile Flooring | Chris | Carpeteria | 4620995 | 20.0913
| Acoustical Ceiling | Brieann | T-Bar | 2042120 | 8.8788
| Painting & Caulking | Todd | Stony Stainers | 409887 | 1.7821
| Toilet Accessories, Fire Extinguishers & Window Treatments | Todd | Omega Bathrooms | 642406 | 2.7931
| Fire Caulking | Brittany | Spuawking Caulking | 659061 | 2.8655
| Rough Carpentry | Nick | Redwood Original | 506623 | 2.2027
| Wall/Column Coverings - Corner Guards & Bumpers | Nick | DAWG | 452661 | 1.9681
| Interior Signage | Todd | Magic! Signs | 52000 | 0.22609
| Lockers | Brittany | Hammetime Contractors | 40888 | 0.17777
9 | CONVEYING
| Elevators | Dan | Easy Lift, Inc. | 2360000 | 10.2609
10 | SPECIAL CONSTRUCTION
| Lab Equipment | Chris | Lab Greek Equipment | 387995 | 1.6869
| P-Tube | Nick | Quick Shot | 725664 | 3.1551
| Radiation Shielding | Brittany | A. Taylor | 248191 | 1.0791
| Food Serivce | Dan | West Coast | 54112 | 0.23527
12 | FIRE PROTECTION
| Fire Sprinklers | Brieann | Arrowhead Fire Protection | 1564000 | 6.8
13 | MECHANICAL
| HVAC | Kaitlin | Fitter and Sheet Mech | 12877990 | 55.9913
| Piping | Kaitlin | Prime | 24925641 | 108.3724
| Controls | Kaitlin | MODBUS | 8164197 | 35.4965
14 | ELECTRICAL
| Electrical | Chris | High Voltage Electric | 23515600 | 102.2417
| Fire Alarm | Dan | Sysertech | 5325000 | 23.1522
| Data | Nick | Pretty Lights | 10356787 | 45.0295
GENERAL CONDITIONS
| Jobsite Management & Site Requirements | DPR Construction |  |  | 0
| SUBTOTAL |  |  | 121845771 | 529.7642
| Contractors Insurance & Bonds | 2.2% |  | 2680606.962 | 11.6548
| Fee | 1% |  | 1218457.71 | 5.2976 | <-- Enter Fee % in Cell
| Design & Construction Contingency | 2.523% |  | 3255164.328 | 14.1529
| PROJECTED CONSTRUCTION COSTS |  |  | 129000000 | 560.8696
| DESIGN COST |  |  | 1000000
| Meeting Target Proect Costs |  |  | 1000000
| TOTAL PROJECT COST |  |  | 131000000

## Washington SOV (hidden)
SCHEDULE OF VALUES
PROJECT: | Sutter Medical Center |  | DPR JOB NO: | 020912-Y4
LOCATION: | Castro Valley San Francisco |  | ESTIMATE NO: | Target Cost
CLIENT: | Sutter Medical Group |  | DATE: | 02/09/12
ARCHITECT: | Devenney Group |  | ESTIMATOR: |  |  | <-- Enter Team Name
AREA SUMMARY:
| CONSTRUCTION AREA | 230000 | sf | BUILDING TYPE | Lab
|  |  |  | DURATION | 24 | mo
SYSTEMS | DESCRIPTION | POINT OF CONTACT | SUBCONTRACTOR NAME | TOTAL | 569.5652 | Comments
NUMBER
8 | INTERIOR CONSTRUCTION
| Metal Studs, Drywall, Taping & Insulation | Nick | Self Performed | 13219332 | 57.4754
| Casework | Brieann | NorCon Builders | 5074621.83 | 22.0636 | LEED Documentation done in house saving $300,000.
| Doors, Frames & Hardware | Dan | Platinum Puertas | 3620000 | 15.7391 | Superior abilities in 3D modeling and shop drawings. Coordination
| Carpeting, Rubber & Tile Flooring | Chris | Carpeteria and Tileria | 4620995 | 20.0913 | All Subs Spec the same work. They were low bid
| Acoustical Ceiling | Brieann | ABCeilings | 1956410 | 8.5061 | low bid. Off site storage. Same inclusions
| Painting & Caulking | Todd | Splish Splash | 404000 | 1.7565 | includes patching
| Toilet Accessories, Fire Extinguishers & Window Treatments | Todd | Bathrooms, LLC. | 642406 | 2.7931 | included window treatment
| Fire Caulking | Brittany | Hole Stuffers | 732290 | 3.1839 | low bid was unclear if it included vertical penetrations
| Rough Carpentry | Nick | Redwood Original Cuts | 506623 | 2.2027 | certified forestry stewardship agreement
| Wall/Column Coverings - Corner Guards & Bumpers | Nick | DAWG Deflections | 452661 | 1.9681 | included bumber base and wall covers
| Interior Signage | Todd | Magic Signs | 52000 | 0.22609 | field verification and shop drawings
| Lockers | Brittany | Bear Down Contractors | 33000 | 0.14348 | detailed and complete
9 | CONVEYING
| Elevators | Dan | Easy Lifts, Inc. | 2630000 | 11.4348 | low bid.
10 | SPECIAL CONSTRUCTION
| Lab Equipment | Chris | Shiny Equipment Inc. | 507907 | 2.2083 | low reasonable bid
| P-Tube | Nick | Quick Shot System | 725664 | 3.1551 | low bid with warranty
| Radiation Shielding | Brittany | Knight | 254221 | 1.1053 | quoted correct spec section. Included drawings and daily clean-up
| Food Serivce | Dan | West Coast Restaurant Supply | 54112 | 0.23527 | included keying of hardware locks, connection to Soda System and final hook-up. Low bid with taxes included. Furnish and Install exhaust hoods
12 | FIRE PROTECTION
| Fire Sprinklers | Brieann | Arrowhead Fire Protection | 1564000 | 6.8 | low bid
13 | MECHANICAL
| HVAC | Kaitlin | Fitter and Sheet Mechanical | 12877990 | 55.9913 | safety rating & painted support wires
| Piping | Kaitlin | Prime That Trap Plumbing | 24925641 | 108.3724 | low bid. Most clarified scope
| Controls | Kaitlin | Snowden Technologies | 8333456 | 36.2324 | safety rating
14 | ELECTRICAL
| Electrical | Chris | Tiered Electrical | 23439799 | 101.9122 | low bid
| Fire Alarm | Dan | Blazer Electric, Inc. | 5450000 | 23.6957 | comissioning and pretest
| Data | Nick | Pretty Lights Fiber Mash Up Co. | 10356787 | 45.0295 | detailed. Covered more work for less money.
GENERAL CONDITIONS
| Jobsite Management & Site Requirements | DPR Construction |  |  | 0
| SUBTOTAL |  |  | 122433915.83 | 532.3214
| Contractors Insurance & Bonds | 2.2% |  | 2693546.1483 | 11.7111
| Fee | 2% |  | 2448678.3166 | 10.6464 | <-- Enter Fee % in Cell
| Design & Construction Contingency | 1.104% |  | 1423859.7051 | 6.1907
| PROJECTED CONSTRUCTION COSTS |  |  | 129000000 | 560.8696
| DESIGN COST |  |  | 1000000
| Meeting Target Proect Costs |  |  | 1000000
| TOTAL PROJECT COST |  |  | 131000000

## UVU SOV (hidden)
SCHEDULE OF VALUES
PROJECT: | Sutter Medical Center |  | DPR JOB NO: | 020912-Y4
LOCATION: | Castro Valley San Francisco |  | ESTIMATE NO: | Target Cost
CLIENT: | Sutter Medical Group |  | DATE: | 02/09/12
ARCHITECT: | Devenney Group |  | ESTIMATOR: |  |  | <-- Enter Team Name
AREA SUMMARY:
| CONSTRUCTION AREA | 230000 | sf | BUILDING TYPE | Lab
|  |  |  | DURATION | 24 | mo
SYSTEMS | DESCRIPTION | POINT OF CONTACT | SUBCONTRACTOR NAME | TOTAL | 569.5652 | Comments
NUMBER
8 | INTERIOR CONSTRUCTION
| Metal Studs, Drywall, Taping & Insulation | Nick | DPR | 13219332 | 57.4754
| Casework | Brieann | Billy's Base and More | 5374621.83 | 23.3679
| Doors, Frames & Hardware | Dan | Platinum Puertas | 3620000 | 15.7391
| Carpeting, Rubber & Tile Flooring | Chris | Carpeteria and Tileria | 4620995 | 20.0913
| Acoustical Ceiling | Brieann | ABCeilings | 1956419 | 8.5062
| Painting & Caulking | Todd | Splish Splash | 404000 | 1.7565
| Toilet Accessories, Fire Extinguishers & Window Treatments | Todd | Omega | 642406 | 2.7931
| Fire Caulking | Brittany | Squawking Caulking | 659061 | 2.8655
| Rough Carpentry | Nick | Woodchuckers INC | 500212 | 2.1748
| Wall/Column Coverings - Corner Guards & Bumpers | Nick | CH & G Protection | 450360 | 1.9581
| Interior Signage | Todd | World Specialties Direct | 54667 | 0.23768
| Lockers | Brittany | Bear Down Contractors | 33000 | 0.14348
9 | CONVEYING
| Elevators | Dan | Raiser Techolgies | 2677200 | 11.64
10 | SPECIAL CONSTRUCTION
| Lab Equipment | Chris | Lab Geek Equipment | 387995 | 1.6869
| P-Tube | Nick | Quick Shot System | 725664 | 3.1551
| Radiation Shielding | Brittany | Knight | 254221 | 1.1053
| Food Serivce | Dan | Restaurant Supply | 54112 | 0.23527
12 | FIRE PROTECTION
| Fire Sprinklers | Brieann | West Coast Fire Protection | 2079200 | 9.04
13 | MECHANICAL
| HVAC | Kaitlin | Mason East Mechanical | 12261162 | 53.3094
| Piping | Kaitlin | Pergo Engineered Systems | 25234561 | 109.7155
| Controls | Kaitlin | ModBus Controls | 8164197 | 35.4965
14 | ELECTRICAL
| Electrical | Chris | High Voltage Electric | 23516600 | 102.2461
| Fire Alarm | Dan | Sysertech | 5325000 | 23.1522
| Data | Nick | MGMT Data | 10350212 | 45.0009
GENERAL CONDITIONS
| Jobsite Management & Site Requirements | DPR Construction |  |  | 0
| SUBTOTAL |  |  | 122565197.83 | 532.8922
| Contractors Insurance & Bonds | 2.2% |  | 2696434.3523 | 11.7236
| Fee | 2% |  | 2451303.9566 | 10.6578 | <-- Enter Fee % in Cell
| Design & Construction Contingency | 0.9977% |  | 1287063.8611 | 5.5959
| PROJECTED CONSTRUCTION COSTS |  |  | 129000000 | 560.8696
| DESIGN COST |  |  | 1000000
| Meeting Target Proect Costs |  |  | 1000000
| TOTAL PROJECT COST |  |  | 131000000

## Sheet1 (hidden)
08-9010 | Fireproofing - Labor | 80136 | 124133
08-9011 | Fireproofing - Material | 43997
08-9017 | Lanmor Services - Labor | 1315 | 2852
08-9018 | Lanmor Services - Material | 1537
08-9021 | Auto Operators (Smart Doors) - Labor | 2509 | 3356
08-9022 | Auto Operators (Smart Doors) - Material | 847
08-9030 | Glass & Glazing (Trainor Labor) | 112333 | 309495
08-9031 | Galss & Glazing (Trainor Material) | 197162
08-9034 | Doors - Labor | 83235 | 675943
08-9035 | Doors - Material | 592708
08-9036 | Accordion Fire Doors - Labor | 4737 | 82985
08-9037 | Accordion Fire Doors - Materials | 78248
08-9038 | Operable Partition - Labor | 9000 | 11900
08-9039 | Operable Partition - Material | 2900
08-9040 | ICU Doors and Door Operators - Labor | 35688 | 151276
08-9041 | ICU Doors and Door Operators - Material | 115588
08-9080 | Paint - Labor | 160838 | 214712
08-9081 | Paint - Material | 53874
08-9090 | Casework - Labor | 242616 | 438882
08-9091 | Casework - Material | 196266
08-9092 | Flooring - Labor | 353226 | 1310293
08-9093 | Flooring - Material | 957067
08-9094 | Terrazzo - Labor | 114738 | 178734
08-9095 | Terrazzo - Material | 63996
08-9096 | Acoustical Ceiling - Labor | 140019 | 350764
08-9097 | Acoustical Ceiling - Material | 210745
08-9098 | Epoxy - Labor | 32992 | 58190
08-9099 | Epoxy - Material | 25198
08-9100 | Fence Gate - Labor | 14120 | 52002
08-9101 | Fence Gate - Material | 37882
09-9000 | Hydraulic Elevator - Labor | 61094 | 147273
09-9001 | Hydraulic Elevator - Material | 86179
09-9002 | Pneumatic Tube System - Labor | 25712 | 100805
09-9003 | Pneumatic Tube System - Material | 75093
09-9004 | Auto Door Operator - Smart Doors | 7065
09-9005 | Elevator Service - Centric Labor | 20850
10-9000 | Toilet Accessories - Labor | 6650 | 23890
10-9001 | Toilet Accessories - Material | 17240
10-9004 | Wall Protection - Labor | 185549 | 500634
10-9005 | Wall Protection - Material | 315085
10-9006 | Window Treatment - Labor | 2674 | 14058
10-9007 | Window Treatment - Material | 11384
11-9000 | OR Supports - Labor | 218489 | 381700
11-9001 | OR Supports - Material | 163211
11-9005 | Patient Lifts | 38381
12-9000 | Fire Protection - Labor | 271792 | 494763
12-9001 | Fire Protection - Material | 222971
13-9000 | Mechanical - Labor | 4175187 | 10998585
13-9001 | Mechanical - Material | 6823398
13-9002 | Bel-Aire Labor | 190046 | 345413
13-9003 | Bel-Aire Material | 155367
13-9004 | Fuel Tank - Labor | 90048 | 222439
13-9005 | Fuel Tank - Material | 132391
13-9006 | Labor: Mechanical | 23105
13-9007 | Materials: Mechanical | 7748
14-9000 | Electrical - Labor | 2405318 | 5182226
14-9001 | Electrical - Material | 2776908
14-9002 | Special Systems Cabling - Labor | 216012 | 592351
14-9003 | Special Systems Cabling - Material | 376339
14-9004 | Security Integration - Labor | 107502 | 329288
14-9005 | Security Integration - Material | 221786
16-9040 | Temporary Scaffolding | 60643 | 119156
16-9041 | Scaffolding (Safway Material) | 58513
16-9042 | Scaffolding Harsco Labor | 55316
16-9043 | Scaffolding Harsco Materia | 32784