## EXAMPLE
BID ANALYSIS SHEET
|  | PROJECT: | GENE THEORY |  |  | 3 Coats Painters
|  | TRADE: | PAINT |  |  | 177962
BID PACKAGE:
|  | BID DATE: | 2017-12-01
|  | DESCRIPTION |  | 3 Coats Painters | Johnson Brothers Painting Co. | Prestine Painting Inc.
1) | SCOPE INCLUSIONS:
| 1.01 | Base Bid |  | 105362 | see below | 132200
| 1.01 | Paint Walls |  | included | 74445 | included
| 1.02 | Paint Gyp. Ceilings |  | included | 45362 | included
| 1.03 | Paint Gyp Soffits |  | included | 10709 | included
| 1.04 | Paint Hollow Metal Doors |  | 34600 | excluded | excluded
| 1.05 | Paint Hollow Metal Frames |  | 28000 | excluded | 37000
| 1.06 | Caulking |  | included | included | included
1.07
1.08
1.09
1.1
1.11
1.12
1.13
|  |  | TOTAL BASE BID: | 167962 | 130516 | 169200 | Should match subs initial base proposal amount
2) | COSTS TO COMPLETE (List Allowances DPR needs to carry to cover undefined scopes or risks, if any)
| 3.01 | 80 Hours of Touch-Up Paint |  | 10000 | 10000 | 10000
3.02
3.03
3.04
|  | Subtotal Cost to Complete: |  | 10000 | 10000 | 10000
COMPARISON TOTAL |  |  |  | 177962 | 140516 | 179200
3) | SCHEDULE
| 4.01 | Total Field Man Hours to Complete Work |  | 500 hours | 450 hours | 433 hours
| 4.02 | Average Crew Size |  | 4 | 5 | 6
4) | LABOR & EQUIPMENT RATES |  |  | RT / OT / DT | RT / OT / DT | RT / OT / DT
| 8.01 | General Foreman |  |  | 122.84
| 8.02 | Foreman |  | 84.97/117.04/149.11 | 110.92 | 71.25/96.16/121.17
| 8.03 | Journeyman |  | 80.39/110.19/139.99 | 98.17 | 67.45/90.59/133.88
| 8.04 | Apprentice |  |  | 92.43 | 55.78/73.77/91.85
5) | UNIT PRICES
9.01
9.02
9.03
RECOMMENDATION:
QUESTIONS / CLARIFICATIONS (List bid analysis notes, questions, responses, etc. below.)
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60

## MISCELLANEOUS METALS
BID ANALYSIS SHEET
|  | PROJECT: | GENE THEORY |  |  | Subcontractor #1 | Should List the Selected Subcontractor
|  | TRADE: | Miscellaneous Metals |  |  | 0
BID PACKAGE:
BID DATE:
|  | DESCRIPTION |  | Subcontractor #1 | Subcontractor #2 | Subcontractor #3
1) | SCOPE INCLUSIONS:
| 1.01 | Base Bid
1.01
1.02
1.03
1.04
1.05
1.06
1.07
1.08
1.09
1.1
1.11
1.12
1.13
|  |  | TOTAL BASE BID: | 0 | 0 | 0 | Should match subs initial base proposal amount
2) | COSTS TO COMPLETE (List Allowances DPR needs to carry to cover undefined scopes or risks, if any)
3.01
3.02
3.03
3.04
|  | Subtotal Cost to Complete: |  | 0 | 0 | 0
COMPARISON TOTAL |  |  |  | 0 | 0 | 0
3) | SCHEDULE
| 4.01 | Total Field Man Hours to Complete Work
| 4.02 | Average Crew Size
4) | LABOR & EQUIPMENT RATES |  |  | RT / OT / DT | RT / OT / DT | RT / OT / DT
| 8.01 | General Foreman
| 8.02 | Foreman
| 8.03 | Journeyman
| 8.04 | Apprentice
5) | UNIT PRICES
9.01
9.02
9.03
RECOMMENDATION:
QUESTIONS / CLARIFICATIONS (List bid analysis notes, questions, responses, etc. below.)
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60

## DOORS, FRAMES & HARDWARE
BID ANALYSIS SHEET
|  | PROJECT: | GENE THEORY |  |  | Subcontractor #1 | Should List the Selected Subcontractor
|  | TRADE: | Doors, Frames and Hardware |  |  | 0
BID PACKAGE:
BID DATE:
|  | DESCRIPTION |  | Subcontractor #1 | Subcontractor #2 | Subcontractor #3
1) | SCOPE INCLUSIONS:
| 1.01 | Base Bid
1.01
1.02
1.03
1.04
1.05
1.06
1.07
1.08
1.09
1.1
1.11
1.12
1.13
|  |  | TOTAL BASE BID: | 0 | 0 | 0 | Should match subs initial base proposal amount
2) | COSTS TO COMPLETE (List Allowances DPR needs to carry to cover undefined scopes or risks, if any)
3.01
3.02
3.03
3.04
|  | Subtotal Cost to Complete: |  | 0 | 0 | 0
COMPARISON TOTAL |  |  |  | 0 | 0 | 0
3) | SCHEDULE
| 4.01 | Total Field Man Hours to Complete Work
| 4.02 | Average Crew Size
4) | LABOR & EQUIPMENT RATES |  |  | RT / OT / DT | RT / OT / DT | RT / OT / DT
| 8.01 | General Foreman
| 8.02 | Foreman
| 8.03 | Journeyman
| 8.04 | Apprentice
5) | UNIT PRICES
9.01
9.02
9.03
RECOMMENDATION:
QUESTIONS / CLARIFICATIONS (List bid analysis notes, questions, responses, etc. below.)
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60

## TILE
BID ANALYSIS SHEET
|  | PROJECT: | GENE THEORY |  |  | Subcontractor #1 | Should List the Selected Subcontractor
|  | TRADE: | Tile |  |  | 0
BID PACKAGE:
BID DATE:
|  | DESCRIPTION |  | Subcontractor #1 | Subcontractor #2 | Subcontractor #3
1) | SCOPE INCLUSIONS:
| 1.01 | Base Bid
1.01
1.02
1.03
1.04
1.05
1.06
1.07
1.08
1.09
1.1
1.11
1.12
1.13
|  |  | TOTAL BASE BID: | 0 | 0 | 0 | Should match subs initial base proposal amount
2) | COSTS TO COMPLETE (List Allowances DPR needs to carry to cover undefined scopes or risks, if any)
3.01
3.02
3.03
3.04
|  | Subtotal Cost to Complete: |  | 0 | 0 | 0
COMPARISON TOTAL |  |  |  | 0 | 0 | 0
3) | SCHEDULE
| 4.01 | Total Field Man Hours to Complete Work
| 4.02 | Average Crew Size
4) | LABOR & EQUIPMENT RATES |  |  | RT / OT / DT | RT / OT / DT | RT / OT / DT
| 8.01 | General Foreman
| 8.02 | Foreman
| 8.03 | Journeyman
| 8.04 | Apprentice
5) | UNIT PRICES
9.01
9.02
9.03
RECOMMENDATION:
QUESTIONS / CLARIFICATIONS (List bid analysis notes, questions, responses, etc. below.)
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60

## FIBER CEMENT PANELS
BID ANALYSIS SHEET
|  | PROJECT: | GENE THEORY |  |  | Subcontractor #1 | Should List the Selected Subcontractor
|  | TRADE: | Fiber Cement Panels |  |  | 0
BID PACKAGE:
BID DATE:
|  | DESCRIPTION |  | Subcontractor #1 | Subcontractor #2 | Subcontractor #3
1) | SCOPE INCLUSIONS:
| 1.01 | Base Bid
1.01
1.02
1.03
1.04
1.05
1.06
1.07
1.08
1.09
1.1
1.11
1.12
1.13
|  |  | TOTAL BASE BID: | 0 | 0 | 0 | Should match subs initial base proposal amount
2) | COSTS TO COMPLETE (List Allowances DPR needs to carry to cover undefined scopes or risks, if any)
3.01
3.02
3.03
3.04
|  | Subtotal Cost to Complete: |  | 0 | 0 | 0
COMPARISON TOTAL |  |  |  | 0 | 0 | 0
3) | SCHEDULE
| 4.01 | Total Field Man Hours to Complete Work
| 4.02 | Average Crew Size
4) | LABOR & EQUIPMENT RATES |  |  | RT / OT / DT | RT / OT / DT | RT / OT / DT
| 8.01 | General Foreman
| 8.02 | Foreman
| 8.03 | Journeyman
| 8.04 | Apprentice
5) | UNIT PRICES
9.01
9.02
9.03
RECOMMENDATION:
QUESTIONS / CLARIFICATIONS (List bid analysis notes, questions, responses, etc. below.)
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60

## ELECTRICAL
BID ANALYSIS SHEET
|  | PROJECT: | GENE THEORY |  |  | Subcontractor #1 | Should List the Selected Subcontractor
|  | TRADE: | Electrical |  |  | 0
BID PACKAGE:
BID DATE:
|  | DESCRIPTION |  | Subcontractor #1 | Subcontractor #2 | Subcontractor #3
1) | SCOPE INCLUSIONS:
| 1.01 | Base Bid
1.01
1.02
1.03
1.04
1.05
1.06
1.07
1.08
1.09
1.1
1.11
1.12
1.13
|  |  | TOTAL BASE BID: | 0 | 0 | 0 | Should match subs initial base proposal amount
2) | COSTS TO COMPLETE (List Allowances DPR needs to carry to cover undefined scopes or risks, if any)
3.01
3.02
3.03
3.04
|  | Subtotal Cost to Complete: |  | 0 | 0 | 0
COMPARISON TOTAL |  |  |  | 0 | 0 | 0
3) | SCHEDULE
| 4.01 | Total Field Man Hours to Complete Work
| 4.02 | Average Crew Size
4) | LABOR & EQUIPMENT RATES |  |  | RT / OT / DT | RT / OT / DT | RT / OT / DT
| 8.01 | General Foreman
| 8.02 | Foreman
| 8.03 | Journeyman
| 8.04 | Apprentice
5) | UNIT PRICES
9.01
9.02
9.03
RECOMMENDATION:
QUESTIONS / CLARIFICATIONS (List bid analysis notes, questions, responses, etc. below.)
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60

## FIRE PROTECTION
BID ANALYSIS SHEET
|  | PROJECT: | GENE THEORY |  |  | Subcontractor #1 | Should List the Selected Subcontractor
|  | TRADE: | SITE UTILITIES |  |  | 0
BID PACKAGE:
BID DATE:
|  | DESCRIPTION |  | Subcontractor #1 | Subcontractor #2 | Subcontractor #3
1) | SCOPE INCLUSIONS:
| 1.01 | Base Bid
1.01
1.02
1.03
1.04
1.05
1.06
1.07
1.08
1.09
1.1
1.11
1.12
1.13
|  |  | TOTAL BASE BID: | 0 | 0 | 0 | Should match subs initial base proposal amount
2) | COSTS TO COMPLETE (List Allowances DPR needs to carry to cover undefined scopes or risks, if any)
3.01
3.02
3.03
3.04
|  | Subtotal Cost to Complete: |  | 0 | 0 | 0
COMPARISON TOTAL |  |  |  | 0 | 0 | 0
3) | SCHEDULE
| 4.01 | Total Field Man Hours to Complete Work
| 4.02 | Average Crew Size
4) | LABOR & EQUIPMENT RATES |  |  | RT / OT / DT | RT / OT / DT | RT / OT / DT
| 8.01 | General Foreman
| 8.02 | Foreman
| 8.03 | Journeyman
| 8.04 | Apprentice
5) | UNIT PRICES
9.01
9.02
9.03
RECOMMENDATION:
QUESTIONS / CLARIFICATIONS (List bid analysis notes, questions, responses, etc. below.)
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60