## Summary Exercise
Owner: Fox Studios
Project: Office Building 103 |  |  |  |  | Designer: Langdon Wilson
Location: Los Angeles, CA |  |  |  |  | Area: 523,244 SF
Description | Quantity | UoM | Unit Price | Cost | Remarks
DIRECT COSTS
PRECONSTRUCTION SERVICES | 1 | LS |  | 230302 | Provide per precon estimate exercise
SITEWORK | 1 | LS |  | 5998256
SHOTCRETE WALLS | 1 | LS |  | 666541
CONCRETE | 1 | LS |  | 7899237
CONCRETE SLAB ON METAL DECK | 1 | LS |  | 926595 | Provide per concrete estimate exercise
CONCRETE REINFORCING | 1 | LS |  | 2861568
MASONRY | 1 | LS |  | 280356
STRUCTURAL STEEL | 1 | LS |  | 3221357 | Provide per steel budget exercise
METAL DECK & MISC METALS | 1 | LS |  | 1778223
WOOD & PLASTIC | 1 | LS |  | 104462
THERMAL/MOISTURE PROTECTION | 1 | LS |  | 998261
DOORS & WINDOWS | 1 | LS |  | 3606336
FINISHES | 1 | LS |  | 3872241
SPECIALTIES | 1 | LS |  | 206182
BUILDING EQUIPMENT | 1 | LS |  | 110837
CONVEYING SYSTEMS | 1 | LS |  | 1504314
BLDG MECHANICAL | 1 | LS |  | 4839189
BLDG ELECTRICAL | 1 | LS |  | 2372177 | Provide per electrical recap sheet
SUBCONTRACTOR BONDS | 1 | LS |  | 564864
STREET USE IMPACTS | 1 | LS |  | 50000
DIRECT COSTS |  |  |  | 42091298 | Calculate Direct Costs
GENERAL EXPENSE COSTS
PROJECT STAFF | 1 | LS |  | 1396615 | Provide per staff estimate exercise
PROJECT OVERHEAD & EQUIP | 1 | LS |  | 664281 | Provide per equip/overhead exercise
INSURANCE/BONDS/TAXES | 1 | LS |  | 667481
GENERAL EXPENSE COSTS |  |  |  | 2728377 | Calculate General Expense Cost
TOTAL COST |  |  |  | 44819675 | Calculate Total Cost
Fee | 3.3% | % |  | 1479049.275 | Input Fee % and Amount
CONTRACTOR'S CONTINGENCY | 0.75% | % |  | 336147.5625 | Calculate Contingency on Total Cost Only
TOTAL BID |  |  |  | 46634871.8375 | Calculate Total Bid Amount