## Precon Budget Exercise
FOX OFFICE BUILDING | [7 empty] | PRECONSTRUCTION STAFF BUDGET
Los Angeles, CA |  |  | EXHIBIT - A
ITEM | QTY |  | RATE | PROD | MH | LABOR | UNIT | MATERIAL | UNIT | EQUIP/SUB | TOTAL
PRECONSTRUCTION STAFFING | 7 | MO
PROJECT EXECUTIVE |  | MO | (Home Office Overhead) |  |  |  |  | 0 |  | 0 | 0
PRECONSTRUCTION MANAGER | 3.5 | MO | 110 |  | 606.6655 | 66733.205 |  | 0 |  | 0 | 66733.205
CONSTRUCTION MANAGER | 1 | MO | 110 |  | 173.333 | 19066.63 |  | 0 |  | 0 | 19066.63
CHIEF ESTIMATOR | 1 | MO | 110 |  | 173.333 | 19066.63 |  | 0 |  | 0 | 19066.63
SR ESTIMATOR | 1 | MO | 80 |  | 173.333 | 13866.64 |  | 0 |  | 0 | 13866.64
ESTIMATOR | 2 | MO | 60 |  | 346.666 | 20799.96 |  | 0 |  | 0 | 20799.96
PROJ SUPERINTENDENT | 2 | MO | 83.49 |  | 346.666 | 28943.1443 |  | 0 |  | 0 | 28943.1443
PROJECT MANAGER | 3.5 | MO | 93.34 |  | 606.6655 | 56626.1578 |  | 0 |  | 0 | 56626.1578
SCHEDULER | 0.5 | MO | 60 |  | 86.6665 | 5199.99 |  | 0 |  | 0 | 5199.99
(Add to and Expand this Spread Sheet as Necessary)
TOTAL BUDGET - PRECONSTRUCTION | [5 empty] | 230302.3571 |  | 0 |  | 0 | 230302.3571
[6 empty] | EXTENDED BY |  |  |  |  | ______
[6 empty] | CHECKED BY |  |  |  |  | ______

## Staff Rates
Billing Rates | Per Hour
Preconstruction Manager | 110
Construction Manager | 110
Chief Estimator | 110
Senior Estimator | 80
Estimator | 60
Project Superintendent | 83.49
Assistant Superintendent | 82.15
Project Manager | 93.34
Project Engineer | 58.91
Office Admin/Accountant | 45
Safety Coordinator | 50
QC Supervisor | 55
Secretary | 28.57
Scheduler | 60
Use these rates for the preconstruction and construction staff estimates.
Some or all of the above (singly or in multiples) may be required for each phase.
Rates are fully burdened