## GE Staff Budget Exercise
FOX OFFICE BUILDING | [7 empty] | CONSTRUCTION STAFF BUDGET
Los Angeles, CA |  |  | EXHIBIT - B
ITEM | QTY |  | RATE | PROD | MH | LABOR | UNIT | MATERIAL | UNIT | EQUIP/SUB | TOTAL
GENERAL EXPENSE STAFFING
PROJECT EXECUTIVE |  | MO | (Home Office Overhead) |  |  |  |  | 0 |  | 0 | 0
PROJECT MANAGER | 22 | MO | 93.34 |  | 3813.326 | 355935.8488 |  | 0 |  | 0 | 355935.8488
PROJ SUPERINTENDENT | 22 | MO | 83.49 |  | 3813.326 | 318374.5877 |  | 0 |  | 0 | 318374.5877
ENGINEER-STRUCTURE | 21 | MO | 58.91 |  | 3639.993 | 214431.9876 |  | 0 |  | 0 | 214431.9876
ENGINEER-MEP/FINISHES | 21 | MO | 58.91 |  | 3639.993 | 214431.9876 |  | 0 |  | 0 | 214431.9876
SECRETARY | 19 | MO | 28.57 |  | 3293.327 | 94090.3524 |  | 0 |  | 0 | 94090.3524
CONCRETE SUPERINTENDENT | 14 | MO | 82.15 |  | 2426.662 | 199350.2833 |  | 0 |  | 0 | 199350.2833
(Add to and Expand this Spread Sheet as Necessary)
TOTAL BUDGET - PROJECT STAFF | [5 empty] | 1396615.0475 |  | 0 |  | 0 | 1396615.0475
[6 empty] | EXTENDED BY |  |  |  |  | ______
[6 empty] | CHECKED BY |  |  |  |  | ______

## Staff Rates
Billing Rates | Per Hour
Preconstruction Manager | 110
Construction Manager | 110
Chief Estimator | 110
Senior Estimator | 80
Estimator | 60
Project Superintendent | 83.49
Assistant Superintendent | 82.15
Project Manager | 93.34
Project Engineer | 58.91
Office Admin/Accountant | 45
Safety Coordinator | 50
QC Supervisor | 55
Secretary | 28.57
Scheduler | 60
Use these rates for the preconstruction and construction staff estimates.
Some or all of the above (singly or in multiples) may be required for each phase.
Rates are fully burdened