## Contract Assessment
Owner Contract Risk Assessment
Job Number
| Owner: |  |  |  | Contractors Role (GC, CM, D/B):
| Architect: |  |  |  | Project Volume:
| Project Name: |  |  |  | Design Status:
| Prepared Date |  |  |  | Compensation basis
| Prepared By/For |  |  |  | Contract Form
No. | Risk Description | Yes | No | Contract Reference | Comments
A | Responsibilities of Design/Builder | x | x
1 | Do the Owner-Approved Construction Documents, supersede the Owner's Project Criteria for scope, quality and function?
2 | Is the Design/Builder responsible for adherence to applicable laws and codes?
3 | Is there a Design Contingency for adjustments and corrections in the Construction Documents?
B | Responsibilities of Owner
4 | Is Owner responsible to pay for and provide necessary surveys? (Geotechnical etc.)
5 | Is Owner responsible for existing physical conditions at the site?
6 | Is Owner liable for payment of permits, fees, authorizations, etc. required by city, state, etc.? If so, are these costs covered in our GMP?
7 | Is the Owner responsible for Special Inspections?
C | Scope
8 | Do the Scope Documents listed in the Contract match the Scope Documents that the Contract Value is based upon?
D | Time
9 | Schedule attached & aligned w/ contract milestones?
10 | Are strikes an excusable delay to the Project?
11 | Are all delay costs for Owner-responsible delays compensable via Change Order?
12 | Are the appropriate number of weather days included in the contract?
13 | Is Design/Builder obligated to meet all activity dates in our schedule, instead of just the Contract Substantial Completion and/or Milestone dates?
E | Budget/GMP/Contract Sum
14 | Is there an allowable Design/Build Contingency? If so, is it adequate?
15 | Does Design/Builder need Owner's approval to spend Contingency?
16 | Is there a shared savings clause?
F | Indemnification/Insurance
17 | Is Design/Builder's Indemnification of Owner limited "to the extent of Design/Builder's negligence"?
18 | Does Owner indemnify Design/Builder for existing Hazardous Materials?
19 | Is Builder's Risk insurance provided by Owner?
20 | Is Design/Builder liable for Insurance deductibles for Builder's Risk losses not resulting from Design/Builder's fault or negligence?
21 | If Owner is providing the builder's risk insurance, will Design/Builder and the Subcontractors be named as Additional Insureds?
G | Cost Reimbursement & Billings
22 | Is Design/Builder required to remove liens if Owner is in default of payments obligations?
23 | What is the payment period? Is it acceptable to Design/Builder and Subs?
24 | Is the Owner allowed to hold retainage until Final Completion?
25 | Interest accrues on late Owner payments?
26 | Does Design/Builder have the right to stop work if Owner fails to pay per the Contract?
27 | Can Design/Builder include deposits for pre-ordered equipment in monthly payment applications?
H | Changes
28 | Do Change Orders take precedence over the Agreement?
29 | Is an acceptable Change Order Fee percentage stipulated?
30 | Is Fee reduced for deductive change orders?
31 | Is Design/Builder required to required to wait for Owners approval before acting upon Owner Change Directives? If so, is Owner responsible for any delays caused by delayed approvals?
I | Damages/Disputes |  |  | 4.5.2
32 | Is there a mutual waiver of Consequential Damages clause?
33 | Are Liquidated Damages the only damages stipulated for late performance
34 | Does the dispute resolution process require litigation instead of arbitration?
35 | Are Attorneys fees payable to the Prevailing Party in a dispute under the Contract?
J | Other
36 | Performance and Payment Bonds Required?
37 | Warranty duration greater than 1 Year after Substantial Completion? Is the start date for Warranties acceptable?
38 | Is Building Information Modeling required? If so, are these costs included within the GMP?
K | Other significant terms and provisions in the contract not in above risk analysis
39
40
41
42
43
44
45
46
47
48