## Proposal Summary (hidden)
Gwinnett Tech
Life Sciences Center
Lawrenceville, GA
Proposal Summary
Lump Sum Bid
Last Updated 10-21-09 |  |  |  | Total Area (GSF): | 81000
Pkg # | Description | Qty | Unit | $ / Unit | Cost
1 | Earthwork & Utilities | #REF! | #REF! | #REF! | #REF!
2 | Selective Demolition | #REF! | #REF! | #REF! | #REF!
3 | Site Improvements | #REF! | #REF! | #REF! | #REF!
4 | Deep Foundations | #REF! | #REF! | #REF! | #REF!
5 | Concrete | #REF! | #REF! | #REF! | #REF!
6 | Precast / Cast Stone | #REF! | #REF! | #REF! | #REF!
7 | Masonry | #REF! | #REF! | #REF! | #REF!
8 | Structural & Misc Steel | #REF! | #REF! | #REF! | #REF!
9 | Rough Carpentry | #REF! | #REF! | #REF! | #REF!
10 | Millwork/ Casework | #REF! | #REF! | #REF! | #REF!
11 | Waterproofing/ Caulk | #REF! | #REF! | #REF! | #REF!
12 | Fireproofing | #REF! | #REF! | #REF! | #REF!
13 | Roofing | #REF! | #REF! | #REF! | #REF!
14 | Metal Panels | #REF! | #REF! | #REF! | #REF!
15 | Doors/ Frames/ Hardware (Material) | #REF! | #REF! | #REF! | #REF!
16 | Doors/ Hardware (Install) | #REF! | #REF! | #REF! | #REF!
17 | Overhead/ Special Acting Doors | #REF! | #REF! | #REF! | #REF!
18 | Glass & Glazing | #REF! | #REF! | #REF! | #REF!
19 | Stucco, Lath, EIFS | #REF! | #REF! | #REF! | #REF!
20 | Drywall & ACT | #REF! | #REF! | #REF! | #REF!
21 | Tile | #REF! | #REF! | #REF! | #REF!
22 | Resilient Flooring | #REF! | #REF! | #REF! | #REF!
23 | Special Flooring | #REF! | #REF! | #REF! | #REF!
24 | Painting & Wallcovering | #REF! | #REF! | #REF! | #REF!
25 | Misc Specialties | #REF! | #REF! | #REF! | #REF!
26 | Toilet Partitions & Accessories | #REF! | #REF! | #REF! | #REF!
27 | Equipment | #REF! | #REF! | #REF! | #REF!
28 | Furnishings | #REF! | #REF! | #REF! | #REF!
29 | Special Construction | #REF! | #REF! | #REF! | #REF!
30 | Conveying Systems | #REF! | #REF! | #REF! | #REF!
31 | Fire Protection | #REF! | #REF! | #REF! | #REF!
32 | Plumbing | #REF! | #REF! | #REF! | #REF!
33 | HVAC & Test/ balance | #REF! | #REF! | #REF! | #REF!
34 | Electrical & Low Voltage | #REF! | #REF! | #REF! | #REF!
35 | General Items | #REF! | #REF! | #REF! | #REF!
| Direct Construction Cost | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| General Conditions, Insurances, & Fees | #REF! | #REF! | #REF! | #REF!
| Total Construction Cost | #REF! | #REF! | #REF! | #REF!

## Pkg Cut-Add (hidden)
AFLAC
CSC Renovation
Columbus, GA
BID PACKAGE SUMMARY
[5 empty] | BID DATE: | 2009-07-09
PKG # | PACKAGE DESCRIPTION | BID DAY |  | BID DAY | SUB
|  | BUDGET | CUT/ADD | TOTAL | NAME | COMMENTS
#REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  | #REF!
|  | #REF! | 0 | #REF!
#REF!

## Materials Procurement Plan
The Living Building @ Georgia Tech
Materials Procurement Plan
Team Name:
BP # | Description | Budget | Estimator | Sub Selection | Sub Quote
1 | GENERAL REQUIREMENTS
3 | CIP CONCRETE
5 | STRUCTURAL STEEL
6 | WOOD STRUCTURE
9A | DRYWALL
9B | CEILINGS
9C | INTERIOR PAINT
7 | INSULATION
26A | PV INVERTER
26B | PV BATTERY
| Total Available Budget | 0 |  | Estimated Cost | 0
|  |  |  | Delta | 0

## Procurement Estimate
Bid Pkg |  |  |  |  | Skanska Budget | SUB 1 | SUB 2 | SUB 3
| Description | Qty | Unit | Unit Cost |  | Total | Total | Total
1 | GENERAL REQUIREMENTS |  |  |  | Skanska Budget | Building Supply Surplus Atlanta, GA | Maners Building Supply Martinez, GA | BMC McDonough, GA
BASE BID
| Final Cleaning | 35800 | sf | 0.53673 | 19215 | 21480 | 26850 | 20000
| Dumpsters | 50 | ea | 450 | 22500 | 27500 | 25000 | 27500
| Daily Cleaning Labor | 12 | ea | 3500 | 42000 | 36000 | 30000 | 36000
| Temporary Fencing, Temp Roads/Laydown | 1 | ls | 15000 | 15000 | 10000 | 10000 | 8000
| Mockups | 1 | ls | 50000 | 50000 | 45000 | 45000 | 50000
| Launch MDO Sign 4'x12'x1/2" | 2 | ea | 1080.5 | 2161 | 2400 | Not Available | 5000
1 | GENERAL REQUIREMENTS |  |  |  | 150876 | 142380 | 136850 | 146500
3 | CIP CONCRETE |  |  |  | Skanska Budget | Argos Norcross, GA | Thomas Concrete Berkeley Lake, GA | Cemex Alpharetta, GA
| BASE BID |  |  |  |  | 1415000 | 1075703 | 1265860
Insert Scoring Matrix Here
| Footings, Grade Beams 3000 psf | 403 | cy |  |  | included | included | included
| CIP Concrete - Retaining Basement Wall 3,000 psi | 246 | cy |  |  | included | included | included
| CIP Concrete - Basement Wall | 45 | cy |  |  | included | included | included
| CIP Concrete - Cistern w/ Crystanlline Treatment 4,500 psi | 74 | cy |  |  | included | included | included
| CIP Concrete - Pier Columns & C1, C2, C4 | 5 | cy |  |  | included | included | included
| CIP Concrete - Podium at Articulated Columns | 1.1 | cy |  |  | included | included | included
| CIP Concrete - Pads at Equipment | 8 | cy |  |  | included | included | included
| CIP Concrete - 1st & 2nd Floor Ramps | 14 | cy |  |  | included | included | included
| Footing at Site Wall from loading dock to road | 40 | lf |  |  | included | included | included
| CIP Concrete - Site Wall - from loading dock to road | 200 | sf |  |  | included | included | included
| Slab on Grade 5" thick 3500 psi | 18468 | cy |  |  | included | included | included
| Knee Wall @ Access Floor Step Down | 2 | cy |  |  | included | included | included
| Knee Wall @ 1st Flr 2' Step Down | 10 | cy |  |  | included | included | included
| Topping Slab (3.5") w/ Fiber Rein. @ Radiant Flooring | 20600 | sf |  |  | included | included | included
| 1" Rigid Insualtion below topping slab @ Lvl 1 Radiant Floor | 11973 | sf |  |  | included | included | included
| Vapor Retarder @ Slab Assembly F1, F3, F6 | 13793 | sf |  |  | included | included | included
AR-101 | Change 10" Working Base @ Slab Assembly back to 4" | -16906 | SF |  |  | included | included | included
AR-102 | Delete 2" capilary break layer of stone/sand | -16906 | sf |  |  | included | included | included
AR-103 | Change 3" Rigid Insulation - Foundation R-15 back to 2" | -11973 | sf |  |  | included | included | included
AR-104 | Change 4" Rigid Insulation - Foundation R-20 back to 2" | -6753 | sf |  |  | included | included | included
AR-105 | Change 5" Rigid Insulation - Foundation R-25 back to 2" | -900 | sf |  |  | included | included | included
MP-08b | Remove Addition for depressed slab, 1' | -197 | SF |  |  | included | included | included
MP-08a | Remove Addition for depressed slab, excavation | -88 | CY |  |  | included | included | included
3 | CIP CONCRETE |  |  |  | 0 | 1415000 | 1075703 | 1265860
5 | STRUCTURAL STEEL |  |  |  | Skanska Budget | Scafco Spokane, WA | Clark Dietrich West Chester, OH | Marinoware Griffin, GA
| BASE BID |  |  |  |  | 633016 | 784586 | 659382
Insert Scoring Matrix Here
| 6" Pipe Articulated Columns | 4.39 | tns | 5915 | 25966.85 | included | included | included
| 3" Pipe Brace | 44 | ea | 70.62 | 3107.28 | included | included | included
| 3/4" Dia Rod | 88 | ea | 172.4 | 15171.2 | included | included | included
| Steel Columns | 4.34 | tns | 5915 | 25671.1 | included | included | included
| Steel Column Base Plates & Anchors | 31 | ea | 275 | 8525 | included | included | included
| Steel Beams w/ brackets & fastners | 39.46 | tns | 5915 | 233405.9 | included | included | included
| Queen Posts, Braced Frames bracket & bolts | 66 | ea | 2660 | 175560 | included | included | included
| Green Roof Parapet Support above windows @ Auditorium | 64 | lf | 265.63 | 17000.32 | included | included | included
| Support Steel @ Auditorium Door A602 | 24 | lf | 265.63 | 6375.12 | included | included | included
| Misc Steel | 35800 | sf | 0.25 | 8950 | included | included | included
| Support for Water Heater | 1 | ea | 500 | 500 | included | included | included
| Misc Support Steel for Rooftop DOAS | 1 | ea | 750 | 750 | included | included | included
| Projection Screen and Projector Supports | 10 | ea | 1250 | 12500 | included | included | included
| Lift and Fold Door Support Steel at Outdoor Study | 16 | lf | 125 | 2000 | included | included | included
| Vanity Supports | 35 | lf | 100 | 3500 | included | included | included
| Toilet Partitions Supports | 10 | ea | 150 | 1500 | included | included | included
| Vertical Brick Angles | 144 | lf | 75.5 | 10872 | included | included | included
| Bent Plate Pour Stop A9/A511 | 175 | lf | 68.57 | 11999.75 | included | included | included
| Countertop Supports @ Innovation Learning | 3 | ea | 1400 | 4200 | included | included | included
| Additional Elevator Shaft Support Steel | 4 | ea | 2487.5 | 9950 | included | included | included
| PV Panel Support Frame (in PV cost) |  | ls |  | 0 | included | included | included
| Steel Expansion to Accomodate Trina Layout | 1 | bay | 20950 | 20950 | included | included | included
| Steel Plate Fin E1/A511 | 327 | lf | 100 | 32700 | included | included | included
| Steel Plate Parapet A1/A507 | 34 | lf | 250 | 8500 | included | included | included
| Steel Plate Parapet A5/A507 | 20 | lf | 750 | 15000 | included | included | included
| Steel Plate Soffit A1,A5,G1/A503 | 90 | lf | 150 | 13500 | included | included | included
| Brick Reveal D4/A502 | 46 | lf | 50 | 2300 | included | included | included
| Sill Angle H5/A500 | 80 | lf | 75 | 6000 | included | included | included
| Misc. Brick Closure Angle A502 | 300 | lf | 75 | 22500 | included | included | included
| Steel Plate Door Jamb D1/A502 | 20 | lf | 75 | 1500 | included | included | included
| Bent Plate at Wood Corner A1/A504 | 80 | lf | 75 | 6000 | included | included | included
| Misc. Steel at Ext Shades | 2 | tn | 5915 | 11830 | included | included | included
| Misc Steel at Curtainwall | 1 | ls | 15000 | 15000 | included | included | included
| Elevator Pit Ladder | 1 | ea | 3040 | 3040 | included | included | included
| Ships Ladder @ Roof | 1 | ea | 3150 | 3150 | included | included | included
| Cane Detection Rail | 1 | ea | 1500 | 1500 | included | included | included
| Metal Screen Under Basement Stair | 21 | lf | 255 | 5355 | included | included | included
| Steel framing/composite slab elevated concrete deck | 1 | ls | 152378 | 152378 | 249925 | 169925 | 189925
5 | STRUCTURAL STEEL |  |  |  | 898707.52 | 882941 | 954511 | 849307
6 | WOOD STRUCTURE |  |  |  | Skanska Budget | Universal TS 5631 NC-62, Burlington, NC 27215 | Alamco/Galyon 1250 Nueces St, George West, TX 78022 | Nordic Lam Quebec, Canada
| BASE BID |  |  |  |  | 1024786 | 1058238 | 986433
Insert Scoring Matrix Here
| Laminated 2x6 and 2x4 Decking, FSC @ 2nd Lvl Flr | 10842 | sf | 11 | 119262 | 356000 | 286000 | 458397
| Laminated 2x6 and 2x4 Decking, FSC @ Roof | 18683 | sf | 11 | 205513 | included above | included above | included above
| Laminated 2x6 and 2x4 Decking Installation, Unloading | 29525 | sf | 6.5 | 191912.5 | 164310 | 171150 | 164310
| 5/8" Plywood, FSC Certified | 29525 | sf | 2.4 | 70860 | 82318 | 69383.75 | 80318
| Roof Deck @ Vestibules | 445 | sf | 20 | 8900 | included | included | included
| Acoustical Mat on NLT | 9440 | sf | 2 | 18880 | 20850 | 19824 | 18880
| One coat stain NLT deck | 63980 | sf | 0.65 | 41587 | Excluded | 30307 | Excluded
| Structural Columns, Material, FSC Certified | 1625 | lf | 54.25 | 88156.25 | included | included | included
| Structural Beams/Trusses, FSC Certified | 4402 | lf | 49.55 | 218119.1 | included | included | included
| Connections, Lam-to-Lam, Tie rod and Connecting hardware | 4402 | lf | 79.5 | 349959 | included | included | included
| One coat stain glu-lam | 6027 | lf | 1.6838 | 10148 | included | included | included
| Glu-Lam Installation, Unloading | 6207 | lf | 34.0433 | 211307 | included | included | included
6 | WOOD STRUCTURE |  |  |  | 1534603.85 | 1648264 | 1634902.75 | 1708338
7 | INSULATION |  |  |  | Skanska Budget | Owens Corning Fairburn, GA | Knauf Shelbyville, IN | CertainTeed Athens, GA
| BASE BID |  |  |  |  | 147000 | 145000 | 153000
Insert Scoring Matrix Here
7 | INSULATION |  |  |  | 160000 | 147000 | 145000 | 153000
9A | DRYWALL |  |  |  | Skanska Budget | Georgia Pacific Cumberland City, TN | USG Bridgeport, AL | CertainTeed Moundsville, WV
| BASE BID |  |  |  |  | 524428 | 597269 | 592870
Insert Scoring Matrix Here
| Rigid Wall Insulation - 3" at Metal Panels | 5797 | sf | 5 | 28985 | included | included | included
| Rigid Wall Insulation - 3" at Wood Siding | 4880 | sf | 5 | 24400 | included | included | included
| Backup at Brick (No Rigid Insulation) | 8996 | sf | 14 | 125944 | included | included | included
| Backup at Metal Panels (No Rigid Insulation) | 5797 | sf | 14 | 81158 | included | included | included
| Backup at Wood (No Rigid Insulation) | 4880 | sf | 14 | 68320 | included | included | included
| Furring @ CMU | 2298 | sf | 3.5 | 8043 | included | included | included
| Interior Partition, 2 gyp, no insulation | 19710 | sf | 8 | 157680 | included | included | included
| Interior Partition, 2 gyp, batt insulation | 708 | sf | 10 | 7080 | included | included | included
| Interior Partition, 1 gyp, no insulation | 3508 | sf | 6.5 | 22802 | included | included | included
| Interior Partition, 1 gyp, batt insulation | 381 | sf | 8.5 | 3238.5 | included | included | included
| Knee Walls @ Kitchenette & Coffee Cart | 313 | sf | 15 | 4695 | included | included | included
| Gypsum Bulkhead at Skylight /Atrium | 100 | sf | 12 | 1200 | included | included | included
| Change CMU walls to GWB shaftwall (leave elevator shaft as CMU) | 2196 | sf | 9.75 | 21411 | included | included | included
9A | DRYWALL |  |  |  | 554956.5 | 524428 | 597269 | 592870
9B | CEILINGS |  |  |  | Skanska Budget | Armstrong | CertainTeed | USG
| BASE BID |  |  |  |  | 131759.68 | 73775 | 83923
Insert Scoring Matrix Here
| Ceiling Tile | 423 | sy | 39 | 16497 | included | 18027 | included
| Ceiling Grid | 22180 | sf | 4.35 | 96483 | included | included | 96483
| Accessories | 4100 | sf | 2.4 | 9840 | included | 12540 | included
| Acoustical Sealant | 3600 | lf | 1.25 | 4500 | included | 4799 | included
9B | CEILINGS |  |  |  | 127320 | 131759.68 | 109141 | 180406
9C | INTERIOR PAINT |  |  |  | Skanska Budget | Benjamin Moore Marietta, GA | Ecos Fairforest, SC | Sherwin Williams Athens, GA
| BASE BID |  |  |  |  | 65700 | 68950 | 58286
Insert Scoring Matrix Here
| Paint - Walls - Prime + 2 Finish Coats | 36650 | sf | 0.75 | 27487.5 | Included | Included | Included
| Paint - Doors, Latex Paint - 2 Finish Coats | 34 | ea | 80 | 2720 | Included | Included | Included
| Paint - Frames, Latex Paint - 2 Finish Coats | 34 | ea | 80 | 2720 | Included | Included | Included
| Paint - Sprinkler Piping | 3600 | lf | 2.65 | 9540 | 9540 | 9540 | 9900
| Paint - Interior steel trim and frames | 1 | ls | 17000 | 17000 | Included | Included | Included
| Paint Ext Door | 9 | ea | 75 | 675 | Included | Included | Included
| Paint Ext HM Frame | 7 | ea | 50 | 350 | Included | Included | Included
| Paint Canopy Columns | 360 | lf | 25 | 9000 | 9000 | 8820 | 7200
| Paint Canopy Joists | 2250 | lf | 12 | 27000 | 27000 | 27000 | 27000
| Prep Canopy Steel for Paint | 1 | ls | 7500 | 7500 | 5000 | 4500 | 4500
| Paint Misc. Exterior Steel | 1 | ls | 15000 | 15000 | Included | Included | Included
| Steel framing/composite slab elevated concrete deck | 1 | ls | 10000 | 10000 | 7500 | 8500 | 8000
9C | INTERIOR PAINT |  |  |  | 128992.5 | 123740 | 127310 | 114886
26A | PV INVERTER |  |  |  | Skanska Budget | SolarEdge Victorville, CA | SMA Rocklin, CA | Huawei Shenzhen, China
| BASE BID |  |  |  |  | 57000 | 48000 | 55000
Insert Scoring Matrix Here
26A | PV INVERTER |  |  |  | 60000 | 57000 | 48000 | 55000
26B | PV BATTERY |  |  |  | Skanska Budget | LG Seoul, South Korea | Samsung Seoul, South Korea
| BASE BID |  |  |  |  | 135000 | 125500
Insert Scoring Matrix Here
26B | PV BATTERY |  |  |  | 150000 | 135000 | 125500 | 0

## Waste Estimate
Materials and Soil Estimate Summary
0 | 2ND | BIDDERS | BOND |  |  | Qty | Unit |  |  |  |  | Comments
*Note: complete yellow highlighted sections
BID DAY |  |  |  | 1 | SOIL EXCAVATION | [6 empty] | Assume 100% waste
[6 empty] | Unit of Measure provided |  | Item by volume |  | Item by weight
[5 empty] | Excavated clean soil | 2000 | cubic yards | 2000 | cubic yards | 2000 | tons
Total waste by volume and weight:
|  |  |  | 3 | CIP CONCRETE | [6 empty] | Assume 10% waste.
[6 empty] | Unit of Measure provided |  | Item by volume |  | Item by weight
BASE BID
[5 empty] | Footings, Grade Beams 3000 psf | 403 | cubic yards | 403 | cubic yards
[5 empty] | CIP Concrete - Retaining Basement Wall 3,000 psi | 246 | cubic yards | 246 | cubic yards
[5 empty] | CIP Concrete - Basement Wall | 45 | cubic yards | 45 | cubic yards
[5 empty] | CIP Concrete - Cistern w/ Crystanlline Treatment 4,500 psi | 74 | cubic yards | 74 | cubic yards
[5 empty] | CIP Concrete - Pier Columns & C1, C2, C4 | 5 | cubic yards | 5 | cubic yards
[5 empty] | CIP Concrete - Podium at Articulated Columns | 1.1 | cubic yard | 1.1 | cubic yard
[5 empty] | CIP Concrete - Pads at Equipment | 8 | cubic yards | 8 | cubic yards
[5 empty] | CIP Concrete - 1st & 2nd Floor Ramps | 14 | cubic yards | 14 | cubic yards
[5 empty] | Footing at Site Wall from loading dock to road | 2 | cubic yards | 2 | cubic yards
[5 empty] | CIP Concrete - Site Wall - from loading dock to road | 14 | cubic yards | 14 | cubic yards
[5 empty] | Slab on Grade 5" thick 3500 psi | 18468 | cubic yards | 18468 | cubic yards
[5 empty] | Knee Wall @ Access Floor Step Down | 2 | cubic yards | 2 | cubic yards
[5 empty] | Knee Wall @ 1st Flr 2' Step Down | 10 | cubic yards | 10 | cubic yards
[5 empty] | Topping Slab (3.5") w/ Fiber Rein. @ Radiant Flooring | 2670 | cubic yards | 2670 | cubic yards
[5 empty] | 1" Rigid Insulation below topping slab @ Lvl 1 Radiant Floor | 445 | cubic yards | 445 | cubic yards
[5 empty] | Vapor Retarder @ Slab Assembly F1, F3, F6 | 1532.6 | cubic yards | 1532.6 | cubic yards
Total waste by volume and weight:
|  |  |  | 5 | STRUCTURAL STEEL | [6 empty] | Assume 10% waste for all materials except those marked as "ea."
Assume 0% waste for materials marked with "ea" quantity (each)
[6 empty] | Unit of Measure provided |  | Item by volume |  | Item by weight
BASE BID
[5 empty] | 6" Pipe Articulated Columns | 4.39 | tons | 17.9184 | cubic feet | 4.39 | tons
[5 empty] | 3" Pipe Brace | 44 | ea
[5 empty] | 3/4" Dia Rod | 88 | ea
[5 empty] | Steel Columns | 4.34 | tons | 17.7143 | cubic feet | 4.34 | tons
[5 empty] | Steel Column Base Plates & Anchors | 31 | ea
[5 empty] | Steel Beams w/ brackets & fastners | 39.46 | tons | 161.0612 | cubic feet | 39.46 | tons
[5 empty] | Queen Posts, Braced Frames bracket & bolts | 66 | ea
[5 empty] | Green Roof Parapet Support above windows @ Auditorium | 64 | lf | 24.4898 | cubic feet | 6 | tons
[5 empty] | Support Steel @ Auditorium Door A602 | 24 | lf | 4.0816 | cubic feet | 1 | tons
[5 empty] | Misc Steel | 35800 | sf | 2448.9796 | cubic feet | 600 | tons
[5 empty] | Support for Water Heater | 1 | ea
[5 empty] | Misc Support Steel for Rooftop DOAS | 1 | ea
[5 empty] | Projection Screen and Projector Supports | 10 | ea
[5 empty] | Lift and Fold Door Support Steel at Outdoor Study | 16 | lf | 1.5918 | cubic feet | 780 | pounds
[5 empty] | Vanity Supports | 35 | lf | 2.448 | cubic feet | 1200 | pounds
[5 empty] | Toilet Partitions Supports | 10 | ea
[5 empty] | Vertical Brick Angles | 144 | lf | 1.4285 | cubic feet | 700 | pounds
[5 empty] | Bent Plate Pour Stop A9/A511 | 175 | lf | 1.7551 | cubic feet | 860 | pounds
[5 empty] | Countertop Supports @ Innovation Learning | 3 | ea
[5 empty] | Additional Elevator Shaft Support Steel | 4 | ea
[5 empty] | Steel Expansion to Accomodate Trina Layout | 1 | ea
[5 empty] | Steel Plate Fin E1/A511 | 327 | lf | 3.2653 | cubic feet | 1600 | pounds
[5 empty] | Steel Plate Parapet A1/A507 | 34 | lf | 0.32653 | cubic feet | 160 | pounds
[5 empty] | Steel Plate Parapet A5/A507 | 20 | lf | 0.20408 | cubic feet | 100 | pounds
[5 empty] | Steel Plate Soffit A1,A5,G1/A503 | 90 | lf | 0.89796 | cubic feet | 440 | pounds
[5 empty] | Brick Reveal D4/A502 | 46 | lf | 0.45918 | cubic feet | 225 | pounds
[5 empty] | Sill Angle H5/A500 | 80 | lf | 0.81633 | cubic feet | 400 | pounds
[5 empty] | Misc. Brick Closure Angle A502 | 300 | lf | 3 | cubic feet | 1470 | pounds
[5 empty] | Steel Plate Door Jamb D1/A502 | 20 | lf | 0.2 | cubic feet | 98 | pounds
[5 empty] | Bent Plate at Wood Corner A1/A504 | 80 | lf | 0.81633 | cubic feet | 400 | pounds
[5 empty] | Misc. Steel at Ext Shades | 2 | tons | 8.1633 | cubic feet | 2 | tons
[5 empty] | Misc Steel at Curtainwall | 1 | ls | 4.0816 | cubic feet | 1 | ton
[5 empty] | Elevator Pit Ladder | 1 | ea
[5 empty] | Ships Ladder @ Roof | 1 | ea
[5 empty] | Cane Detection Rail | 1 | ea
[5 empty] | Metal Screen Under Basement Stair | 21 | lf | 0.20408 | cubic feet | 100 | pounds
[5 empty] | Steel framing/composite slab elevated concrete deck | 1 | ls | 4.0816 | cubic feet | 1 | ton
Total waste by volume and weight:
|  |  |  | 6 | WOOD STRUCTURE | [6 empty] | Assume 10% waste
Do not include acoustical mat, one coat stain, connecting hardware, glu-lam, or glu-lam insulation in waste estimate- assume 0%.
[6 empty] | Unit of Measure provided |  | Item by volume |  | Item by weight
BASE BID
[5 empty] | Laminated 2x6 and 2x4 Decking, FSC @ 2nd Lvl Flr | 120 | sf | 30.5882 | cubic feet | 1.3 | tons
[5 empty] | Laminated 2x6 and 2x4 Decking, FSC @ Roof | 18683 | sf | 4941.1765 | cubic feet | 210 | tons
[5 empty] | Laminated 2x6 and 2x4 Decking Installation, Unloading | 29525 | sf | 7764.7059 | cubic feet | 330 | tons
[5 empty] | 5/8" Plywood, FSC Certified | 29525 | sf | 1294.1176 | cubic feet | 55 | tons
[5 empty] | Roof Deck @ Vestibules | 445 | sf | 117.6471 | cubic feet | 5 | tons
[5 empty] | Acoustical Mat on NLT | 9440 | sf
[5 empty] | One coat stain NLT deck | 63980 | sf
[5 empty] | Structural Columns, Material, FSC Certified | 1625 | lf | 635.2941 | cubic feet | 27 | tons
[5 empty] | Structural Beams/Trusses, FSC Certified | 4402 | lf | 1741.1765 | cubic feet | 74 | tons
[5 empty] | Connections, Lam-to-Lam, Tie rod and Connecting hardware | 4402 | lf
[5 empty] | One coat stain glu-lam | 6027 | lf
[5 empty] | Glu-Lam Installation, Unloading | 6207 | lf
Total waste by volume and weight:
|  |  |  | 9A | DRYWALL | [6 empty] | Assume 10% waste
[5 empty] | (Gypsum Board) | [6 empty] | Do not include backup and furring.
AND INSULATION
[6 empty] | Unit of Measure provided |  | Item by volume |  | Item by weight
BASE BID
[5 empty] | Rigid Wall Insulation - 3" at Metal Panels | 5797 | sf | 107.3519 | cubic yards | 8695.5 | pounds
[5 empty] | Rigid Wall Insulation - 3" at Wood Siding | 4880 | sf | 90.3704 | cubic yards | 7320 | pounds
[5 empty] | Backup at Brick (No Rigid Insulation) | 8996 | sf
[5 empty] | Backup at Metal Panels (No Rigid Insulation) | 5797 | sf
[5 empty] | Backup at Wood (No Rigid Insulation) | 4880 | sf
[5 empty] | Furring @ CMU | 2298 | sf
[5 empty] | Interior Partition, 2 gyp, no insulation | 19710 | sf | 365 | cubic yards
[5 empty] | Interior Partition, 2 gyp, batt insulation | 708 | sf | 13.1111 | cubic yards
[5 empty] | Interior Partition, 1 gyp, no insulation | 3508 | sf | 64.963 | cubic yards
[5 empty] | Interior Partition, 1 gyp, batt insulation | 381 | sf | 7.0556 | cubic yards
[5 empty] | Knee Walls @ Kitchenette & Coffee Cart | 313 | sf | 5.7963 | cubic yards
[5 empty] | Gypsum Bulkhead at Skylight /Atrium | 100 | sf | 1.8519 | cubic yards
Total waste by volume and weight:
|  |  |  | 9B | CEILINGS | [6 empty] | Assume 0% waste for tile, grid, accessories
Do not include sealant in waste estimate- assume 0%.
Assume 10% waste for rubber base
[6 empty] | Unit of Measure provided |  | Item by volume |  | Item by weight
BASE BID
[5 empty] | Ceiling Tile | 423 | sy
[5 empty] | Ceiling Grid | 22180 | sf
[5 empty] | Accessories | 4100 | sf
[5 empty] | Acoustical Sealant | 3600 | lf
[5 empty] | Rubber Base | 3600 | lf | 112.8571 | cubic feet | 790 | pounds
Total waste by volume and weight:
|  |  |  | 9C | INTERIOR PAINT | [6 empty] | Do not include paint in waste estimate- assume 0%.
BASE BID
[5 empty] | Paint - Walls - Prime + 2 Finish Coats | 36650 | sf
[5 empty] | Paint - Doors, Latex Paint - 2 Finish Coats | 34 | ea
[5 empty] | Paint - Frames, Latex Paint - 2 Finish Coats | 34 | ea
[5 empty] | Paint - Sprinkler Piping | 3600 | lf
[5 empty] | Paint - Interior steel trim and frames | 1 | ls
[5 empty] | Paint Ext Door | 9 | ea
[5 empty] | Paint Ext HM Frame | 7 | ea
[5 empty] | Paint Canopy Columns | 360 | lf
[5 empty] | Paint Canopy Joists | 2250 | lf
[5 empty] | Prep Canopy Steel for Paint | 1 | ls
[5 empty] | Paint Misc. Exterior Steel | 1 | ls
[5 empty] | Steel framing/composite slab elevated concrete deck | 1 | ls
[5 empty] | Estimated additional waste | [6 empty] | Assume 100% waste
[6 empty] | Unit of Measure provided |  | Item by volume |  | Item by weight
[5 empty] | Personal food waste | 10 | tons | 50.5051 | cubic yards | 10 | tons
[5 empty] | Plastic/Cans | 15 | tons | 652.1739 | cubic yards | 15 | tons
[5 empty] | Cardboard | 25 | tons | 670.7808 | cubic yards | 25 | tons
[5 empty] | Other non-recyclable waste | 35 | tons | 35 | cubic yards | 35 | tons

## Unit Prices
Concrete Beams | U/M | $/UM
Formwork- Beam Sides | sf | 12
Formwork- Beam Bottoms | sf | 12
Reinforcing- Furnish | ton | 850
Reinforcing- Placement | ton | 450
Concrete Material- Furnish- Assume 5% Waste | cy | 135
Pumping | cy | 7
Place and Finish | cy | 65
Strip Footings
Excavation | cy | 14
Formwork | sf | 4.5
Fine Grade Bottoms | sf | 0.15
Reinforcing- Furnish | ton | 850
Reinforcing- Placement | ton | 450
Concrete Material- Furnish- Assume 5% Waste | cy | 120
Pumping | cy | 7
Place and Finish | cy | 65
Backfill | cy | 22
Spread Footings
Excavation | cy | 14
Formwork | sf | 4.5
Fine Grade Bottoms | sf | 0.15
Reinforcing- Furnish | ton | 850
Reinforcing- Placement | ton | 450
Concrete Material- Furnish- Assume 5% Waste | cy | 120
Pumping | cy | 7
Place and Finish | cy | 65
Backfill | cy | 22
Slab on Grade
Stone Base- 4" Thick | ton | 45
Vapor Barrier | sf | 0.15
Fine Grading | sf | 0.15
Formwork at Turndown Edges | lf | 8
WWF- Material | sf | 0.35
WWF- Placement | sf | 0.45
Concrete Material- Furnish- Assume 5% Waste | cy | 120
Pumping | cy | 7
Place and Finish | cy | 0
Slab Finish and Cure | sf | 1
Elevated Slab
Formwork- Elevated | sf | 12
Reinforcing- Furnish | ton | 850
Reinforcing- Placement | ton | 450
Concrete Material- Furnish- Assume 5% Waste | cy | 140
Pumping | cy | 7
Place and Finish | cy | 0
Slab Finish and Cure | sf | 2
Topping Slabs
Concrete Material- Furnish- Assume 5% Waste | cy | 145
Pumping | cy | 7
Place and Finish | cy | 0
Slab Finish and Cure | sf | 1
Walls
Formwork- Both Sides | sf | 10
Reinforcing- Furnish | ton | 850
Reinforcing- Placement | ton | 450
Concrete Material- Furnish- Assume 5% Waste | cy | 130
Pumping | cy | 7
Place and Finish | cy | 65
Rub and Patch Exposed Surfaces | sf | 1
Columns
Formwork | sf | 10
Reinforcing- Furnish | ton | 850
Reinforcing- Placement | ton | 450
Concrete Material- Furnish- Assume 5% Waste | cy | 125
Pumping | cy | 6
Place and Finish | cy | 65
Rub and Patch Exposed Surfaces | sf | 1
Total of Above
1" Foam at Topping Slab | sf | 1.25
2" Foam | sf | 2
3" Foam | sf | 2.75
Crane and Operator | mo | 20000
Total with Hoisting

## VE List
| The Living Building at Georgia Tech | The Living Building at Georgia Tech
| 100% Design Development ¦ Deductive Alternatives | 100% Design Development ¦ Deductive Alternatives | [16 empty] | 2017-07-10 | 0 | 0 | 0 | 0
Priority | Design Schedule Impact | VE Item No. | Description | Qty | UoM | $/UM | Green | Yellow | Red | Proposed Value | Values of Accepted | Date Accepted | Values of Pending | Decisions Required By | Values of Rejected | Rejected | Notes | Design Team Feedback | EUI Impact | Ball-in-Court | Status of Item in 12/4/17 GMP Submission | Status of Item in 12/20/17 Documents | Unrealized VE Amount
Accepted VE items from 50% DD not incorporated in 100% DD documents | [6 empty] | -1754287.7594 | -280370 | -175000
Pending VE items from 50% DD not incorporated in 100% DD documents
Rejected VE items from 50% DD not incorporated in 100% DD documents
| Large | AR-15 | Reduce bldg volume by 2' total | 1 | LS |  | -71489.93 | -71489.93 | -71489.93 | -71489.93 |  |  |  |  | -71489.93 | 2017-05-23 |  |  |  | Rejected | Rejected | Rejected
| Small | AR-23 | $25/sf Stucco at Wood Soffits | 1 | LS |  | -10035 | -10035 | -10035 | -10035 |  |  |  |  | -10035 | 2017-05-23 |  |  |  | Rejected | Rejected | Rejected
| Medium | AR-24 | Accoya Wood Siding Replacement with Brick | 1 | LS |  | -33285 | -33285 | -33285 | -33285 |  |  |  |  | -33285 | 2017-05-23 |  |  |  | Rejected | Rejected | Rejected
| Medium | AR-25 | Use double-pane glass ILO triple-pane at vestibule | 1 | LS |  | -51300 | -51300 | -51300 | -51300 |  |  |  |  | -51300 | 2017-05-23 |  |  |  | Rejected | Rejected | Rejected
| Medium | AR-26 | Salvage casework ILO new casework | 1 | LS |  | -10000 | -10000 | -10000 | -10000 |  |  |  |  | -10000 | 2017-05-23 |  |  |  | Rejected | Rejected | Rejected
| Medium | AR-27 | Reduce Interior Glazing | 1 | LS |  | -6908 | -6908 | -6908 | -6908 |  |  |  |  | -6908 | 2017-05-23 |  |  |  | Rejected | Rejected | Rejected
| Small | AR-28 | Eliminate Skylights | -179 | SF |  | -53700 | -53700 | -53700 | -53700 |  |  |  |  | -53700 | 2017-05-23 |  |  |  | Rejected | Rejected | Rejected
| Small | AR-29 | Remove (2) Sinks at Maker Space | 1 | LS |  | -4500 | -4500 | -4500 | -4500 |  |  |  |  | -4500 | 2017-05-23 |  |  |  | Rejected | Rejected | Rejected
| Medium | AR-30 | Manually-operated windows ILO automatically controlled windows | 30 | Ea |  | -77507.22 | -77507.22 | -77507.22 | -77507.22 |  |  |  |  | -77507.22 | 2017-06-06 | Discussed as a deductive alternate, not VE item | PAE recommends rejecting this measure. It is unclear if the controls cost of an added red light/green light system is included in the savings. There is significant risk, even with the red light/ green light system of loosing controls of space temperatures and building energy use. Because the spaces don't have "owners" it is usually not feasible to rely on occupants to control the space tightly. | Increase | Rejected | Rejected | Rejected
|  | AR-30a | Remove Controls | 30 | Ea | [9 empty] | -29457.22 |  |  |  |  | Rejected | Rejected | Rejected
|  | AR-30b | Remove Window Motor | 30 | Ea | [9 empty] | -40050 |  |  |  |  | Rejected | Rejected | Rejected
|  | AR-30c | Add Red Light/Green Light allowance, per zone | 12 | Ea | [9 empty] | -8000 |  |  |  |  | Rejected | Rejected | Rejected
| Large | AR-47 | Building Reduction Option 02 | 1 | LS |  | -111600 | -111600 | -111600 | -111600 |  |  |  |  | -111600 | 2017-06-06 | Mutually Exclusive to AR-46. |  |  | Rejected | Rejected | Rejected
| Small | C-03 | Relocating trees ILO new trees | 1 | LS |  | -45419.37 | -45419.37 | -45419.37 | -45419.37 |  |  |  |  | -45419.37 | 2017-05-23 |  |  |  | Rejected | Rejected | Rejected
| Small | C-04 | Remove Green Screen from Stair | 1 | LS |  | -19040 | -19040 | -19040 | -19040 |  |  |  |  | -19040 | 2017-05-23 |  |  |  | Rejected | Rejected | Rejected
| Small | C-05 | Remove All Irrigation Allowance | 1 | LS |  | -35000 | -35000 | -35000 | -35000 |  |  |  |  | -35000 | 2017-05-23 |  |  |  | Rejected | Rejected | Rejected
| Medium | MP-11 | Load Shave off HVAC Equipment | 1 | LS |  | -100000 | -100000 | -100000 | -100000 |  |  |  |  | -100000 | 2017-05-23 |  |  |  | Rejected | Rejected | Rejected
| Large | MP-12 | Alternative Duct System - Ductsox | 1 | LS |  | -6500 | -6500 | -6500 | -6500 |  |  |  |  | -6500 | 2017-06-06 | Potential to review complete ductsox system as well as from the riser on. Determined additional savings not worth the investigation. | Further evaluation needed. | Ductsox may result in 10% increase in fan energy. Prihoda (alternate manufacturer) may be fan energy neutral. | Rejected | Rejected | Rejected
| Small | MP-19 | Removal of Greywater System Treatment Capabilities for Irrigation | 1 | LS |  | -70000 | -70000 | -70000 | -70000 |  |  |  |  | -70000 | 2017-06-06 | To be validated as a deductive alternate, rejected for VE discussion. | Suggestion from Biohabitats - Needs AHJ Response |  | Rejected | Rejected | Rejected
New VE items from 100% DD
| Small | AR-01 | Typical Parapet ilo Glass Rail @ Roof | 1 | LS |  | -5000 |  |  | -5000 | -5000 | 2017-05-23 | [7 empty] | LAS to revise docs | Incorporated in GMP | Incorporated in documents
| Medium | AR-02 | Revise brick specs to remove seismic clips and portland cement lime mortar, modular vs. norman unit price (target savings) | 7447 | SF | -2 | -14894 |  |  | -14894 | -14894 | 2017-05-23 |  |  |  |  | Brick size was revised- still need to revised clips/mortar spec |  |  | LAS to revise docs | Incorporated in GMP | Incorporated in documents
| Small | AR-14 | Paint ilo Wood Paneling @ 2nd Floor Ramp | 1 | LS |  | -6750 |  |  | -6750 | -6750 | 2017-05-23 | [7 empty] | LAS to revise docs | Incorporated in GMP | Incorporated in documents. Wood paneling is Alternate #3
| N/A | AR-51 | Design Assist Cost Savings for Curtainwall System (2.5% Targeted Cost Reduction) | 9764 | SF |  | -30512.5 |  |  | -30512.5 | -30512.5 | 2017-09-29 |  |  |  |  | Kawneer is leading manufacturer at this time. Kawneer allows multiple vendor pricing on their system (Crown Corr & All State). Skanska to demonstrate effort for 3rd vendor pricing if unavailable. |  |  | Skanska to reach out to Kawneer and get additional proposals. BK contacted local rep on 9/29- 3rd number received 10/11/17 | Incorporated in GMP | Included in GMP- nothing to incorporate in documents
| Small | AR-53 | 2" Fin - Reduce 16" projection to 14" & bent plate ilo welded edge | -327 | lf | 28.56 | -9339.12 |  |  | -9339.12 | -9339.12 | 2017-06-13 |  |  |  |  | pending SES feedback from meeting held on 10/10 |  |  | LAS to revise docs | Incorporated in GMP | Incorporated in documents
|  | AR-101 | Change 10" Working Base @ Slab Assembly back to 4" | -16906 | SF | 5.12 | -86558 |  |  | -86558 | -86558 | 2017-09-29 | [7 empty] | LAS to revise docs | Incorporated in GMP | Incorporated in documents
|  | AR-102 | Delete 2" capilary break layer of stone/sand | -16906 | sf | 1.28 | -21639.68 |  |  | -21639.68 | -21639.68 | 2017-09-29 | [7 empty] | LAS to revise docs | Incorporated in GMP | Incorporated in documents
|  | AR-103 | Change 3" Rigid Insulation - Foundation R-15 back to 2" - value in AR-106 | -11973 | sf | 2.5 | [5 empty] | 2017-11-07 |  |  |  |  | Per insulation update 11/7/17 |  |  | LAS to review requirements and confirm if this can be implemented | Incorporated in GMP | Incorporated in documents
|  | AR-104 | Change 4" Rigid Insulation - Foundation R-20 back to 2" - value in AR-106 | -6753 | sf | 3 | [5 empty] | 2017-11-07 |  |  |  |  | Per insulation update 11/7/17 |  |  | LAS to review requirements and confirm if this can be implemented | Incorporated in GMP | Incorporated in documents
|  | AR-105 | Change 5" Rigid Insulation - Foundation R-25 back to 2" - value in AR-106 | -900 | sf | 3.7 | [5 empty] | 2017-09-29 |  |  |  |  | Only below auditorium. |  |  | LAS to revise docs | Incorporated in GMP | Incorporated in documents
|  | AR-106 | Insulation updated per LAS update dated 11/8/2017 | -1 | ls | 53521.5 | -53521.5 |  |  | -53521.5 | -53521.5 | 2017-11-08 |  |  |  |  | pending review of full changes at permit set, value represents AR-103, AR-104, and AR-105 accepted |  |  |  | Incorporated in GMP | Incorporated in documents
|  | AR-107 | Remove added Mullion Extensions (use proposed 8" stock extrusion) | -376 | sf | 46.9 | -17634.4 |  |  | -17634.4 | -17634 | 2017-09-29 |  |  |  |  | pricing per crown corr detail per 20171006, eliminating all deep covers and using a standard 3/4" cover will deduct an additional $4,560 |  |  | LAS to revise docs | Incorporated in GMP | Incorporated in documents
|  | AR-108 | Manual Coiling Door @ Loading Dock ilo specified Automatic | -1 | ls | 7780 | -7780 |  |  | -7780 | -7780 | 2017-09-29 |  |  |  |  | Assa Abloy 14'x9' manual door $3,518 |  |  | Skanska sent info to LAS regarding roll-up door 10/11/17 | Incorporated in GMP | Not incorporated in drawings
|  | AR-109 | Remove added Exterior bar grating at bike storage | -375 | sf | 12 |  |  |  | -4500 |  |  |  |  | -4500 | 2017-09-29 |  |  |  | Rejected | Incorporated in GMP
|  | AR-110 | Remove added Bird Spikes | -1447 | lf | 20 | -28940 |  |  | -28940 | -28940 | 2017-09-29 | [7 empty] | LAS to revise docs | Incorporated in GMP | Incorporated in documents
|  | AR-112 | Change Metal Soffit at Loading to stucco (pending further savings if insulated exposed deck) | -1196 | sf | 20 | -23920 |  |  | -23920 | -23920 | 2017-09-29 | -11960 |  |  |  | May be impacted by ST-101 and would be insulation on exposed decking |  |  | LAS to revise docs | Incorporated in GMP | Incorporated in documents
|  | AR-113 | Reduce Roof Garden media area | -1312 | sf | 24.5 |  |  |  | -32144 |  |  |  |  | -32144 | 2017-09-29 |  |  |  | Rejected | Incorporated in GMP
|  | AR-114 | Move Signage to FFE | -1 | allw | 40100 | -40100 |  |  | -40100 | -40100 | 2017-09-29 | [7 empty] | LAS to revise docs | Incorporated in GMP | Included in GMP- nothing to incorporate in documents
|  | AR-115 | Remove Salvaged Counter @ Innovation Learning | -11 | lf | 275 |  |  |  | -3025 |  |  |  |  | -3025 | 2017-09-29 |  |  |  | Rejected | Incorporated in GMP
|  | AR-116 | Remove Bench @ Collaboration & Multi Purpose | -62 | lf | 195 |  |  |  | -12090 |  |  |  |  | -12090 | 2017-09-29 |  |  |  | Rejected | Incorporated in GMP
|  | AR-117 | Door Hardware procurement change to glazing subcontractor | -1 | ls | 15000 | -15000 |  |  | -15000 | -15000 | 2017-10-10 |  |  |  |  | Skanska shifted purchasing of glass door hardware to glazing provider. Further cost reductions may be realized if specificationis are changed |  |  |  | Incorporated in GMP | Included in GMP- nothing to incorporate in documents
|  | AR-118 | Adjust acoustical design to $110,000 allowance - accomplished by removing the wood battens | -1 | ls | 98698 | -98698 |  |  | -98698 | -98698 | 2017-09-29 |  |  |  |  | Accutrack & Novawall system revised proposal is per allowance. |  |  | LAS to revise docs | Incorporated in GMP | Wood batten is an Alternate, base design is a new diamond/hexagon pattern. Pricing pending
|  | AR-119 | Cable trellis cost reduction | -1 | ls | 20000 | -20000 |  |  | -20000 | -20000 | 2017-09-29 |  |  |  |  | Specify Jakob and others if possible, the attachments at the south entrance needs to be detailed (suggested curb at base and fin at top). |  |  | LAS to revise docs | Incorporated in GMP | Incorporated in documents
|  | AR-120 | Revise non salvage restroom tile specification. | -1 | ls | 10000 | -10000 |  |  | -10000 | -10000 | 2017-09-29 |  |  |  |  | LAS to revise design, Williams & Lindsey suggested other tiles (CT1 Urban Canvas, CT3 Colar Appeal) Mike says it is $7,500+ worth of a reduction. We can achieve futher reductions per a call to be scheduled 10/26. Lindsey Tile proposed Daltile CW01 Ice White 2"x12" ilo CT-3 Ann Sacks Metro nuovo artic white 2"x8" . Incorporation of larger salvage tile size may further reduce the cost. |  |  | Skanska to set up call with Williams Tile 10/26 | Incorporated in GMP | Not incorporated in drawings
|  | AR-121a | Target reduction on stairs and railings - woven stainless w/ crimp | -350 | lf | 150 | -52500 |  |  | -52500 | -52500 | 2017-09-29 |  |  |  |  | per SES who is going to build a mock up for approval. Cable rail is an add of ~$70/lf. |  |  | SES Mock up pending | Incorporated in GMP | Incorporated in documents
|  | AR-121b | Target reduction on stairs and railings - remove holes from feature stair | -21 | ea | 500 | -10500 |  |  | -10500 | -10500 | 2017-10-12 |  |  |  |  | pending SES feedback from meeting held on 10/10. |  |  |  | Incorporated in GMP | Incorporated in documents
|  | AR-121c | Reduce guardrail heights on interior to 42" / Exterior @ Roof to remain at 48" | [13 empty] | Value reflected in AR-121a |  |  |  | Incorporated in GMP | Incorporated in documents
|  | AR-122 | Change concrete ramps to wood framing | -1 | ls | 8547 | -8547 |  |  | -8547 | -8547 | 2017-09-29 | [7 empty] | LAS to revise docs | Incorporated in GMP | Incorporated in documents
|  | AR-123 | Delete staining/coating of nail-lam decking | -1 | ls | 41586 | -41586 |  |  | -41586 | -41586 | 2017-09-29 |  |  |  |  | Beams and columns need coating / wood decking does not. |  |  | LAS to revise docs | Incorporated in GMP | Not incorporated - 06 1529.3.02.C.7&8 saturation and sealing coat is included in the specification.
|  | AR-124 | Substitute material for Accoya wood at soffits and wall to save $4.4/sf | 4881 | sf | -4.4 | -21476.4 |  |  | -21476.4 | -21476.4 | 2017-10-11 |  |  |  |  | material pricing is Thermory Ash Cladding -- $8.57/SF (install phone of $42/sf for residential - thoughts are it will go down with larger area) Accoya material pricing is $13/sf also Rulon product material only $20 to $22/sf - 25% premiun for Thermory FSC and changes to furring |  |  | pending material review | Incorporated in GMP | Not incorporated in drawings
|  | AR-125 | Review roof spec to target $/sf savings- 60 mil TPO ilo 80 mil | 13375 | sf | -2 |  |  |  | -26750 |  |  |  |  | -26750 | 2017-10-31 | $2/sf savings to go to 60 mil, will be 20 year warranty. 20-yr warranty not acceptable. |  |  | Additional manufacturers have confirmed that 80 mil is required for 30 year warranty for this roof with the PV array. (rejected, still searching) | Incorporated in GMP
|  | AR-126 | Change CMU walls to GWB shaftwall (leave elevator shaft as CMU) | 2196 | sf | -4.25 | -9333 |  |  | -9333 | -9333 | 2017-09-29 | [7 empty] | LAS to revise docs | Incorporated in GMP | Incorporated in documents
|  | AR-127 | Delete cost for salvaged wood treads- find low cost/free material | -1 | ls | 58540 | -58540 |  |  | -58540 | -58540 | 2017-09-29 |  |  |  |  | Use salvaged Tech Tower joists |  |  | LAS to revise docs | Incorporated in GMP | Incorporated in documents
|  | AR-128 | Delete bee box / outdoor study area | 1 | ls | -22619.85 |  |  |  | -22619.85 |  |  |  |  | -22619.85 | 2017-09-29 | Need to further define what this entails/changes |  |  | Rejected | Incorporated in GMP
|  | AR-129 | Drop structure at auditorium to remove need for ramp | [6 empty] | 0 | [5 empty] | 2017-09-29 | Need to further define what this entails/changes |  |  | Rejected | Incorporated in GMP
|  | AR-130 | Reduce classroom capacity to 50, and auditorium capacity to 120 | [6 empty] | 0 | [5 empty] | 2017-09-29 | Need to further define what this entails/changes |  |  | Rejected | Incorporated in GMP
|  | AR-131 | Substitute alternate girt system at metal panels | -1 | ls | 12700 | -12700 |  |  | -12700 | -12700 | 2017-09-29 | [7 empty] | Will adjust pricing based on alternate manufacturer already in spec | Incorporated in GMP | Incorporated in documents
|  | AR-132 | Topping slab thickness reduction from 3.5" to 3" (material only - structure to be evaluated) | -1 | ls | 4800 | -4800 |  |  | -4800 | -4800 | 2017-09-29 | [7 empty] | LAS to revise docs | Incorporated in GMP | Incorporated in documents
|  | AR-133 | Remove steel corner detail @ brick exterior by changing to stacked bond. Use break metal | -1 | ls | 10000 |  | -10000 |  | -10000 |  |  | -10000 | [7 empty] | Incorporated in GMP | Incorporated in documents
|  | AR-134 | Remove the Coffee Cart (no water or power) | [6 empty] | 0 | [9 empty] | Skanska to verify with GT if accepted/rejected | Not incorporated in GMP | Not incorporated in drawings
|  | AR-134a | Replace CT-2 tile with paint | -84 | sf | 33 | -2772 |  |  | -2772 |  |  |  |  | -2772 | [5 empty] | Not incorporated in GMP | Not incorporated in drawings
|  | AR-134b | Remove Coffee Cart Rollers | -8 | lf | 650 | -5200 |  |  | -5200 |  |  |  |  | -5200 | [5 empty] | Not incorporated in GMP | Not incorporated in drawings
|  | AR-134c | Remove Basecabinet w/ Counter | -7 | lf | 350 | -2450 |  |  | -2450 |  |  |  |  | -2450 | [5 empty] | Not incorporated in GMP | Not incorporated in drawings
|  | AR-134d | Reduce Banquette | -1.6667 | lf | 350 | -583.3333 |  |  | -583.3333 |  |  |  |  | -583.3333 | [5 empty] | Not incorporated in GMP | Not incorporated in drawings
|  | AR-134e | Remove Sink, Pipe, and water heater | -1 | ea | 1400 | -1400 |  |  | -1400 |  |  |  |  | -1400 | [5 empty] | Not incorporated in GMP | Not incorporated in drawings
|  | AR-134f | Remove Power | -1 | ea | 250 | -250 |  |  | -250 |  |  |  |  | -250 | [5 empty] | Not incorporated in GMP | Not incorporated in drawings
|  | AR-134g | Remove (9) PV panels | -9 | ea | 450 | -4050 |  |  | -4050 |  |  |  |  | -4050 | [5 empty] | Not incorporated in GMP | Not incorporated in drawings
|  | C-01a | Further reduction of Herbaceous Perennials - 12" spacing | -10279.5 | ea | 2.95 | -30324.525 |  |  | -30324.525 | -30324.53 | 2017-10-12 | [7 empty] | LAS to revise docs / Skanska to confirm pricing for spacing change from 10" to 12" | Incorporated in GMP at negative allowance pending confirmation in next set of documents. See allowances | Incorporated in documents
|  | C-101 | Irrigation target reduction | -1 | ls | [11 empty] | Vendor assumption is $80-90K value of roof and ground level system. |  |  | Call with Russell 10/3 to discuss with consultant. | Incorporated in GMP
|  | C-101a | Remove back flow preventer | -1 | ea | 4140 | -4140 |  |  | -4140 | -4140 | 2017-10-11 |  |  |  |  | per Russell |  |  |  | Incorporated in GMP | Incorporated in documents
|  | C-101b | Expand irrigation line spacing to 24" (from 12") includes C-101c | -1 | ls | 14720 | -14720 |  |  | -14720 | -14720 | 2017-10-11 |  |  |  |  | per Russell |  |  |  | Incorporated in GMP | Site spacing is 24", roof 12"
|  | C-101c | Remove inner drop lines at trees (in above reduction of line spacing) | -60 | ea |  |  |  |  | 0 |  | 2017-10-11 |  |  |  |  | per Russell - value included in C-101b |  |  |  | Incorporated in GMP | Incorporated in documents
|  | C-101d | Open controller to Calsense vs. Baseline | 1 | ea | 4255 |  |  |  | 4255 |  |  |  |  | 4255 | 2017-10-11 | per Russell - Calsense is an increase in cost
|  | C-101e | Remove pipe sleeves (HDPE) | -240 | lf | 11.5 |  |  |  | -2760 |  |  |  |  | -2760 | 2017-10-12 | per Russell - not recommended to remove sleeve
|  | C-101f | Replace underground irrigation with overhead system | -1 | ls | 21850 |  |  |  | -21850 |  |  |  |  | -21850 | 2017-10-03 | Don't want spray tied to grey water system
|  | C-101g | Remove the vestibule green roof irrigation - add this system to VE list | -2 | ea | 200 |  |  |  | -400 |  |  |  |  | -400 | 2017-10-12 | pending Russell confirmation on this value / Would create additional burden on systems to process condensate water being used for this irrigation.
|  | C-102 | Reduce planting beds/soil volume | -1000 | cy | 87.87 |  | -87870 |  | -87870 | -87870 | 2017-10-11 |  |  |  |  | 1,518 CY represents 75% of the planting soil increase |  |  | Landscape/civil to review required storage | Incorporated in GMP at negative allowance pending confirmation in next set of documents. See allowances | C-102 & C-111 combine for a reduction of 1,391 CY. Based on LS101 a reduction of 857 CY was realized.
|  | C-104 | Target reduction for alternative manufacturer for storm retention | -1 | ls | 28700 | -28700 |  |  | -28700 | -28700 | 2017-10-11 |  |  |  |  | 100% recycled HDPE HydroVault system |  |  | Pending update per Dennis Taylor and Reeves | Incorporated in GMP | Incorporated in documents
|  | C-105 | Reduce/consolidate storage cube footprint | -1 | ls | 15000 |  | -15000 |  | -15000 | -15000 | 2017-10-12 |  |  |  |  | site reduction and effects are pending |  |  | Landscape/civil to review required storage | Incorporated in GMP at negative allowance pending confirmation in next set of documents. See allowances | Not incorporated in drawings. Storage volume has actually
|  | C-106 | Reduce bed storage depth 6"-12" | -1 | ls | 8000 |  | -8000 |  | -8000 | -8000 | 2017-10-12 |  |  |  |  | revised soil depth plan is pending |  |  | Landscape/civil to review required storage | Not incorporated. Item is reflected in C-103 and C-111 already
|  | C-107 | Reduce vehicular pavement from 12" to 8" | 6062 | sf | -3.2 | -19398.4 |  |  | -19398.4 | -19398.4 | 2017-09-29 | [7 empty] | LAS to revise docs | Incorporated in GMP | Incorporated in documents
|  | C-108 | Reduce subbase at porous sidewalks to 6" | 993 | sf | -3.2 | -3177.6 |  |  | -3177.6 | -3177.6 | 2017-09-29 | [7 empty] | LAS to revise docs | Incorporated in GMP | 6" of 57 stone and 2" choker course
|  | C-109 | Change State Street sidewalk from porous concrete to standard | -1 | ls | 11780 | -11780 |  |  | -11780 | -11780 | 2017-09-29 | [7 empty] | LAS to revise docs | Incorporated in GMP | Incorporated in documents
|  | C-110 | Remove sewer overflow | -1 | ls | 35940 |  |  |  | -35940 |  |  | -35940 |  |  |  | N&B $35,840 |  |  | Rejected
|  | C-103 | Target reduction on hardscape - remaining after C-111 | -1 | ls | 18198.3889 |  |  |  | -18198.3889 |  |  | -18198.3889 |  |  |  | original target $100,000, this represents the remaining target |  |  | Landscape/civil to review possible changes- Skanska to confirm savings | Not incorporated. No information on target changes provided. Will reflect any changes in GMP "true-up" estimate.
|  | C-111 | Site Boundary Reduction per LD101 on 10/6/17 | [6 empty] | 0 | [10 empty] | Incorporated in GMP at negative allowance pending confirmation in next set of documents. See allowances
|  |  | Remove porous pavement | -1477 | sf | 19 | -28063 |  |  | -28063 | -28063 | 2017-10-12 | [7 empty] | LAS to revise documents | Incorporated in GMP at negative allowance pending confirmation in next set of documents. See allowances | Incorporated in documents
|  |  | Remove sidewalk @ boardwalk Alternate area | -714 | sf | 15 | -10710 |  |  | -10710 | -10710 | 2017-10-12 | [7 empty] | LAS to revise documents | Incorporated in GMP at negative allowance pending confirmation in next set of documents. See allowances | Incorporated in documents
|  |  | Remove concrete steps | -161 | sf | 55 | -8855 |  |  | -8855 | -8855 | 2017-10-12 | [7 empty] | LAS to revise documents | Incorporated in GMP at negative allowance pending confirmation in next set of documents. See allowances | Incorporated in documents
|  |  | Remove planted area - soil | -390.5556 | CY | 87.5 | -34173.6111 |  |  | -34173.6111 | -34173.6111 | 2017-10-12 | [7 empty] | LAS to revise documents | Incorporated in GMP at negative allowance pending confirmation in next set of documents. See allowances | C-102 & C-111 combine for a reduction of 1,391 CY. Based on LS101 a reduction of 857 CY was realized.
|  |  | Remove Z type fixtures | -5 | ea | 6700 | -33500 |  |  | -33500 | -33500 | 2017-10-12 | [7 empty] | LAS to revise documents | Incorporated in GMP at negative allowance pending confirmation in next set of documents. See allowances | Incorporated in documents
|  | ST-101 | Steel framing/composite slab ilo elevated concrete deck | -1 | ls | 29493.6 | -29493.6 |  |  | -29493.6 | -29493.6 | 2017-09-29 |  |  |  |  | Dividing line from ground floor to basement needs to be evaluated. |  |  | LAS to revise docs | Incorporated in GMP | Incorporated in documents
|  | ST-102 | Steel frame/wood decking ilo glu-lam/NLT (assumes 12#/sf steel) | -1 | ls | [11 empty] | Need to evaluate vs working with steel/glulam subs to drive costs of glulam/NLT back to 50%DD cost |  |  | Need to set up meeting with Skanska/LAS/U&C, and subs
|  | ST-103 | Review of Steel/wood design with vendors/design team | [6 empty] | 0
|  | ST-104 | Turnkey package for all structure | [6 empty] | 0 | [6 empty] | proposal received 10/24/17, No savings |  |  |  | Not incorporated. Turnkey package did not yield savings, and eliminated the use of salvaged lumber in NLT panels. | N/A
|  | ST-105 | Coordination of Brace Frame scope per 10/10/17 Structure meeting | -1 | ls | 171000 | -171000 |  |  | -171000 | -171000 | 2017-10-10 | [8 empty] | Incorporated in GMP | Included in GMP- nothing to incorporate in documents
|  | ST-106 | Review FSC waste risk of 30% by vendor and go at risk for a lower factor | -1 | ls | 50000 |  |  | -50000 | -50000 | -50000 | 2017-10-12 |  |  |  |  | meeting held 10/10/17 |  |  | Skanska to lead review w/ Southern Timber | Not incorporated. Vendor who had this risk dropped from bidding. Next subcontractor carried. | N/A
|  | ST-107 | Target reduction of Timber Structure through review of NLT deck | -1 | ls | 50000 |  |  | -50000 | -50000 | -50000 | 2017-10-12 |  |  |  |  | meeting held 10/10/17 |  |  | Skanska to lead review w/ Southern Timber | Incorporated in GMP | Included in GMP- nothing to incorporate in documents
|  | ST-108 | PV Canopy adjustment to return to a ballasted system over east roof | -1 | ls | 50000 | -25000 |  |  | -50000 | -25000 | 2017-10-12 | -25000 |  |  |  | LAS/MHP needs to know how many sf need to go back on the roof. |  |  | LAS & U+C to provide narrative & drawing | Not incorporated. Ballasted system efficiency was lower, which would have required more panels. | Not incorporated in drawings
|  | ST-109 | Target reduction of installation of NLT & Glu Lam system | -1 | ls | 150000 |  |  | -75000 | -150000 | -75000 | 2017-10-12 | -75000 |  |  |  | Skanska in review to achieve target |  |  | Skanska | Incorporated in GMP | Included in GMP- nothing to incorporate in documents
0
0
|  | MP-101 | Remove (2) composting bins @ basement | -2 | ea | 7000 |  |  |  | -14000 |  |  |  |  | -14000 | 2017-09-29 | Based upon occupant load. |  |  | Rejected
| Large | MP-08 | Overhead Air Distribution @ Auditorium | 1 | LS | [5 empty] | -47516.09 | 2017-10-11 |  |  |  |  | Revised 10/11/17 |  | Slight increase (1/2 EUI) | LAS to revise docs | Incorporated in GMP
|  | MP-08a | Remove Raised Access Flooring including floor registers | 4090 | SF | -44990 | -44990 |  |  | -44990 | -44990 | [8 empty] | LAS to revise docs | Incorporated in GMP | Incorporated in documents
|  | MP-08b | Remove Addition for depressed slab, 1' | 197 | SF | -6057.75 | -6057.75 |  |  | -6057.75 | -6057.75 | [8 empty] | LAS to revise docs | Incorporated in GMP | Incorporated in documents
|  | MP-08a | Remove Addition for depressed slab, excavation | 87.7 | CY | -532.34 | -532.34 |  |  | -532.34 | -532.34 | [8 empty] | LAS to revise docs | Incorporated in GMP | Incorporated in documents
|  | MP-08c | Mechanical System add - OA requirement w/ relief, fully ducted, wrapped, and 30 diffusers | 1 | LS |  | 10000 |  |  | 10000 | 10000 | 2017-10-12 |  |  |  |  | BKI value per review of N&B narrative |  |  | N&B provided narrative | Incorporated in GMP | Incorporated in documents
|  | MP-08d | Change Controls and Instrumentation for overhead air distribution in lieu of underfloor ( eliminate 2 big ass fans) | 1 | LS |  |  |  |  | 0 | [6 empty] | JCI removed controls of fans, they are controled by a wall switch, so no $ to remove |  |  | NCB to provide narrative for alignment of JCI required scope. | Incorporated in GMP | Incorporated in documents
|  | MP-08e | Power and Data modification with conduit in slab | 1 | LS |  | 6700 |  |  | 6700 | 6700 | 2017-10-12 | [7 empty] | LAS to revise docs | Incorporated in GMP | Incorporated in documents
|  | MP-08f | Deduct 2 big ass fans | -2 | ea | 6318 | -12636 |  |  | -12636 | -12636 | 2017-10-27 |  |  |  |  | N&B deleted per supplying high and returning low |  |  |  | Incorporated in GMP | Not incorporated in drawings - A411 | 12636
|  | MP-102 | Allow fiberglass insulation on chilled water piping, exterior roof piping, and riser piping in lieu of foamglass - keep all mechanical piping located 8' and below as cellular glass | -1 | ls | 28500 | -28500 |  |  | -28500 | -28500 | 2017-10-12 | [7 empty] | LAS/NCB to revise docs | Incorporated in GMP
|  | MP-103 | Remove Grey Water treatment skid and assoicated piping & tanks | -1 | ls | 104521 | -104521 |  |  | -104521 | -104521 | 2017-10-31 |  |  |  |  | Remove the greywater treatment skid and assoicated piping. |  |  | Erin updated diagram, pricing due | Incorporated in GMP | Incorporated in documents
|  | MP-104 | Relocate Main GW Treatment tank inside building / eliminate long UG run | -1 | ls | 10000 |  |  |  | -10000 |  |  |  |  | -10000 | 2017-10-24 |  |  |  | Rejected 10/24/17 | Incorporated in GMP
|  | MP-105 | Eliminate one Mop Sink | -1 | ls | 1950 |  |  |  | -1950 |  |  |  |  | -1950 | 2017-09-29 |  |  |  | Rejected | Incorporated in GMP
|  | MP-106 | Utilize standard Galvanized ductwork | -1 | ls | 27190 |  |  |  | -27190 |  |  |  |  | -27190 | 2017-09-29 | Would need LBC exception |  |  | Rejected | Incorporated in GMP
|  | MP-107 | Change the 316 stainless ductwork to 304 stainless materials | -1 | ls | 4610 | -4610 |  |  | -4610 | -4610 | 2017-09-29 |  |  |  |  | Offer a credit of $4,610 to use 316 SS ilo 304 SS or a credit of $3,015 to use aluminum |  |  | LAS to revise docs | Incorporated in GMP | Incorporated in documents
|  | MP-108 | Remove the liner from the OA ductwork / utilize external wrap | -1 | ls | 2500 | -2500 |  |  | -2500 | -2500 | 2017-09-29 | [7 empty] | LAS to revise docs | Incorporated in GMP | Incorporated in documents
|  | MP-109 | Review integrated automation system for potential savings (target) | [6 empty] | 0 | [10 empty] | Incorporated in GMP | Incorporated in documents
|  | MP-109a | Remove Fire Alarm Integration | -1 | ls | 5430 | -5430 |  |  | -5430 |  | 2017-10-24 |  |  |  |  | value reflected in base # |  |  | N&B to revise docs | Incorporated in GMP | Incorporated in documents
|  | MP-109b | Remove Elevator Integration | -1 | ls | 6750 | -6750 |  |  | -6750 |  | 2017-10-24 |  |  |  |  | value reflected in base # |  |  | N&B to revise docs | Incorporated in GMP | Incorporated in documents
|  | MP-109c | Reduce Custom Dashboard profiles to (4) | -1 | ls | 14366 | -14366 |  |  | -14366 |  | 2017-10-24 |  |  |  |  | value reflected in base # |  |  | N&B to revise docs | Incorporated in GMP | Incorporated in documents
|  | MP-110 | Replace distributed CO2 and relative humidity sensors with Aircuity system. | [6 empty] | 0 | [5 empty] | 2017-10-12 | AirCuity is a $100,000 add per JCI |  |  | Skanska to get pricing from JCI | Incorporated in GMP | Incorporated in documents
|  | MP-111 | Remove all Unit Heaters from the project. | -1 | ls | 4500 | -4500 |  |  | -4500 | -4500 | 2017-09-29 | [7 empty] | LAS to revise docs | Incorporated in GMP | Incorporated in documents
|  | MP-112 | Remove all Baseboard Heaters from the project. | -1 | ls | 9500 | -9500 |  |  | -9500 | -9500 | 2017-09-29 | [7 empty] | LAS to revise docs | Incorporated in GMP | Incorporated in documents
|  | MP-113 | Combine FCU-101 and FCU-102 into one FCU. | -1 | ls | 6150 | -6150 |  |  | -6150 | -6150 | 2017-09-29 | [7 empty] | LAS to revise docs | Incorporated in GMP | Incorporated in documents
|  | MP-114 | Combine FCU-201 and FCU-202 into one FCU. | -1 | ls | 6150 | -6150 |  |  | -6150 | -6150 | 2017-09-29 | [7 empty] | LAS to revise docs | Incorporated in GMP | Incorporated in documents
|  | MP-115 | Controls VE (use cable tray already in job ILO conduit where possible) | -1 | ls | 24913 | -24913 |  |  | -24913 | -24913 | 2017-10-11 |  |  |  |  | JCI priced per N&B sketch |  |  | LAS to revise docs | Incorporated in GMP | Incorporated in documents
|  | MP-116 | Serve Office & Class Lab sinks from water line on second floor. | -1 | ls | 1350 | -1350 |  |  | -1350 | -1350 | 2017-11-10 |  |  |  |  | Need to evaluate sharing of lines between 1st & 2nd floors for further reductions. |  |  | N&B and BKI to review and revise docs | Incorporated in GMP | Incorporated in documents
|  | MP-117 | Alternate composting toilet manufacturer/revised phoenix installation price | -1 | ls | 55000 | -55000 |  |  | -55000 | -55000 | 2017-10-12 | [8 empty] | Incorporated in GMP | Incorporated in documents
|  | MP-118 | Excess Ductwork to another GT Project | -1 | ls | 6700 |  |  |  | -6700 |  |  |  |  | -6700 | 2017-10-12 | Anticipating 8,790 pounds of left over material, value is $6,700 |  |  |  | Incorporated in GMP | Incorporated in documents
|  | MP-119 | Alternate material ILO stainless ductwork for exhaust duct | -1 | ls | 4610 |  |  |  |  | 0 | [5 empty] | Double entry to MP-107 |  |  |  | Incorporated in GMP | Incorporated in documents
|  | MP-120 | Delete two radiant heat zones, combine RZ-108B w/ RZ-108A (no change in sf) and delete RZ-103B and associated 160 sf | -1 | ls | 4500 | -4500 |  |  | -4500 | -4500 | 2017-10-20 | [7 empty] | N&B to revise docs | Incorporated in GMP | Incorporated in documents
|  | MP-121 | Remove eye washes | -1 | ls | 5000 | -5000 |  |  | -5000 | -5000 | 2017-10-20 | [8 empty] | Incorporated in GMP | Incorporated in documents
|  | MP-122 | revised Uponor price | -1 | ls | 5245 | -5245 |  |  | -5245 | -5245 | 2017-10-20 | [8 empty] | Incorporated in GMP | Incorporated in documents
|  | MP-123 | Rainwater to Potable treatment skid per Georgia Tank | -1 | ls | 83357 | -83357 |  |  | -83357 |  |  | -83357 |  |  |  | remove filter redundancy in the potable water system |  |  | GA Tanks updated diagram, pricing due | Incorporated in GMP | Partial reduction incorporated +/- $33k not realized | 33100
|  | MP-124 | Remove Classroom Fan Controls and Wiring | -1 | ls | 50000 |  | -50000 |  | -50000 |  |  | -50000 | [7 empty] | Incorporated in GMP | Incorporated in documents | 0
|  | E-101 | Combine solar arrays, eliminating smaller array and DC microgrid | -1 | ls | 50000 | -50000 |  |  | -50000 | -50000 | 2017-10-10 |  |  |  |  | This represents scope removed from both Hanna and electrical |  |  | LAS to revise docs | Incorporated in GMP | Incorporated into drawings
|  | E-102 | Remove floor data (floor box) connections in the Innovation Learning Area and Collaboration Areas. Utilizing more wireless instead hard-wired connections. The floor box infrastructure would remain if GT OIT would want to add more cabling in the future. | -1 | ls | 1780 | -1780 |  |  | -1780 | -1780 | 2017-10-10 |  |  |  |  | GT stated that (2) data outlets were required at each location but no floor boxes would be required. |  |  | Skanska to verify scope being removed. | Incorporated in GMP | Incorporated into drawings
|  | E-103 | Remove 3 video surveillance cameras covering elevator lobbies and add one inside the elevator to provide similar coverage. Add a camera at 2nd floor egress from roof | -2 | ea | 3800 | -7600 |  |  | -7600 | -7600 | 2017-10-19 | [7 empty] | N&B to revise docs | Incorporated in GMP | Incorporated into drawings
|  | E-104 | Remove Stair 199 camera. The interior entrance is covered on the 2nd floor. | -1 | ls | 3800 | -3800 |  |  | -3800 | -3800 | 2017-10-10 |  |  |  |  | moved to the 2nd floor and one camera removed |  |  | N&B to revise docs | Incorporated in GMP | Incorporated into drawings
|  | E-105 | Remove wireless lock and provide standard key locks for all Electrical Rooms. | -11 | ea | 895 | -9845 |  |  | -9845 | -9845 | 2017-10-10 | [7 empty] | N&B to revise docs | Incorporated in GMP | Incorporated into drawings
|  | E-106 | Remove wireless locks and provide standard key locks for all Class Rooms and Labs. | -13 | ea | 894.7368 |  |  |  | -11631.5789 |  |  |  |  | 2017-10-10 | -11631.5789 |  |  |  | LAS to revise docs | Incorporated in GMP | Incorporated into drawings
|  | E-107 | Remove wall data behind lecterns in 1st floor Classrooms and keep data in the floor box only. | -2 | ea | 137 |  |  |  | -274 |  |  |  |  | 2017-10-10 | -274 |  |  |  | LAS to revise docs | Incorporated in GMP | Incorporated into drawings
|  | E-108 | Reduce data drops in open office to 1 data per workstation and accommodate 1 future data or voice jack at each desk | -12 | ea | 300 | -3600 |  |  | -3600 | -3600 | 2017-10-19 | [7 empty] | N&B to revise docs | Incorporated in GMP | Incorporated into drawings
|  | E-109 | Consolidate 2 standard cameras to one multi-sensor camera in the Lobby Display of Level 1 | -1 | ls | 500 | -500 |  |  | -500 | -500 | 2017-10-19 | [7 empty] | N&B to revise docs | Incorporated in GMP | Incorporated into drawings
|  | E-111 | Limit the networked lighting control system to regularly occupied spaces. In BOH spaces, provide only vacancy sensors or timer switches. | -1 | ls | 2385 | -2385 |  |  | -2385 | -2385 | 2017-10-12 | [7 empty] | N&B to revise docs | Incorporated in GMP | Incorporated into drawings
|  | E-112 | Target Lighting Fixture Package Reduction to $14/SF for Lighting/Controls Installed | -1 | ls | 87500 |  | -77000 |  | -77000 | -77000 | 2017-10-12 |  |  |  |  | This is a $2.5/sf target reduce for the interior fixture package. |  |  | Action item for design assist meetings | Incorporated in GMP | Incorporated into drawings
|  | E-112a | Basement light fixture adjustment | -84 | lf | 125 |  | -10500 |  | -10500 | -10500 | 2017-10-20 | [7 empty] | LAS/N&B to revise docs | Incorporated in GMP- Fixtures were added, not removed. | Incorporated into drawings
|  | E-112b | Boost up the lumen and shorten the fixture length | [6 empty] | 0 | 0 | [5 empty] | action per electrical review 10/20/17 |  |  | LAS/N&B to revise docs | Incorporated in GMP | Incorporated into Dwg's - Lumens have also been increased based on the new luminaire Schedule compared to 100% DD
|  | E-113 | Reduce fire alarm to code minimum in circulation spaces. GT standard requires additional devices. | -1 | ls | 22000 |  | -22000 |  | -22000 | [6 empty] | N&B to review |  |  | N&B to review what this would do, and get GT to review/approve | Incorporated in GMP at negative allowance pending confirmation in next set of documents. See allowances | Not Incorporated into drawings.
|  | E-114 | Remove (1) camera at roof hatch | -1 | ls | 3800 | -3800 |  |  | -3800 | -3800 | 2017-10-19 | [7 empty] | N&B to revise docs | Incorporated in GMP | Incorporated into drawings - T113A
|  | E-115 | Reduce the number of outlets in each room (class lab, classrooms) | [13 empty] | N&B to review the reduction in outlets |  |  | N&B to revise docs | Incorporated in GMP | Incorporated into drawings - along ext. walls of rooms
|  | E-116 | Remove Blue Phones from project | -2 | ls | 15454.5 | -30909 |  |  | -30909 | -30909 | 2017-11-10 | [7 empty] | Skanska to verify with GT | Incorporated in GMP | Sheet T010 - ECS phones still shown, but note below states they are not in the contract
|  | E-117 | Remove type Z fixtures from the west side of the site | -6 | ls | 6700 | -40200 |  |  | -40200 | -40200 | 2017-11-10 | [8 empty] | Incorporated in GMP | Incorporated into drawings - Note states (NIC)
|  | E-118 | Lai VE items to Eckardt to update
|  | AV-101 | Remove third projector in Auditorium on short wall. | [6 empty] | 0 | [9 empty] | Skanska to price, GT to review is appropriate
|  | AV-102 | Remove projection system in Innovation Learning. This is a small area that could be served by a display on cart. | [6 empty] | 0 | [9 empty] | Skanska to price, GT to review is appropriate
|  |  | New/Revisited topics discussed in 10/12 Meeting: | [6 empty] | 0
|  |  | Remove the irrigation system tied to the condensate | [6 empty] | 0
|  |  | Reduce the building occupancy through shorter hours of operation | [6 empty] | 0
|  |  | Remove the Bee Box | [6 empty] | 0
|  |  | Reduce the occupancy of the Auditorium | [6 empty] | 0
|  |  | Remove all type B light fixtures and replace with another pendant | [6 empty] | 0
|  |  | Reduce 50% of the lights hung from the PV | [6 empty] | 0
|  |  | Class labs - remove (1) row of lights (3 to 2 rows) | [6 empty] | 0
|  |  | Hanna Solar to review Battery system by Telsa PowerPack & Switch powered by GELI | [6 empty] | 0
|  |  | Windows manual vs. automatic | [6 empty] | 0
|  |  | Genwall system analysis | [6 empty] | 0
0
|  | Z-01 | SUBTOTAL (Non-Exclusive) | [6 empty] | -3263710.0973 | -2001049.0311 |  | -309455.3889 |  | -818677.7033 | [7 empty] | 45736
|  | Z-02 | MARKUPS ADJUSTMENT | 1 | LS |  |  |  |  | -282953.5383 | -173484.7418 |  | -26828.822 |  | -70976.8166
|  | Z-03 | GRAND TOTAL | [6 empty] | -3546663.6356 | -2174533.7729 |  | -336284.2109 |  | -889654.5199
[6 empty] | Accepted VE Total |  |  |  |  | -2174533.7729 | Pending VE Total | -336284.2109
[6 empty] | Estimate Total |  |  |  |  | 21471781.2082 | Estimate Total w/ Accepted VE | 19297247.4352
[6 empty] | Estimate Total w/ Accepted VE |  |  |  |  | 19297247.4352 | Estimate Total w/ Pending VE | 18960963.2243 |  |  |  |  | 21935646.03
[6 empty] | Budget |  |  |  |  | 18600000 | Budget | 18600000 |  |  |  |  | 19761112.2571
[6 empty] | Gap to Budget with Accepted VE |  |  |  |  | -697247.4352 | Gap to Budget w/ Accepted & Pending VE | -360963.2243
[6 empty] | Accepted VE Contingencies | [5 empty] | Projected with Pending VE Contingencies
[6 empty] | Revised Direct Cost w/ Accepted VE |  |  |  |  | 15483950.0149 | Revised Direct Cost with Accepted & Pending VE | 15174494.626
[6 empty] | Design Contingency Remaining |  |  |  |  | 400000 | Design Contingency Remaining | 400000
[6 empty] | Escalation Remaining |  |  |  |  | 154839.5001 | Escalation Remaining | 151744.9463
[6 empty] | Contractor's Contingency Remaining |  |  |  |  | 464518.5004 | Contractor's Contingency Remaining | 455234.8388
[6 empty] | Total Contingencies Remaining |  |  |  |  | 1019358.0006 | Total Contingencies Remaining | 1006979.785