## SIPS
Sanford Consortium for Regenerative Medicine
Block | AREA
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39
Interstitial | Zone 1
Interstitial | Zone 2
Interstitial | Zone 3
Level 1 | Zone 1
Level 1 | Zone 2
Level 1 | Zone 3
Level 2 | Zone 1
Level 2 | Zone 2
Level 3 | Zone 1
Level 3 | Zone 2
Level 4 | Zone 1
Level 4 | Zone 2
|  | # |  |  | SIPS Activitiy | [9 empty] | Duration | [6 empty] | # |  |  | SIPS Activitiy | [9 empty] | Duration
1
Install Duct Laterals & Branch Lines

## Chart Answer
Production Rates
ID | MEP Install | # of days to complete each Level
| Install Plumbing Piping Laterals | 15
3 | Install FS Laterals & Drops for Duct | 5
5 | Install Plumbing Piping Mains | 10
| Install Shoring | 10
| Install Duct Laterals & Branch Lines | 15
| Install Duct Mains | 10
| Perform Duct Leakage Test/Repairs | 5
9 | Frame Critical Walls & Ceilings | 10
| Install Mechanical Piping Mains | 10
| Remove Shores | 10
| Install Hangers & Racks | 5
| MEP Layout | 5
| Install Mechanical Piping Laterals | 15
| Insulate Pipe & Duct | 15