{"text_format":"1","workbook":"xlsx","n_sheets":2,"sheets":["HCC","Sheet1"],"not_rendered":{"charts":0,"images":1,"macros":0,"external_links":0,"defined_names":200,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"HCC","index":0,"n_rows":34,"n_cols":296,"rows_kept":34,"cut":false,"hidden":false,"merged":[[1,290,1,295],[1,212,1,217],[1,206,1,211],[1,200,1,205],[1,194,1,199],[1,284,1,289],[1,272,1,277],[1,266,1,271],[1,260,1,265],[1,254,1,259],[1,248,1,253],[1,242,1,247],[1,236,1,241],[1,230,1,235],[1,224,1,229],[1,218,1,223],[1,278,1,283],[1,188,1,193],[1,116,1,121],[1,110,1,115],[1,104,1,109],[1,182,1,187],[1,176,1,181],[1,170,1,175],[1,164,1,169],[1,122,1,127],[1,158,1,163],[1,152,1,157],[1,146,1,151],[1,140,1,145],[1,134,1,139],[1,128,1,133],[1,80,1,85],[1,86,1,91],[1,92,1,97],[1,98,1,103],[0,56,0,82],[1,68,1,73],[1,74,1,79],[1,56,1,61],[1,62,1,67],[4,10,4,11],[0,38,0,55],[1,20,1,25],[1,26,1,31],[1,32,1,37],[0,20,0,37],[0,14,0,19],[1,38,1,43],[1,44,1,49],[1,50,1,55],[1,15,1,19]]}
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"April",null,null,null,null,null,"May",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"August",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"September"]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Week 87",null,null,null,null,null,"Week 88",null,null,null,null,null,"Week 89",null,null,null,null,null,"Week 01",null,null,null,null,null,"Week 02",null,null,null,null,null,"Week 03",null,null,null,null,null,"Week 04",null,null,null,null,null,"Week 05",null,null,null,null,null,"Week 06",null,null,null,null,null,"Week 07",null,null,null,null,null,"Week 08",null,null,null,null,null,"Week 09",null,null,null,null,null,"Week 10",null,null,null,null,null,"Week 11",null,null,null,null,null,"Week 12",null,null,null,null,null,"Week 13",null,null,null,null,null,"Week 14",null,null,null,null,null,"Week 15",null,null,null,null,null,"Week 16",null,null,null,null,null,"Week 17",null,null,null,null,null,"Week 18",null,null,null,null,null,"Week 19",null,null,null,null,null,"Week 20",null,null,null,null,null,"Week 21",null,null,null,null,null,"Week 22",null,null,null,null,null,"Week 23",null,null,null,null,null,"Week 24",null,null,null,null,null,"Week 25",null,null,null,null,null,"Week 26",null,null,null,null,null,"Week 27",null,null,null,null,null,"Week 28",null,null,null,null,null,"Week 29",null,null,null,null,null,"Week 30",null,null,null,null,null,"Week 31",null,null,null,null,null,"Week 32",null,null,null,null,null,"Week 33",null,null,null,null,null,"Week 34",null,null,null,null,null,"Week 35",null,null,null,null,null,"Week 36",null,null,null,null,null,"Week 37",null,null,null,null,null,"Week 38",null,null,null,null,null,"Week 39",null,null,null,null,null,"Week 40",null,null,null,null,null,"Week 41",null,null,null,null,null,"Week 42",null,null,null,null,null,"Week 43"]
[null,null,null,null,"Region VII- Commercial Building Division",null,null,null,null,null,null,null,null,null,{"$f":"O5","v":"2011-04-25"},null,null,null,null,null,{"$f":"U5","v":"2011-05-02"},null,null,null,null,null,{"$f":"AA5","v":"2011-05-09"},null,null,null,null,null,{"$f":"AG5","v":"2011-05-16"},null,null,null,null,null,{"$f":"AM5","v":"2013-12-23"},null,null,null,null,null,{"$f":"AS5","v":"2013-12-30"},null,null,null,null,null,{"$f":"AY5","v":"2014-01-06"},null,null,null,null,null,{"$f":"BE5","v":"2014-01-13"},null,null,null,null,null,{"$f":"BK5","v":"2014-01-20"},null,null,null,null,null,{"$f":"BQ5","v":"2014-01-27"},null,null,null,null,null,{"$f":"BW5","v":"2014-02-03"},null,null,null,null,null,{"$f":"CC5","v":"2014-02-10"},null,null,null,null,null,{"$f":"CI5","v":"2014-02-17"},null,null,null,null,null,{"$f":"CO5","v":"2014-02-24"},null,null,null,null,null,{"$f":"CU5","v":"2014-03-03"},null,null,null,null,null,{"$f":"DA5","v":"2014-03-10"},null,null,null,null,null,{"$f":"DG5","v":"2014-03-17"},null,null,null,null,null,{"$f":"DM5","v":"2014-03-24"},null,null,null,null,null,{"$f":"DS5","v":"2014-03-31"},null,null,null,null,null,{"$f":"DY5","v":"2014-04-07"},null,null,null,null,null,{"$f":"EE5","v":"2014-04-14"},null,null,null,null,null,{"$f":"EK5","v":"2014-04-21"},null,null,null,null,null,{"$f":"EQ5","v":"2014-04-28"},null,null,null,null,null,{"$f":"EW5","v":"2014-05-05"},null,null,null,null,null,{"$f":"FC5","v":"2014-05-12"},null,null,null,null,null,{"$f":"FI5","v":"2014-05-19"},null,null,null,null,null,{"$f":"FO5","v":"2014-05-26"},null,null,null,null,null,{"$f":"FU5","v":"2014-06-02"},null,null,null,null,null,{"$f":"GA5","v":"2014-06-09"},null,null,null,null,null,{"$f":"GG5","v":"2014-06-16"},null,null,null,null,null,{"$f":"GM5","v":"2014-06-23"},null,null,null,null,null,{"$f":"GS5","v":"2014-06-30"},null,null,null,null,null,{"$f":"GY5","v":"2014-07-07"},null,null,null,null,null,{"$f":"HE5","v":"2014-07-14"},null,null,null,null,null,{"$f":"HK5","v":"2014-07-21"},null,null,null,null,null,{"$f":"HQ5","v":"2014-07-28"},null,null,null,null,null,{"$f":"HW5","v":"2014-08-04"},null,null,null,null,null,{"$f":"IC5","v":"2014-08-11"},null,null,null,null,null,{"$f":"II5","v":"2014-08-18"},null,null,null,null,null,{"$f":"IO5","v":"2014-08-25"},null,null,null,null,null,{"$f":"IU5","v":"2014-09-01"},null,null,null,null,null,{"$f":"JA5","v":"2014-09-08"},null,null,null,null,null,{"$f":"JG5","v":"2014-09-15"},null,null,null,null,null,{"$f":"JM5","v":"2014-09-22"},null,null,null,null,null,{"$f":"JS5","v":"2014-09-29"},null,null,null,null,null,{"$f":"JY5","v":"2014-10-06"},null,null,null,null,null,{"$f":"KE5","v":"2014-10-13"}]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S"]
[null,"Resp.",null,null,"Activity","JHA",null,"Material On site?","Anticipated Delivery Date","Resp Sub","HPCC Crew",null,"Start","Finish","2011-04-25","2011-04-26","2011-04-27","2011-04-28","2011-04-29","2011-04-30","2011-05-02","2011-05-03","2011-05-04","2011-05-05","2011-05-06","2011-05-07","2011-05-09","2011-05-10","2011-05-11","2011-05-12","2011-05-13","2011-05-14","2011-05-16","2011-05-17","2011-05-18","2011-05-19","2011-05-20","2011-05-21","2013-12-23","2013-12-24","2013-12-25","2013-12-26","2013-12-27","2013-12-28","2013-12-30","2013-12-31","2014-01-01","2014-01-02","2014-01-03","2014-01-04","2014-01-06","2014-01-07","2014-01-08","2014-01-09","2014-01-10","2014-01-11","2014-01-13","2014-01-14","2014-01-15","2014-01-16","2014-01-17","2014-01-18","2014-01-20","2014-01-21","2014-01-22","2014-01-23","2014-01-24","2014-01-25","2014-01-27","2014-01-28","2014-01-29","2014-01-30","2014-01-31","2014-02-01","2014-02-03","2014-02-04","2014-02-05","2014-02-06","2014-02-07","2014-02-08","2014-02-10","2014-02-11","2014-02-12","2014-02-13","2014-02-14","2014-02-15","2014-02-17","2014-02-18","2014-02-19","2014-02-20","2014-02-21","2014-02-22","2014-02-24","2014-02-25","2014-02-26","2014-02-27","2014-02-28","2014-03-01","2014-03-03","2014-03-04","2014-03-05","2014-03-06","2014-03-07","2014-03-08","2014-03-10","2014-03-11","2014-03-12","2014-03-13","2014-03-14","2014-03-15","2014-03-17","2014-03-18","2014-03-19","2014-03-20","2014-03-21","2014-03-22","2014-03-24","2014-03-25","2014-03-26","2014-03-27","2014-03-28","2014-03-29","2014-03-31","2014-04-01","2014-04-02","2014-04-03","2014-04-04","2014-04-05","2014-04-07","2014-04-08","2014-04-09","2014-04-10","2014-04-11","2014-04-12","2014-04-14","2014-04-15","2014-04-16","2014-04-17","2014-04-18","2014-04-19","2014-04-21","2014-04-22","2014-04-23","2014-04-24","2014-04-25","2014-04-26","2014-04-28","2014-04-29","2014-04-30","2014-05-01","2014-05-02","2014-05-03","2014-05-05","2014-05-06","2014-05-07","2014-05-08","2014-05-09","2014-05-10","2014-05-12","2014-05-13","2014-05-14","2014-05-15","2014-05-16","2014-05-17","2014-05-19","2014-05-20","2014-05-21","2014-05-22","2014-05-23","2014-05-24","2014-05-26","2014-05-27","2014-05-28","2014-05-29","2014-05-30","2014-05-31","2014-06-02","2014-06-03","2014-06-04","2014-06-05","2014-06-06","2014-06-07","2014-06-09","2014-06-10","2014-06-11","2014-06-12","2014-06-13","2014-06-14","2014-06-16","2014-06-17","2014-06-18","2014-06-19","2014-06-20","2014-06-21","2014-06-23","2014-06-24","2014-06-25","2014-06-26","2014-06-27","2014-06-28","2014-06-30","2014-07-01","2014-07-02","2014-07-03","2014-07-04","2014-07-05","2014-07-07","2014-07-08","2014-07-09","2014-07-10","2014-07-11","2014-07-12","2014-07-14","2014-07-15","2014-07-16","2014-07-17","2014-07-18","2014-07-19","2014-07-21","2014-07-22","2014-07-23","2014-07-24","2014-07-25","2014-07-26","2014-07-28","2014-07-29","2014-07-30","2014-07-31","2014-08-01","2014-08-02","2014-08-04","2014-08-05","2014-08-06","2014-08-07","2014-08-08","2014-08-09","2014-08-11","2014-08-12","2014-08-13","2014-08-14","2014-08-15","2014-08-16","2014-08-18","2014-08-19","2014-08-20","2014-08-21","2014-08-22","2014-08-23","2014-08-25","2014-08-26","2014-08-27","2014-08-28","2014-08-29","2014-08-30","2014-09-01","2014-09-02","2014-09-03","2014-09-04","2014-09-05","2014-09-06","2014-09-08","2014-09-09","2014-09-10","2014-09-11","2014-09-12","2014-09-13","2014-09-15","2014-09-16","2014-09-17","2014-09-18","2014-09-19","2014-09-20","2014-09-22","2014-09-23","2014-09-24","2014-09-25","2014-09-26","2014-09-27","2014-09-29","2014-09-30","2014-10-01","2014-10-02","2014-10-03","2014-10-04","2014-10-06","2014-10-07","2014-10-08","2014-10-09","2014-10-10","2014-10-11","2014-10-13","2014-10-14","2014-10-15","2014-10-16","2014-10-17","2014-10-18"]
[1]
[2]
[3]
[4]
[5]
[6]
[7]
[8]
[9]
[10]
[11]
[12]
[13]
[14]
[15]
[16]
[16]
[17]
[18]
[19]
[20]
[43]
[44]
[45]
[46]
[47]
[48]
[49]
[50,null,null,null," ",null,null," ",null,null,null,null," "," "]

{"sheet":"Sheet1","index":1,"n_rows":5,"n_cols":1,"rows_kept":5,"cut":false,"hidden":false,"merged":[]}
["Activites"]
["ConSpan Vault"]
["Contech Storm Pipe"]
["Garage Xcel UG Tie-In"]
["Remove Gas Pump"]