{"text_format":"1","workbook":"xlsx","n_sheets":2,"sheets":["HCC","Sheet1"],"not_rendered":{"charts":0,"images":1,"macros":0,"external_links":0,"defined_names":200,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"HCC","index":0,"n_rows":29,"n_cols":122,"rows_kept":29,"cut":false,"hidden":false,"merged":[[4,10,4,11],[1,20,1,25],[1,26,1,31],[1,32,1,37],[0,20,0,37],[0,14,0,19],[1,15,1,19],[1,44,1,49],[1,50,1,55],[1,56,1,61],[1,62,1,67],[0,38,0,46],[1,38,1,43],[1,80,1,85],[1,74,1,79],[1,68,1,73],[1,86,1,91],[1,116,1,121],[1,110,1,115],[1,104,1,109],[1,98,1,103],[1,92,1,97]]}
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"April",null,null,null,null,null,"May"]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Week 87",null,null,null,null,null,"Week 88",null,null,null,null,null,"Week 89",null,null,null,null,null,"Week 07",null,null,null,null,null,"Week 08",null,null,null,null,null,"Week 09",null,null,null,null,null,"Week 10",null,null,null,null,null,"Week 11",null,null,null,null,null,"Week 12",null,null,null,null,null,"Week 13",null,null,null,null,null,"Week 14",null,null,null,null,null,"Week 15",null,null,null,null,null,"Week 16",null,null,null,null,null,"Week 17",null,null,null,null,null,"Week 18",null,null,null,null,null,"Week 19",null,null,null,null,null,"Week 20"]
[null,null,null,null,"Region VII- Commercial Building Division",null,null,null,null,null,null,null,null,null,{"$f":"O5","v":"2011-04-25"},null,null,null,null,null,{"$f":"U5","v":"2011-05-02"},null,null,null,null,null,{"$f":"AA5","v":"2011-05-09"},null,null,null,null,null,{"$f":"AG5","v":"2011-05-16"},null,null,null,null,null,{"$f":"AM5","v":"2014-02-03"},null,null,null,null,null,{"$f":"AS5","v":"2014-02-10"},null,null,null,null,null,{"$f":"AY5","v":"2014-02-17"},null,null,null,null,null,{"$f":"BE5","v":"2014-02-24"},null,null,null,null,null,{"$f":"BK5","v":"2014-03-03"},null,null,null,null,null,{"$f":"BQ5","v":"2014-03-10"},null,null,null,null,null,{"$f":"BW5","v":"2014-03-17"},null,null,null,null,null,{"$f":"CC5","v":"2014-03-24"},null,null,null,null,null,{"$f":"CI5","v":"2014-03-31"},null,null,null,null,null,{"$f":"CO5","v":"2014-04-07"},null,null,null,null,null,{"$f":"CU5","v":"2014-04-14"},null,null,null,null,null,{"$f":"DA5","v":"2014-04-21"},null,null,null,null,null,{"$f":"DG5","v":"2014-04-28"},null,null,null,null,null,{"$f":"DM5","v":"2014-05-05"}]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S","M","T","W","T","F","S"]
[null,"Resp.",null,null,"Activity","JHA",null,"Material On site?","Anticipated Delivery Date","Resp Sub","HPCC Crew",null,"Start","Finish","2011-04-25","2011-04-26","2011-04-27","2011-04-28","2011-04-29","2011-04-30","2011-05-02","2011-05-03","2011-05-04","2011-05-05","2011-05-06","2011-05-07","2011-05-09","2011-05-10","2011-05-11","2011-05-12","2011-05-13","2011-05-14","2011-05-16","2011-05-17","2011-05-18","2011-05-19","2011-05-20","2011-05-21","2014-02-03","2014-02-04","2014-02-05","2014-02-06","2014-02-07","2014-02-08","2014-02-10","2014-02-11","2014-02-12","2014-02-13","2014-02-14","2014-02-15","2014-02-17","2014-02-18","2014-02-19","2014-02-20","2014-02-21","2014-02-22","2014-02-24","2014-02-25","2014-02-26","2014-02-27","2014-02-28","2014-03-01","2014-03-03","2014-03-04","2014-03-05","2014-03-06","2014-03-07","2014-03-08","2014-03-10","2014-03-11","2014-03-12","2014-03-13","2014-03-14","2014-03-15","2014-03-17","2014-03-18","2014-03-19","2014-03-20","2014-03-21","2014-03-22","2014-03-24","2014-03-25","2014-03-26","2014-03-27","2014-03-28","2014-03-29","2014-03-31","2014-04-01","2014-04-02","2014-04-03","2014-04-04","2014-04-05","2014-04-07","2014-04-08","2014-04-09","2014-04-10","2014-04-11","2014-04-12","2014-04-14","2014-04-15","2014-04-16","2014-04-17","2014-04-18","2014-04-19","2014-04-21","2014-04-22","2014-04-23","2014-04-24","2014-04-25","2014-04-26","2014-04-28","2014-04-29","2014-04-30","2014-05-01","2014-05-02","2014-05-03","2014-05-05","2014-05-06","2014-05-07","2014-05-08","2014-05-09","2014-05-10"]
[1]
[2,null,null,null,"Change Estimate No. 001 / PR 001"]
[3,null,null,null,"Install Vapor Barrier",null,null,"Y",null,null,null,null,"2014-02-05","2014-02-05"]
[4,null,null,null,"Compile and submit CE 001 / PR 001 notice and backup to Owner",null,null,"N/A",null,null,null,null,"2014-02-06","2014-02-14"]
[5,null,null,null,"Owner approval and execution of change order",null,null,"N/A",null,null,null,null,"2014-02-17","2014-02-21"]
[6,null,null,null,"Re-design for PR 001",null,null,"N/A",null,null,null,null,"2014-02-24","2014-03-07"]
[7,null,null,null,"Owner approval of re-design for PR 001",null,null,"N/A",null,null,null,null,"2014-03-10","2014-03-14"]
[8,null,null,null,"Re-permit for PR 001",null,null,"N/A",null,null,null,null,"2014-03-17","2014-03-28"]
[9,null,null,null,"Remove vapor barrier",null,null,"N/A",null,null,null,null,"2014-03-31","2014-04-01"]
[10,null,null,null,"Excavate and re-work underground MEP rough in",null,null,"N ",null,null,null,null,"2014-04-02","2014-04-08"]
[11,null,null,null,"AHJ signoff of underground MEP rough in",null,null,"N/A",null,null,null,null,"2014-04-09","2014-04-11"]
[12,null,null,null,"Backfill MEP",null,null,"Y",null,null,null,null,"2014-04-14","2014-04-16"]
[13,null,null,null,"Re-install vapor barrier",null,null,"N",null,null,null,null,"2014-04-17","2014-04-18"]
[14,null,null,null,"Form and reinforce slab-on-grade",null,null,"N",null,null,null,null,"2014-04-21","2014-04-28"]
[15]
[16]
[43]
[44]
[45]
[46]
[47]
[48]
[49]
[50,null,null,null," ",null,null," ",null,null,null,null," "," "]

{"sheet":"Sheet1","index":1,"n_rows":5,"n_cols":1,"rows_kept":5,"cut":false,"hidden":false,"merged":[]}
["Activites"]
["ConSpan Vault"]
["Contech Storm Pipe"]
["Garage Xcel UG Tie-In"]
["Remove Gas Pump"]