## Summary
| 2014 ASC Competition - Region VII |  | CE NO. | 1
FRESNO, CA
|  |  | Date: | 2014-02-07
ADDITIVE CHANGES
CHANGE ESTIMATE
PROPOSAL SUMMARY
1 | PROJECT ESTIMATE | 99916
2 | GENERAL CONDITIONS | 516163.2
3 | SUBTOTAL ESTIMATE AND G.C.'S |  | 616079.2
4 | CONTRACTOR BONDS @ 1% |  |  | 6160.792
5 | SUBCONTRACT AND SUPPLIER BONDS @ 1.5% |  |  | 9241.188
6 | BUILDERS RISK INSURANCE @ 1% |  |  | 6160.792
7 | GENERAL LIABILITY INSURANCE @ 1% |  |  | 6160.792
8 | PERMITS |  |  | 1000
9 | BIDDING AND CONSTRUCTION RESERVES @ 5% |  |  | 30803.96
10 | SUBTOTAL ALL INDIRECTS AND RESERVES |  | 59527.524
11 | CONTRACTOR'S FEE @ 3% | 2797.7936 | 20268.2017
12 | TOTAL PROPOSED CHANGE ORDER COST |  |  | 695874.9257
SUMMARY
As requested in Proposal Request 001, this change represents an approximate cost impact of changing Building 3 from a standard housing unit to a memory housing unit. Costs include direct cost from subcontractors as well as increased General Conditions cost. General Conditions have increased due to increased schedule duration associated with the delay to housing unit 3.
REFERENCE DOCUMENTS
Proposal Request 001.
Note on F13: Lowery, Nathaniel L.: From GC estimate spreadsheet: Total GC's = $6,667,123/31 months x 2.4 month schedule extension
Note on H25: Lowery, Nathaniel L.: Provided to teams

## HPCC Selfwork (hidden)
ATTACHMENT #1
TO CHANGE ESTIMATE PROPOSAL SUMMARY
| 2014 ASC Competition - Region VII | [7 empty] | CE NO. | 1
FRESNO, CA
[9 empty] | Date: | 2014-02-07
ADDITIVE CHANGES
HPCC SELFWORK PRICING DETAIL
| ITEM | QTY |  | UNIT | MAT'L | UNIT | EQUIP. | UNIT | LABOR | TOTAL
[5 empty] | 0 |  | 0 |  | 0 | 0
| Carpenters | 0 | HRS |  | 0 |  |  | 22 | 0 | 0
| Carpenter Apprentices | 0 | HRS |  | 0 |  |  | 22 | 0 | 0
| Carpenter Foreman | 0 | HRS |  | 0 |  |  | 24 | 0 | 0
| Cement Finisher | 0 | HRS |  | 0 |  |  | 17 | 0 | 0
| Finisher General Foreman | 0 | HRS |  | 0 |  |  | 24 | 0 | 0
| Laborer | 0 | HRS |  | 0 |  |  | 16 | 0 | 0
| Laborer Foreman | 0 | HRS |  | 0 |  |  | 19 | 0 | 0
0
| SUBTOTAL |  |  |  | 0 |  |  |  | 0 | 0
| Foreman/General Foreman (15% of Labor) | [6 empty] | 0.15 | 0 | 0
| Small Tools and Supplies (5% of Labor) | [6 empty] | 0.05 | 0 | 0
| SUBTOTAL |  |  |  | 0 |  |  |  | 0 | 0
| Selfwork Admin & Fee |  |  |  | 0 |  |  |  | 0 | 0
| TOTAL |  |  |  | 0 |  |  |  | 0 | 0

## Sub Cost
ATTACHMENT #1
TO CHANGE ESTIMATE SUMMARY
| 2014 ASC Competition - Region VII |  | CE NO. | 1
FRESNO, CA
|  |  | Date: | 2014-02-07
ADDITIVE CHANGES
Hensel Phelps Estimate
| Trade | Subcontractor / CO # |  | Cost
1 | Earthwork | Big Al's |  | 5760
2 | Concrete | Gray Concrete Co. |  | 1000
3 | Framing | Harly-Faas |  | 4000
4 | Vapor Barrier | Wanda's Waterproofing |  | 16724
5 | Kitchen Equipment | Kamran |  | 15000
6 | Plumbing | Piper's Plumbing |  | 22632
7 | Electrical | Empire Electric |  | 0
8 | Design Services | Joe Architect |  | 34800
9
10
11
12
13
14
15
16
|  | TOTAL SUBCONTRACTOR AND GENERAL CONDITIONS COST |  | 99916