## Staffing from NTP
California Vetrans Home Fresno, CA
STAFFING MATRIX | [30 empty] | Contract Award: | 2014-02-25
Year: | 2014 | [11 empty] | 2015 | [11 empty] | 2016
Month: | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | Staff
Month #: | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | Totals:
Staff Member
Project Manager | [36 empty] | 31 | bar: 2014 MAR to 2016 SEP
Project Superintendent | [36 empty] | 31 | bar: 2014 MAR to 2016 SEP
Project Estimator | [36 empty] | 12 | bar: 2014 FEB to 2015 JAN
Area Superintendent #1 | [36 empty] | 31 | bar: 2014 MAR to 2016 SEP
Area Superintendent #2 | [36 empty] | 24 | bar: 2014 SEP to 2016 AUG
Area Superintendent #3 | [36 empty] | 24 | bar: 2014 SEP to 2016 AUG
Area Superintendent #4 | [36 empty] | 24 | bar: 2014 SEP to 2016 AUG
Area Superintendent #5 | [36 empty] | 24 | bar: 2014 SEP to 2016 AUG
Project Engineer #1 | [36 empty] | 33 | bar: 2014 MAR to 2016 NOV
Office Engineer #1 | [36 empty] | 31 | bar: 2014 MAR to 2016 SEP
Office Engineer #2 | [36 empty] | 24 | bar: 2014 SEP to 2016 AUG
Office Engineer #3 | [36 empty] | 24 | bar: 2014 SEP to 2016 AUG
Office Engineer #4 | [36 empty] | 24 | bar: 2014 SEP to 2016 AUG
Field Engineer #1 | [36 empty] | 26 | bar: 2014 AUG to 2016 SEP
Field Engineer #2 | [36 empty] | 24 | bar: 2014 SEP to 2016 AUG
Field Engineer #3 | [36 empty] | 24 | bar: 2014 SEP to 2016 AUG
Field Engineer #4 | [36 empty] | 24 | bar: 2014 SEP to 2016 AUG
Field Engineer #5 | [36 empty] | 24 | bar: 2014 SEP to 2016 AUG
Field Engineer #6 | [36 empty] | 24 | bar: 2014 SEP to 2016 AUG
Office Manager | [36 empty] | 31 | bar: 2014 MAR to 2016 SEP
Quality Control Eng | [36 empty] | 24 | bar: 2014 SEP to 2016 AUG
Safety Engineer | [36 empty] | 24 | bar: 2014 SEP to 2016 AUG
Intern | [36 empty] | 3 | bar: 2015 JUL to 2015 SEP
Monthly totals: | 0 | 1 | 7 | 7 | 7 | 7 | 7 | 8 | 22 | 22 | 22 | 22 | 22 | 21 | 21 | 21 | 21 | 21 | 22 | 22 | 22 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 7 | 1 | 1 | 0 | 565
Grand Total