## SIPS
UCI Mesa Court Expansion
Short Interval Production Schedule
Residential Towers SIPS
Date |  | INPUT DATES
Week # |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64
Block | AREA
_______ Tower
2nd Floor | East
West
3rd Floor | East
West
4th Floor | East
West
5th Floor | East
West
6th Floor | East
West
_______ Tower
2nd Floor | East
West
3rd Floor | East
West
4th Floor | East
West
5th Floor | East
West
6th Floor | East
West
______ Tower
2nd Floor | East
West
3rd Floor | East
West
4th Floor | East
West
5th Floor | East
West
6th Floor | East
West
SIPS RULES
COMPREHENSIVE INSPECTIONS WITH ALL DISCIPLINES OF ELECTRICAL, MECHANICAL, PLUMBING, FRAMING WILL BE REQUIRED.
CONSTRUCTION SEQUENCING FOR INTERIORS SHALL FOLLOW A SHORT INTERVAL PRODUCTION SCHEDULE (SIPS)
EACH SIPS WEEK HAS ASSIGNED CONSTRUCTION ACTIVITIES THAT ARE REQUIRED TO BE COMPLETED WITH IN THE WEEK SCHEDULED.
NEW SIPS ACTIVITIES WILL MOVE IN EACH MONDAY AND CONCLUDE ON FRIDAY. ALL SIPS ACTIVITIES THAT ARE NOT COMPLETE BY
2PM FRIDAY WILL REQUIRE OVERTIME HOURS AND SATURDAY WORK.
INSPECTIONS FOR WORK INSTALLED ARE CONDUCTED ON FRIDAYS BY HPCC. INCOMPLETE WORK WILL BE TAGGED AND THE
RESPONSIBLE SUB-CONTRACTOR WILL BE NOTIFIED.
ALL TAGGED AND INCOMPLETE WORK WILL BE COMPLETED BY 2PM SATURDAY AFTERNOON.
IT IS THE RESPONSIBILITY OF EACH CONTRACTOR TO MAN THEIR WORK APPROPRIATLEY TO MAINTAIN THE WEEKLY SIPS SCTIVITIES.

## Activities
Use the below activity sets to complete the SIPS schedule on the first tab.
The below activity list is not in the correct sequence for construction. These activities should be rearranged, on this sheet, to the correct order for construction and numbered sequentially 1-27.
Once you reorganize and number the below activity list then input the number and color only in the SIPS tab and complete the SIPS schedule. All towers are to be completed in 45 weeks.
It should be assumed that each activity/activity set below takes (1) week to complete per area of floor per tower. Activities cannot be overlapped during the week. (I.e. you can only have one activity below performed during the week per area of level per tower)
You may have noticed that the schedule with the activities below cannot be completed within 45 weeks total. Combine (2) activities or activity sets [(2) activities only are allowed to be combined)] below into one activity set to complete during the week it lands on the schedule. Use the color black with white lettering to identify the new activity set below and in the SIPS schedule. Be prepared to discuss why your team selected these two activities to combine and how they can be completed at the same time during the week.
Review the problem statement for any additional requirements.
Doors & Hardware / Specialties / Int. Glazing
Electrical Rough In - Walls / One Side @ Ceiling Soffits
Mech / Plumbing Rough In - Walls
OH Waste/ Vent / Duct
Work Completion List
Soffit / Ceiling Framing
Close Wall/Ceiling Inspections / Insulation
Tape and Finish - Final
Waterproofing / Ceramic Tile
Complete Owner/Arch Punchlist
MEP Rough In - Ceilings
OH Mech / Domestic Piping
T-Grid
Final Paint / Clean
Owner/Arch Punchlist
Layout
Tape and Finish - Initial
OH Electrical
Prime & Paint / Waterproofing
MEP Trim / Finishes
OH Sprinkler Piping / Countertop Supports
Complete Work Completion List
Hang Gyp Walls / Ceilings
Risers
Flooring
Casework / Millwork
Wall Framing