## COMBINED
MARRIOTT @ LUHRS |  |  | 2018 | [19 empty] | 2019
|  |  | AUGUST |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  |  | DECEMBER |  |  |  |  | JAUNARY |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  |  | MAY |  |  |  | JUNE |  |  |  | JULY |  |  |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  | DECEMBER
CREW | WORK AREA |  |  | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23
LEVEL 5 | [73 empty] | 29 | 29 | 29 | 30 | 30
LEVEL 6 | [73 empty] | 29 | 29 | 29 | 30 | 30
LEVEL 7 | [73 empty] | 29 | 29 | 29 | 30 | 30
LEVEL 8 | [73 empty] | 29 | 29 | 29 | 30 | 30
LEVEL 9 | [73 empty] | 29 | 29 | 29 | 30 | 30
LEVEL 10 | [73 empty] | 29 | 29 | 29 | 30 | 30
LEVEL 11 | [73 empty] | 29 | 29 | 29 | 30 | 30
LEVEL 12 | [73 empty] | 29 | 29 | 29 | 30 | 30
LEVEL 13 | [73 empty] | 29 | 29 | 29 | 30 | 30
LEVEL 14 | [73 empty] | 29 | 29 | 29 | 30 | 30
LEVEL 15 | [73 empty] | 29 | 29 | 29 | 30 | 30
LEVEL 16 | [73 empty] | 29 | 29 | 29 | 30 | 30
LEVEL 17 | [73 empty] | 29 | 29 | 29 | 30 | 30
LEVEL 18 | [73 empty] | 29 | 29 | 29 | 30 | 30
LEVEL 19 | [73 empty] | 29 | 29 | 29 | 30 | 30
[12 empty] | TC |  | TOUGH CONCRETE | [6 empty] | SE |  | SPARKY ELEC | [6 empty] | RIOP |  | ROLL IT ON PAINTING | [6 empty] | BB |  | BARLOW BUILDERS
[12 empty] | FAL |  | FRAME A LOT, LLC | [6 empty] | GLFC |  | GLAZING FACTORY | [6 empty] | BAS |  | BUILD-A-SHED | [6 empty] | WSS |  | We So Special
[12 empty] | STF |  | SHOWER THE FIRE | [6 empty] | FAL |  | EXTERIOR FRAMING | [6 empty] | TIN |  | TILE IT NOW! | [6 empty] | OWN |  | APPLIANCES
| Legend: |  |  | OCTOBER 22: PXP; NOVEMBER 5: PEX PLUMBING; DECEMBER 24: TIN; JAUNARY 7: TILE IT NOW!; FEBRUARY 25: SIO; MARCH 11: SKIM IT ON; APRIL 29: OWN; MAY 13: OFCI
[12 empty] | SH |  | SPIRAL HVAC | [6 empty] | BINI |  | BATT IT NOW INSULATION! | [6 empty] | KKI |  | Knock Knock Inc. | [6 empty] | HP |  | HENSEL PHELPS
Note: Use these colors and numbers to fill in the SIPs template. Do not change activity numbers or colors. Refer to next sheet for logic and durations. Do not add or remove activities. Do not account for holidays
| SUB | # | SIPS ACTIVITY | SEPTEMBER 17: SUB; OCTOBER 1: #; OCTOBER 15: SIPS ACTIVITY; DECEMBER 3: SUB; DECEMBER 17: #; DECEMBER 31: SIPS ACTIVITY; FEBRUARY 18: SUB; MARCH 4: #; MARCH 18: SIPS ACTIVITY; MAY 6: SUB; MAY 20: #; JUNE 3: SIPS ACTIVITY; AUGUST 5: 8
[53 empty] | 1.) | CONSTRUCTION SEQUENCING SHALL FOLLOW A SHORT INTERVAL PRODUCTION SCHEDULE (SIPS)
| TC | 15 | FORM, AND PLACE DECK | SEPTEMBER 17: STF; OCTOBER 1: 1; OCTOBER 15: FIRE SPRINKLER; DECEMBER 3: GLFC; DECEMBER 17: 9; DECEMBER 31: INSTALL WINDOW FRAMES; FEBRUARY 18: TIN; MARCH 4: 31; MARCH 18: TILE FLOORING; MAY 6: HP; MAY 20: 10; JUNE 3: FINAL CLEAN
| TC |  | VERTICAL CONCRETE | SEPTEMBER 17: MEP; OCTOBER 15: FIRESTOPPING PENET.; DECEMBER 3: GLFC; DECEMBER 31: GLASS INSTALLED
| TC |  | POST TENSIONING | SEPTEMBER 17: SH; OCTOBER 15: SHAFT/CORRIDOR DUCT; DECEMBER 3: GLFC; DECEMBER 31: WINDOW CAULKING; FEBRUARY 18: TIN; MARCH 4: 20; MARCH 18: TILE FLOORING; AUGUST 5: 2.); AUGUST 12: EACH SIPS WEEK HAS ASSIGNED CONSTRUCTION ACTIVITIES THAT ARE REQUIRED TO BE COMPLETED WITH-IN THE WEEK SCHEDULED. NEW SIPS ACTIVITIES WILL MOVE IN EACH MONDAY AND CONCLUDE ON FRIDAY. ALL SIPS ACTIVITIES THAT ARE NOT COMPLETE BY 2PM FRIDAY MAY REQUIRE WEEKEND WORK.
[7 empty] | SH |  |  |  | FCU DUCTING (RI) | [6 empty] | BINI |  |  |  | SPANDREL INSULATION | [6 empty] | KKI |  |  |  | KNOCK DOWN FRAMES (CY) | [6 empty] | HP |  | 16 |  | PUNCHLIST
| HR | 15.1 | FIRST FLOOR SHORING | FEBRUARY 18: KKI; MARCH 18: BARN DOORS (RI)
[7 empty] | FAL |  | 30 |  | FRAME ENTRANCE SOFFIT | [28 empty] | TBD |  | 19 |  | CORRIDOR AND LOBBY WORK
| HR | 15.2 | 100% RE-SHORES / PATCH | SEPTEMBER 17: FAL; OCTOBER 15: FRAME BATHROOM SOFFIT; DECEMBER 3: FAL; DECEMBER 17: R2; DECEMBER 31: FRAME REMAINING WALLS; FEBRUARY 18: RIOP; MARCH 4: 6; MARCH 18: PRIME PAINT
[18 empty] | FAL |  |  |  | REVISE DOOR OPENINGS | [6 empty] | RIOP |  |  |  | 1ST COAT PAINT | [6 empty] | TBD |  | 21 |  | TAB, Cx, TESTING, TCO | [8 empty] | 3.) | SIPS 15 WILL REQUIRE CLOSURE OF THE CORRIDORS AND WILL MINIMIZE ACCESSABLITY INTO THE ROOMS
| HR | 15.3 | 50% RE-SHORES / PATCH | SEPTEMBER 17: FAL; OCTOBER 1: 11; OCTOBER 15: FRAMING/DRYWALL AT FCU; DECEMBER 3: FAL; DECEMBER 31: FRAMING/DRYWALL AT FCUs
[7 empty] | SH |  |  |  | FCU PIPING | [6 empty] | SH |  |  |  | FCU PIPING | [6 empty] | RIOP |  | 14 |  | PAINT HM FRAMES
| HR | 15.4 | STRIP RE-SHORES | SEPTEMBER 17: SH; OCTOBER 15: SET FCU; DECEMBER 3: SE; DECEMBER 31: FA/TELE TESTING; FEBRUARY 18: RIOP; MARCH 18: WALL PAPER; AUGUST 5: 4.); AUGUST 12: INSPECTIONS MUST BE ONGOING AND CONTINUOUS. INCOMPLETE WORK WILL BE TAGGED AND THE RESPONSIBLE SUB-CONTRACTOR WILL BE NOTIFIED.
| HR |  | GRIND AND PATCH | SEPTEMBER 17: SH; OCTOBER 15: RUN THERMOSTAT WIRE
| PXP |  | ROOF DRAINS | SEPTEMBER 17: SH; OCTOBER 15: FINAL FCU CONNECTION; DECEMBER 3: FAL; DECEMBER 17: R3; DECEMBER 31: FRAMING/DRYWALL AT FCUs; FEBRUARY 18: BAS; MARCH 4: 18; MARCH 18: INSTALL SHELF/VANITY (CY)
[18 empty] | SH |  |  |  | FCU PIPING | [6 empty] | BAS |  |  |  | INSTALL KITCHEN/VANITY/ENTRY/VALANCE (RI) | [19 empty] | 5.) | IT IS THE RESPONSIBILITY OF EACH CONTRACTOR TO MAN THEIR WORK APPROPRIATLEY TO MAINTAIN THE WEEKLY SIPS SCTIVITIES.
| FAL | 8 | INTERIOR WALL LAYOUT | SEPTEMBER 17: SE; OCTOBER 1: 12; OCTOBER 15: ELECTRICAL ROUGH-IN; DECEMBER 3: SH; DECEMBER 31: SET FCUs & INSTALL T-STATS
| PXP |  | ROOF DRAINS - FIRESTOP | DECEMBER 3: SE; DECEMBER 31: COMPLETE ELEC ROUGH-IN; FEBRUARY 18: BAS; MARCH 18: OFCI
| SIO |  | FLOOR PREP | SEPTEMBER 17: SE; OCTOBER 1: 2; OCTOBER 15: ELECTRICAL ROUGH-IN; FEBRUARY 18: SE; MARCH 18: TRIM OUT; AUGUST 5: 6.); AUGUST 12: COMPREHENSIVE INSPECTIONS WITH ALL DISCIPLINES OF ELECTRICAL, MECHANICAL, PLUMBING, FRAMING, ETC WILL BE REQUIRED.
| FAL |  | SKIM COAT CEILINGS | SEPTEMBER 17: SE; OCTOBER 15: FIRE ALARM ROUGH-IN; DECEMBER 3: HP; DECEMBER 17: 3; DECEMBER 31: INSPECTIONS
[7 empty] | SE |  |  |  | TELE-COMM ROUGH-IN | [6 empty] | ALL |  |  |  | COMPLETE WALL CLOSE-IN PUNCH LIST ITEMS | [6 empty] | BB |  | 24 |  | INSTALL SHOWER DOORS
| FAL | 7 | WALL FRAMING & CLIPS | SEPTEMBER 17: SE; OCTOBER 15: PULL WIRE; FEBRUARY 18: PXP; MARCH 18: PLUMBING TRIM; AUGUST 5: 7.); AUGUST 12: BE PART OF THE SOLUTION AND NOT PART OF THE PROBLEM
| KKI/FAL |  | HM FRAMES
| FAL |  | 11" UPPER DRYWALL RIPPER | SEPTEMBER 17: FAL; OCTOBER 1: 5; OCTOBER 15: BACKING WITH BATHROOM; DECEMBER 3: FAL; DECEMBER 17: 17; DECEMBER 31: DRYWALL (WALLS/SOFFITS); FEBRUARY 18: RIOP; MARCH 4: 25; MARCH 18: FINAL PAINT
| FAL |  | SHAFT WALL - 3 SIDES | SEPTEMBER 17: FAL; OCTOBER 15: RESILENT CLIPS AT BATHROOM; DECEMBER 3: BINI; DECEMBER 31: INSULATION; FEBRUARY 18: KKI; MARCH 18: INSTALL DOORS / HW; AUGUST 5: 8.); AUGUST 12: BOOTIES MUST BE WORN ONCE CARPET IS INSTALLED
[7 empty] | FAL |  |  |  | DRYWALL AT TUB/SHOWER | [6 empty] | FAL |  |  |  | TAPE, FLOAT, SAND DRYWALL | [6 empty] | RIOP |  |  |  | PAINT DOORS
| FAL | 26 | FIRE TAPE DRYWALL RIPPER | SEPTEMBER 17: FSSW; OCTOBER 15: FIRE CAULK @ TUBS; DECEMBER 3: FAL; DECEMBER 31: CEILING SKIM TOUCH-UP
| FSSW |  | FIRE CAULKING | FEBRUARY 18: TIN; MARCH 4: 23; MARCH 18: INSTALL CARPET
[7 empty] | MPL |  | 28 |  | DELIVER PANS (3 LEVELS) | [6 empty] | BB |  | 4 |  | SHOWER SURROUNDS | [6 empty] | TIN |  |  |  | INSTALL BASE
| PXP | 13 | PLUMBING ROUGH-IN | SEPTEMBER 17: PXP; OCTOBER 15: SET TUBS / SHOWER PANS; DECEMBER 3: FSSW; DECEMBER 31: FIRE CAULKING; FEBRUARY 18: WSS; MARCH 18: TOILET ACCESSORIES