## Sheet1
Activity | Predecessor | Successor | Duration
Shower Surrounds, Fire Caulking | Drywall (Walls/Soffits), Insulation, Tape, Float, Sand Drywall, Ceiling Skim Touch-Up | Tile Flooring | 1 Week
Fire Tape Drywall Ripper, Fire Caulking | Wall Framing & Clips, HM Frames, 11" Upper Drywall Ripper, Shaft Wall - 3 Sides | Plumbing Rough-In | 1 Week
Final Paint, Install Doors / HW, Paint Doors | Install Shower Doors, Plumbing Trim | Install Carpet, Install Base, Toilet Accessories | 1 Week
Corridor and Lobby Work | Punchlist | Tab, Cx, Testing, TCO | 4 Weeks
Fire Sprinkler, Firestopping Penet., Shaft/Corridor Duct, FCU Ducting (RI) | Plumbing Rough-In | Frame Entrance Soffit, Frame Bathroom Soffit | 1 Week
100% Re-Shores / Patch | First Floor Shoring | 50% Re-Shores / Patch | A minimum of 1 week. Additional as needed
Framing/Drywall at FCU, FCU Piping, Set FCU, Run Thermostat Wire, Final FCU Connection | Frame Entrance Soffit, Frame Bathroom Soffit | Electrical Rough-In | 1 Week
Punchlist | Final Clean | Corridor and Lobby Work | 1 Week
Tab, Cx, Testing, TCO | Corridor and Lobby Work |  | 4 Weeks
Electrical Rough-In, Fire Alarm Rough-In, Tele-Comm Rough-In, Pull Wire | Electrical Rough-In | Backing with Bathroom, Resilent Clips at Bathroom, Drywall at Tub/Shower, Fire Caulk @ Tubs | 2 Weeks - Levels 5 through 10 and 1 Week - Levels 11 and Up
Paint HM Frames, Wall Paper | Prime Paint, 1st Coat Paint | Install Shelf/Vanity (CY), Install Kitchen/Vanity/Entry/Valence (RI), OFCI, Trim Out | 1 Week
Form and Place Deck, Vertical Concrete, Post Tensioning |  | First Floor Shoring | 2 Weeks, First Week is forming and reinforcing (post tensioning) and second week is pouring and stripping
Backing with Bathroom, Resilent Clips at Bathroom, Drywall at Tub/Shower, Fire Caulk @ Tubs | Electrical Rough-In, Fire Alarm Rough-In, Tele-Comm Rough-In, Pull Wire | Deliver Pans (3 Levels), Set Tubs / Shower Pans | 2 Weeks
Final Clean | Install Carpet, Install Base, Toilet Accessories | Punchlist | 1 Week
Deliver Pans (3 Levels), Set Tubs / Shower Pans | Backing with Bathroom, Resilent Clips at Bathroom, Drywall at Tub/Shower, Fire Caulk @ Tubs | Install Window Frames, Glass Installed, Window Caulking, Spandrel Insulation | 1 Week
Framing/Drywall at FCUs, FCU Piping, Set FCUs & Install T-Stats, Complete Elec. Rough-In | Frame Remaining Walls, Revise Door Openings, Framing/Drywall at FCUs, FCU Piping, FA/TELE Testing | Inspections, Complete Wall Close-In Punch List Items | 1 Week
Prime Paint, 1st Coat Paint | Tile Flooring, Knock Down Frames (CY), Barn Doors (RI) | Paint HM Frames, Wall Paper | 1 Week
Install Window Frames, Glass Installed, Window Caulking, Spandrel Insulation | Deliver Pans (3 Levels), Set Tubs / Shower Pans | Frame Remaining Walls, Revise Door Openings, Framing/Drywall at FCUs, FCU Piping, FA/TELE Testing | 2 Weeks
Frame Remaining Walls, Revise Door Openings, Framing/Drywall at FCUs, FCU Piping, FA/TELE Testing | Install Window Frames, Glass Installed, Window Caulking, Spandrel Insulation | Framing/Drywall at FCUs, FCU Piping, Set FCUs & Install T-Stats, Complete Elec. Rough-In | 1 Week
Inspections, Complete Wall Close-In Punch List Items | Framing/Drywall at FCUs, FCU Piping, Set FCUs & Install T-Stats, Complete Elec. Rough-In | Drywall (Walls/Soffits), Insulation, Tape, Float, Sand Drywall, Ceiling Skim Touch-Up | 1 Week
Plumbing Rough-In | Fire Tape Drywall Ripper, Fire Caulking | Fire Sprinkler, Firestopping Penet., Shaft/Corridor Duct, FCU Ducting (RI) | 1 Week - Levels 5 through 10, 2 Weeks - Levels 11 and up
Drywall (Walls/Soffits), Insulation, Tape, Float, Sand Drywall, Ceiling Skim Touch-Up | Inspections, Complete Wall Close-In Punch List Items | Shower Surrounds, Fire Caulking | 3 Weeks
Interior Wall Layout, Roof Drains - Firestop, Floor Prep, Skim Coat Ceilings | Strip Re-Shores, Grind and Patch, Roof Drains | Wall Framing & Clips, HM Frames, 11" Upper Drywall Ripper, Shaft Wall - 3 Sides | 1 week
Tile Flooring | Shower Surrounds, Fire Caulking | Tile Flooring, Knock Down Frames (CY), Barn Doors (RI) | 1 Week
Electrical Rough-In | Framing/Drywall at FCU, FCU Piping, Set FCU, Run Thermostat Wire, Final FCU Connection | Electrical Rough-In, Fire Alarm Rough-In, Tele-Comm Rough-In, Pull Wire | 1 Week
50% Re-Shores / Patch | 100% Re-Shores / Patch | Strip Re-Shores, Grind and Patch, Roof Drains | A minimum of 1 week. Additional as needed
Tile Flooring, Knock Down Frames (CY), Barn Doors (RI) | Tile Flooring | Prime Paint, 1st Coat Paint | 2 Weeks
Frame Entrance Soffit, Frame Bathroom Soffit | Fire Sprinkler, Firestopping Penet., Shaft/Corridor Duct, FCU Ducting (RI) | Framing/Drywall at FCU, FCU Piping, Set FCU, Run Thermostat Wire, Final FCU Connection | 1 Week
Install Shelf/Vanity (CY), Install Kitchen/Vanity/Entry/Valence (RI), OFCI, Trim Out | Paint HM Frames, Wall Paper | Install Shower Doors, Plumbing Trim | 2 Weeks
Install Shower Doors, Plumbing Trim | Install Shelf/Vanity (CY), Install Kitchen/Vanity/Entry/Valence (RI), OFCI, Trim Out | Final Paint, Install Doors / HW, Paint Doors | 1 Week
Wall Framing & Clips, HM Frames, 11" Upper Drywall Ripper, Shaft Wall - 3 Sides | Interior Wall Layout, Roof Drains - Firestop, Floor Prep, Skim Coat Ceilings | Fire Tape Drywall Ripper, Fire Caulking | 1 Week
Strip Re-Shores, Grind and Patch, Roof Drains | 50% Re-Shores / Patch | Interior Wall Layout, Roof Drains - Firestop, Floor Prep, Skim Coat Ceilings | A minimum of 1 week. Additional as needed
Install Carpet, Install Base, Toilet Accessories | Final Paint, Install Doors / HW, Paint Doors | Final Clean | 1 Week
First Floor Shoring | Form and Place Deck, Vertical Concrete, Post Tensioning | 100% Re-Shores/Patch | A minimum of 1 week. Additional as needed