## Sheet1
CHANGE ORDER REQUEST
Attention | Project Engineer
SUBJECT: | Field Order Pricing - Luhrs Marriott
DATE: | 2018-02-08
GC REFERENCE No.:
RFI No.:
SKETCHES
DESCRIPTION OF WORK: Added labor, material, and equipment costs to include change from concrete pump to crane and bucket.
Costs include all fabrication and delivery.
Exclusions
To avoid Impact, Please respond by : ASAP
| Position | QUANTITY | UNITS | RATE/U.P. | LABOR(a) | MATERIAL(b) | EQUIP (d) | SUBTOTAL
Labor
Carpenter | General Foreman | 100 | hr | 70.74 | 7074 | 0 | 0 | 7074
Carpenter | Foreman | 400 | hr | 68.77 | 27508 | 0 | 0 | 27508
Carpenter | Journeyman | 600 | hr | 63.78 | 38268 | 0 | 0 | 38268
Labor Subtotal | [7 empty] | 72850
Materials
Formwork |  | 12500 | lnft | 2.56 | 0 | 32000 | 0 | 32000
Small Tools |  | 600 | hr | 9.14 | 0 | 5484 | 0 | 5484
Sales Tax (8.6%) | [7 empty] | 3223.624
Material Subtotal | [7 empty] | 40707.624
Insurance (2%) | [7 empty] | 2271.1525
Bond (2%) | [7 empty] | 2271.1525
Subtotal | [7 empty] | 4542.305
Total fees on subcontracted work (5%) | [7 empty] | 0
Total Overhead and Profit (15%) | [7 empty] | 17714.9893
Total | [7 empty] | 135814.9183
Stand It Tall
ABC WATER STREET, WATER | [6 empty] | __________________________
PROJECT MANAGER
Subcontractor License No. :XYZXYZ | [6 empty] | This quote is valid for 30 days
Stand it Tall