## Sheet1
CHANGE ORDER REQUEST
DESCRIPTION OF WORK: Added labor, material, and equipment costs to include change from concrete pump to crane and bucket.
Costs include all fabrication and delivery.
Exclusions
To avoid Impact, Please respond by : ASAP
| Position | QUANTITY | UNITS | RATE/U.P. | LABOR(a) | MATERIAL(b) | EQUIP (d) | SUBTOTAL
Labor
Finisher | General Foreman | 0 | hr | 66.76 | 0 | 0 | 0 | 0
Finisher | Foreman | 100 | hr | 62.65 | 6265 | 0 | 0 | 6265
Finisher | Journeyman | 140 | hr | 60.49 | 8468.6 | 0 | 0 | 8468.6
Labor Subtotal | [7 empty] | 14733.6
Material - None |  | 0 |  | 0 | 0 | 0 | 0 | 0
Material Subtotal |  | 0 |  | 0 | 0 | 0 | 0 | 0
Subcontractor Rental
Crane Rental |  | 4 | mo | 14050 | 0 | 56200 | 0 | 56200
Bucket Rental |  | 700 | hr | 7.75 | 0 | 5425 | 0 | 5425
Concrete Pump Rental |  | -24 | days | 1800 | 0 | 0 | -43200 | -43200
Equipment Subtotal |  | 0 | [5 empty] | 18425
Subcontractor Overhead and Profit (5%) | [7 empty] | 921.25
Bonds and Insurance (2%) | [7 empty] | 681.597
Total Overhead and Profit (15%) | [7 empty] | 5214.2171
Total | [7 empty] | 38372.817
__________________________
PROJECT MANAGER
This quote is valid for 30 days
Cola Concrete