## OMFE Staffing Plan 3.1a
OPERATIONS & MAINTENANCE FACILITY EAST
| 2020 |  |  | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | Staff Totals (Man Months)
Month: | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
Month #: | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51
Staff Member
Project Manager | 2020 OCT: 0.5; 2020 NOV: 0.5; 2020 DEC: 1; 2021 JAN: 1; 2021 FEB: 1; 2021 MAR: 1; 2021 APR: 1; 2021 MAY: 1; 2021 JUN: 1; 2021 JUL: 1; 2021 AUG: 1; 2021 SEP: 1; 2021 OCT: 1; 2021 NOV: 1; 2021 DEC: 1; 2022 JAN: 1; 2022 FEB: 1; 2022 MAR: 1; 2022 APR: 1; 2022 MAY: 1; 2022 JUN: 1; 2022 JUL: 1; 2022 AUG: 1; 2022 SEP: 1; 2022 OCT: 1; 2022 NOV: 1 | 25
Project Manager | [51 empty] | 41 | bar: 2021 JUN to 2024 OCT
Project Superintendent | [51 empty] | 40 | bar: 2021 FEB to 2024 MAY
Project Superintendent | [51 empty] | 34 | bar: 2022 JAN to 2024 OCT
Area Superintendent 1 | [51 empty] | 30 | bar: 2021 FEB to 2023 JUL
Area Superintendent 2 | [51 empty] | 40 | bar: 2021 FEB to 2024 MAY
Area Superintendent 3 | [51 empty] | 28 | bar: 2022 JUL to 2024 OCT
Area Superintendent 4 | [51 empty] | 27 | bar: 2022 JUL to 2024 SEP
Project Engineer 1 | [51 empty] | 45 | bar: 2021 FEB to 2024 OCT
Project Engineer 2 | [51 empty] | 44 | bar: 2021 FEB to 2024 SEP
Project Engineer 3 | [51 empty] | 43 | bar: 2021 APR to 2024 OCT
Office Engineer 1 | [51 empty] | 44 | bar: 2021 FEB to 2024 SEP
Office Engineer 2 | [51 empty] | 26 | bar: 2021 FEB to 2023 MAR
Office Engineer 3 | [51 empty] | 34 | bar: 2022 JAN to 2024 OCT
Office Engineer 4 | [51 empty] | 41 | bar: 2021 JUN to 2024 OCT
Field Engineer 1 | [51 empty] | 45 | bar: 2021 FEB to 2024 OCT
Field Engineer 2 | [51 empty] | 20 | bar: 2021 FEB to 2022 SEP
Field Engineer 3 | [51 empty] | 33 | bar: 2021 JUN to 2024 FEB
Field Engineer 4 | [51 empty] | 41 | bar: 2021 JUN to 2024 OCT
Field Engineer 5 | [51 empty] | 41 | bar: 2021 JUN to 2024 OCT
QC Manager | [51 empty] | 45 | bar: 2021 FEB to 2024 OCT
QC Engineer | [51 empty] | 45 | bar: 2021 FEB to 2024 OCT
VDC Manager | [51 empty] | 40 | bar: 2021 FEB to 2024 MAY
Safety Manager | [51 empty] | 33 | bar: 2022 JAN to 2024 SEP
Safety Engineer | [51 empty] | 44 | bar: 2021 FEB to 2024 SEP
Intern (Hourly) | 2021 JUN: 3; 2021 JUL: 3; 2021 AUG: 3; 2021 SEP: 3; 2022 JUN: 3; 2022 JUL: 3; 2022 AUG: 3; 2022 SEP: 3; 2023 JUN: 3; 2023 JUL: 3; 2023 AUG: 3; 2023 SEP: 3; 2024 JUN: 3; 2024 JUL: 3; 2024 AUG: 3; 2024 SEP: 3 | 48
General Foreman | [51 empty] | 30 | bar: 2021 MAR to 2023 AUG
Office Manager (Hourly) | [51 empty] | 45 | bar: 2021 FEB to 2024 OCT
1052