## OMFE GC ESTIMATE
X.3.4 OMFE GENERAL CONDITIONS ESTIMATE
|  |  | Labor |  | Material |  | Equip/Subs
Item | QTY | UNIT | $/UNIT | AMT | $/UNIT | AMT | $/UNIT | AMT | Total
SUPERVISION
Project Manager |  | MO | 14000 | 0 |  |  |  |  | 0
Project Superintendent |  | MO | 14000 | 0 |  |  |  |  | 0
Project Engineer |  | MO | 11500 | 0 |  |  |  |  | 0
Office Engineer |  | MO | 10000 | 0 |  |  |  |  | 0
QC Engineer |  | MO | 10000 | 0 |  |  |  |  | 0
QC Manager |  | MO | 12500 | 0 |  |  |  |  | 0
BIM Manager |  | MO | 11500 | 0 |  |  |  |  | 0
Office Manager |  | MO | 6800 | 0 |  |  |  |  | 0
Travel Expenses | 45 | MO |  |  | 3000 | 135000 |  |  | 135000
Moving & Relocation | 8 | LSUM |  |  | 2500 | 20000 |  |  | 20000
Intern Moving |  | EA |  |  | 1000 | 0 |  |  | 0
Total |  |  |  | 0 |  | 155000 |  | 0 | 155000
ENGINEERING & SURVEY WORK
Area Superintendent |  | MO | 12500 | 0 |  |  |  |  | 0
Field Engineer |  | MO | 9500 | 0 |  |  |  |  | 0
Safety Manager |  | MO | 12500 | 0 |  |  |  |  | 0
Safety Engineer |  | MO | 9500 | 0 |  |  |  |  | 0
General Foreman |  | MO | 11000 | 0 |  |  |  |  | 0
Intern |  | MO | 2600 | 0 |  |  |  |  | 0
Intern Housing (Up to 3 Bedrooms) |  | MO |  |  |  |  | 3400 | 0 | 0
Field Engineer Equipment |  | MO |  |  | 100 | 0 | 1000 | 0 | 0
Professional Surveyor | 1 | LSUM |  |  |  |  | 75000 | 75000 | 75000
Print Drawings | 1 | LSUM |  |  | 5000 | 5000 |  |  | 5000
BIM Support | 40 | MO |  |  | 7500 | 300000 |  |  | 300000
Total |  |  |  | 0 |  | 305000 |  | 75000 | 380000
SAFETY
Drug Testing | 150 | EA |  |  | 400 | 60000 |  |  | 60000
Safety Incentives | 45 | MO |  |  | 200 | 9000 |  |  | 9000
Employee Training | 45 | MO |  |  | 250 | 11250 | 275 | 12375 | 23625
First Aid Supplies | 1 | LS |  |  | 2500 | 2500 |  |  | 2500
Fire Extinguishers | 250 | EA | 25 | 6250 | 50 | 12500 |  |  | 18750
Heat Stress/Lunch Tent | 1 | LS |  |  | 5000 | 5000 |  |  | 5000
Lunch Area Supplies/Maintenance | 45 | MO | 1000 | 45000 |  |  |  |  | 45000
Total |  |  |  | 51250 |  | 100250 |  | 12375 | 163875
TEMP FACILITIES
Office Trailer |  | MO |  |  |  |  | 15000 | 0 | 0
Office Trailer - Set Up/Removal | 1 | EA |  |  |  |  | 35000 | 35000 | 35000
Janitorial Service for Office Space |  | MO |  |  |  |  | 1500 | 0 | 0
Temp Toilets |  | MO |  |  |  |  | 2000 | 0 | 0
Wash Stations |  | MO |  |  |  |  | 500 | 0 | 0
Professional Photos | 1 | LSUM |  |  | 5000 | 5000 |  |  | 5000
Bulletin Boards | 1 | EA |  |  | 4500 | 4500 |  |  | 4500
Project Sign | 1 | EA |  |  | 800 | 800 |  |  | 800
Office Furniture | 1 | LSUM |  |  | 25000 | 25000 |  |  | 25000
Office Supplies |  | MO |  |  | 600 | 0 |  |  | 0
Office Equipment |  | MO |  |  | 3000 | 0 | 700 | 0 | 0
Certified Payroll Reporting |  | MO |  |  |  |  | 1100 | 0 | 0
Computers |  | EA |  |  | 3000 | 0 |  |  | 0
Printers/Plotters |  | MO |  |  | 5600 | 0 |  |  | 0
Postage & Shipping |  | MO |  |  | 700 | 0 |  |  | 0
Telephone & Internet Service Install | 1 | LSUM |  |  |  |  | 15000 | 15000 | 15000
Telephone & Internet Rental |  | MO |  |  |  |  | 1800 | 0 | 0
Temp Fence | 4000 | LF |  |  |  |  | 25 | 100000 | 100000
Relocate Temp Fence | 4 | EA |  |  |  |  | 2500 | 10000 | 10000
SWPPP Setup | 1 | LSUM |  |  |  |  | 5000 | 5000 | 5000
SWPPP Maintenance - 20 hrs/month | 45 | MO | 3500 | 157500 |  |  |  |  | 157500
Dust Control - 20 hrs/month | 39 | MO | 2500 | 97500 |  |  |  |  | 97500
Drinking Water Service | 45 | MO |  |  | 50 | 2250 |  |  | 2250
Ice, Jugs, Cups | 43 | MO |  |  | 200 | 8600 |  |  | 8600
Office Coffee & Cups | 45 | MO |  |  | 500 | 22500 |  |  | 22500
Temp Asphalt Parking Area | 1 | LSUM |  |  |  |  | 40000 | 40000 | 40000
Street Sweeper | 192 | DAY |  |  |  |  | 500 | 96000 | 96000
Temp Power & Lights Set Up | 1 | LSUM |  |  |  |  | 30000 | 30000 | 30000
Temp Power & Lights Maintenance |  | MO |  |  |  |  | 3000 | 0 | 0
Temporary Water / Utilities |  | MO |  |  |  |  | 1000 | 0 | 0
Total |  |  |  | 255000 |  | 68650 |  | 331000 | 654650
BUILDING SERVICES
Weekly Cleanup (2 man days/wk) | 192 | WK | 1800 | 345600 | 100 | 19200 |  |  | 364800
Dumpster Rental - 40 CUYD | 400 | PULL |  |  |  |  | 500 | 200000 | 200000
Final Clean-Up - BLDG | 270000 | SF |  |  |  |  | 0.6 | 162000 | 162000
Final Clean-Up - SITE | 23 | ACRE |  |  |  |  | 1500 | 34500 | 34500
Total |  |  |  | 345600 |  | 19200 |  | 396500 | 761300
FORKLIFT, MAJOR EQUIPMENT & TOOLS
Gradall - 6000# Forklift (1/2 time operation) |  | MO | 5500 | 0 | 1000 | 0 | 2200 | 0 | 0
Water Truck 2500 GAL |  | MO |  |  | 750 | 0 | 2000 | 0 | 0
Generator Unit Rental | 8 | MO |  |  | 400 | 3200 | 1500 | 12000 | 15200
250 CFM Compressor | 25 | MO |  |  | 500 | 12500 | 1300 | 32500 | 45000
Misc. Power Equipment | 1 | LSUM |  |  | 20000 | 20000 |  |  | 20000
Small Tools | 1 | LSUM |  |  | 50000 | 50000 |  |  | 50000
Repairs & Maintenance | 1 | LSUM |  |  |  |  | 20000 | 20000 | 20000
Total |  |  |  | 0 |  | 85700 |  | 64500 | 150200
TRANSPORTATION
Pickup (PS, AS, GF) |  | MO |  |  |  |  | 625 | 0 | 0
Sedan (PM, QCM, SM, VDCM) |  | MO |  |  |  |  | 625 | 0 | 0
FE Carts | 90 | MO |  |  |  |  | 700 | 63000 | 63000
Vehicle Fuel | 45 | MO |  |  | 800 | 36000 |  |  | 36000
Vehicle Maintenance | 45 | MO |  |  | 200 | 9000 |  |  | 9000
Total |  |  |  | 0 |  | 45000 |  | 63000 | 108000
SUMMARY
SUPERVISION |  | LSUM |  | 0 |  | 155000 |  | 0 | 155000
ENGINEERING & SURVEY WORK |  | LSUM |  | 0 |  | 305000 |  | 75000 | 380000
SAFETY |  | LSUM |  | 51250 |  | 100250 |  | 12375 | 163875
TEMP FACILITIES |  | LSUM |  | 255000 |  | 68650 |  | 331000 | 654650
BUILDING SERVICES |  | LSUM |  | 345600 |  | 19200 |  | 396500 | 761300
FORKLIFT, MAJOR EQ, & TOOLS |  | LSUM |  | 0 |  | 85700 |  | 64500 | 150200
TRANSPORTATION |  | LSUM |  | 0 |  | 45000 |  | 63000 | 108000
SALES TAX ON MATERIAL | 10.1% | PCT |  |  | 778800 | 78658.8 |  |  | 78658.8
TOTAL |  |  |  | 651850 |  | 857458.8 |  | 942375 | 2451683.8
[7 empty] | Check: | 2451683.8 | Good