## DAY 2
Operations and Maintenance Facility East
Financial Status Report
Updated: | 2021-01-29 11:07
Estimate Summary | [6 empty] | Total
A | B | C |  | D | E | F | G
DIV | Description | Design Development Budget |  | Subcontractor | Final Cost after buyout complete |  | Projected Gains / Losses
180000
|  | $/SF | Amount | Name | $/SF | Amount | Amount
DESIGN
0 | Site Survey, Geotechnical Report | 4.1667 | 750000 | Hensel Phelps | 4.1667 | 750000 | 0
0 | Schematic Design Development | 26.3889 | 4750000 | Hensel Phelps | 26.3889 | 4750000 | 0
0 | Design Development | 26.3222 | 4738000 | Hensel Phelps | 26.3222 | 4738000 | 0
0 | Construction Documents | 26.5 | 4770000 | Hensel Phelps | 26.5 | 4770000 | 0
0 | Construction Administration | 6.9444 | 1250000 | Hensel Phelps | 6.9444 | 1250000 | 0
| Subtotal - DESIGN | 90.3222 | 16258000 |  | 90.3222 | 16258000 | 0
PRECONSTRUCTION SERVICES
0 | Schedule Development | 0.50667 | 91200 | Hensel Phelps | 0.50667 | 91200 | 0
0 | Estimate Development | 0.59556 | 107200 | Hensel Phelps | 0.59556 | 107200 | 0
0 | Pre-Con General Conditions | 0.27778 | 50000 | Hensel Phelps | 0.27778 | 50000 | 0
| Subtotal - PRE CON | 1.38 | 248400 |  | 1.38 | 248400 | 0
GC
1 | General Conditions | 0 | 0 | Hensel Phelps |  |  | 0
| Subtotal - GC | 0 | 0 |  | 0 | 0 | 0
BUILDING & SITE
2 | Selective Demolition | 1.1013 | 198240 | Demo Bob | 1.0111 | 182000 | 16240
2 | ATC - 1 (KING County Sewer Relocation) | 0 | 0 | HP ATC -1 | 0 | 0 | 0
2 | ATC - 2 (King County Side Sewer) | 0 | 0 | HP ATC -2 | 0 | 0 | 0
2 | ATC - 3 (TOD Phase 2 Shear Wall) | 0 | 0 | HP ATC -3 | 0 | 0 | 0
03 | Concrete - MOW | 0 | 0 | Hensel Phelps | 0 | 0 | 0
03 | Reinforcing - MOW | 0.97222 | 175000 | Hensel Phelps |  | 150000 | 25000
03 | Concrete - OMF | 9.7222 | 1750000 | Hensel Phelps | 6.9444 | 1250000 | 500000
03 | Reinforcing - OMF | 4.1667 | 750000 | Hensel Phelps |  | 625000 | 125000
4 | Concrete Masonry (CMU) | 7.5 | 1350000 | CMU GUY | 6.3889 | 1150000 | 200000
03B | Concrete Paving
3 | Concrete Placement & Finising | 0 | 0
3 | Concrete Reinforcement | 0 | 0
3 | Concrete Materials | 0 | 0
3 | Concrete Formwork | 0 | 0
5 | STRUCTURAL STEEL | 29.9307 | 5387520 | Perfection Erection | 30 | 5400000 | -12480
5 | Miscellaneous Metals & STAIRS | 18.5556 | 3340000 |  |  |  | 3340000
7 | Roofing | 4.1944 | 755000 | No Drips Roofing | 4.9722 | 895000 | -140000
7 | EXTERIOR - METAL PANELS - MOW | 0 | 0 | EXTERIORS R US | 0 | 0 | 0
7 | EXTERIOR - METAL PANELS - OMF | 21.4 | 3852000 | EXTERIORS R US | 21.1111 | 3800000 | 52000
8 | Doors, Frames, Hardware - MOW | 21.4 | 3852000 | Door guy | 21.4 | 3852000 | 0
8 | Doors, Frames, Hardware - OMF | 2.2222 | 400000 | Door guy | 2.0278 | 365000 | 35000
8 | Interior Glazing - MOW & OMF | 6.7778 | 1220000 |  |  |  | 1220000
8 | Drywall / Framing- MOW | 0 | 0 | DRYWALL GUY | 0 | 0 | 0
8 | Drywall / Framing - OMF | 9.7222 | 1750000 | DRYWALL GUY | 9.7222 | 1750000 | 0
9 | Tile | 1.8976 | 341565 | Stone Hard | 1.8976 | 341565 | 0
9 | Acoustical Ceiling | 5.5556 | 1000000 | Grid Guy | 5.5556 | 1000000 | 0
9 | Carpet, Resilient, RTF | 5.7918 | 1042528 | Christian Brothers | 5.7918 | 1042528 | 0
9 | Floor Leveling Allowance | 0.41667 | 75000 | Christian Brothers | 0.41667 | 75000 | 0
9 | Paint & Wall Covering | 6.6667 | 1200000 | Desert Streams, Inc. | 7.5 | 1350000 | -150000
9 | Final Cleaning | 0.915 | 164700 | Mr. Belvedere | 0.915 | 164700 | 0
10 | Signage - Interior | 0.13889 | 25000 | Marco Polo Signs | 0.13889 | 25000 | 0
10 | Signage - Exterior | 0.41667 | 75000 | Marco Polo Signs | 0.5 | 90000 | -15000
10 | Casework & Solid Surface Countertop | 0.77778 | 140000 | Counter Dude | 0.77778 | 140000 | 0
10 | Lockers ( Metal & Plastic) | 0.47222 | 85000 | Lockers R Us | 0.48889 | 88000 | -3000
10 | Racking & Shelving | 1.1111 | 200000 | Racks and All | 1.4167 | 255000 | -55000
10 | Toilet and Bathroom Accessories | 0.36111 | 65000 | Accessories We R | 0.36111 | 65000 | 0
10 | Toilet Partitions | 0.61111 | 110000 | Partition Lady | 0.61111 | 110000 | 0
11 | Whiting - Car Host, Truck Hoist & Turntables | 11.1111 | 2000000 | train lift guy | 12.5 | 2250000 | -250000
11 | Wheel Lathe Equipment | 11.6667 | 2100000 | Wheel truing Dude | 11.6667 | 2100000 | 0
11 | Sanding Equipment | 5.0833 | 915000 |  |  |  | 915000
11 | Train Wash Equipment | 6.8611 | 1235000 |  |  |  | 1235000
12 | Window Shades | 0.17778 | 32000 | Peak-A-Boo Shades | 0.16389 | 29500 | 2500
14 | Elevator | 0.87778 | 158000 | That'll Be Extra, Inc. | 0.87778 | 158000 | 0
21 | Fire Protection | 2.6333 | 474000 | A-1 Steak Sauce | 2.6333 | 474000 | 0
22 | Plumbing | 47.2222 | 8500000 | Mario Bros. Plumping | 48.6111 | 8750000 | -250000
23 | HVAC | 92.0833 | 16575000 | Tin Knockers & Assoc. | 91.6667 | 16500000 | 75000
26 | Electrical & Low Voltage Infrastructure | 250 | 45000000 | Cash Valley Electric | 252.7778 | 45500000 | -500000
26 | Temp Lighting Allowance | 0.55556 | 100000 | Cash Valley Electric | 0.55556 | 100000 | 0
31 | Site Work - Paving | 8.3333 | 1500000 | Landscapes R Us | 6.9444 | 1250000 | 250000
32 | Site Modifications | 0.83333 | 150000 | METAL WORKS | 0.83333 | 150000 | 0
33 | Site Utilities | 5.5556 | 1000000 | Bali Construction | 5.5556 | 1000000 | 0
34 | Track | 266.6667 | 48000000 | RAILCORP | 269.7222 | 48550000 | -550000
| Subtotal - BUILDING & SITE | 872.4586 | 157042553 |  | 838.7627 | 150977293 | 6615260
PERMITS & FEES
90 | Plan Check and Permit Fees | 4.72 | 850000 | Owner | 4.7222 | 850000 | 0
90 | Encroachment Permit | 2.34 | 420615 | Owner | 2.3367 | 420615 | 0
| Subtotal - PERMITS | 7.059 | 1270615 | - | 7.059 | 1270615 | 0
| CONTINGENCY / RESERVES | %
90 | Design | 705.9% | 1270615 | Hensel Phelps |  | 0 | 1270615
90 | Buyout | % | 1270615 | Hensel Phelps |  | 0 | 1270615
90 | Construction | 0% | 1270615 | Hensel Phelps |  | 0 | 1270615
| Subtotal - CONTINGENCY | 21.1769 | 3811845 | - | 0 | 0 | 3811845
| INSURANCE & BONDS | %
90 | Builder's Risk | 0.5% | 810625.065 | Owner | 0.5% | 761239.54 | 49385.525
90 | GL Insurance | 0.53% | 859262.5689 | Hensel Phelps | 0.53% | 806913.9124 | 52348.6565
90 | Bond | 0.62% | 1005175.0806 | Hensel Phelps | 0.62% | 943937.0296 | 61238.051
| Subtotal - BOND & INSURANCE | 14.8615 | 2675062.7145 | - | 13.9561 | 2512090.482 | 162972.2325
| FEES | %
90 | Contractor's Fee |  | 0 | Hensel Phelps |  | 0 | 0
| Subtotal - FEES | 0 | 0 | - | 0 | 0 | 0
| TOTAL CONSTRUCTION COST | 1007.2582 | 181306475.7145 | - | 951.48 | 171266398.482 | 10590077.2325