## RFI
ASC Competition |  | REQUEST FOR INFORMATION |  |  |  | R.F.I.. NO:
Commercial, Region 7
|  | FOR |  |  |  |  | ISSUING SCHOOL:
PHX Sky Train - Stage 2
|  | SHEETS: | DETAILS / SECTIONS: |  | SPECIFICATIONS REF:
|  | Multiple | Multiple |  | 05 12 00
TITLE OR SECTION OF WORK:
RCC Structural Steel Fabrication Clarification
| PERTINENT PROBLEM SECTION: |  |  | ISSUED BY: | 2022-02-10
|  |  |  | DATE: | 2022-02-10
WRITTEN DESCRIPTION OF PROBLEM - ATTACH SKETCHES AS REQUIRED:
The structural tube steel beams were fabricated cold rolled per the specification but collapsed and failed during the testing process. Please advise if heat induction bending is an acceptable alternate fabrication method for the tube steel beams. Do note heat induction bending and follow-up testing will add 2.5 months to the structural steel delivery date.
A/E RESPONSE:
Heat induction bending is acceptable at no additional cost and/or schedule impact. Ensure structural steel testing after heat induction is completed. The structural steel delivery date has been delayed due to testing complications. Please include this delay in the schedule and evaluate if the substantial completion date can still be met. If not, please provide a proposed requested time extension and justification for the additional time. In addition, liquidated damages are $1,500/day. To avoid paying liquidated damages, please justify if the delay costs are compensable.
| BY: Chester McChesney | [5 empty] | DATE: | 2022-02-10
DISTRIBUTION: