## Tab A (2)
Financial Status Report
School / Project Manager:
|  |  |  | Date: | 2022-02-10
Column A | Column B | Column C | Column D | Column E | Column F | Column G
Cost | [5 empty] | Gain or
Control # | Description | GMP Estimate |  | GMP Proposal |  | (Loss)
Division 2
0230000 | Demo Earthwork | 250000 |  | 260000
0201200 | Micropiles | 150000 |  | 110000
0202300 | RCC Select Demolition | 200000 |  | 200000
0221000 | Site Concrete and Paving | 280000 |  | 280000
0221100 | Asphalt and Striping | 200000 |  | 200000
0221200 | RCC Sitework | 1100000 |  | 1100000
0241100 | Drilled Shafts | 750000 |  | 750000
0277000 | Site Concrete | 300000 |  | 300000
0291000 | Landscaping | 2500000 |  | 2500000
0204200 | Fiber Duct Bank | 700000 |  | 700000
| Subtotal |  | 6430000 |  | 6400000 | 30000
Division 3
0301000 | Hensel Phelps Self Perform Concrete | 7500000
0300100 | Structural Concrete & Formwork | 4000000 |  | 3800000
0300200 | Reinforcing | 2100000 |  | 2400000
| Subtotal |  | 13600000 |  | 6200000 | 7400000
Division 4
0402100 | Masonry | 1100000 |  | 1100000
| Subtotal |  | 1100000 |  | 1100000 | 0
Division 5
0503100 | Miscellaneous Steel | 400000 |  | 390000
0505100 | Structural Steel | 5000000 |  | 5000000
0505105 | Cranes for Steel | 250000 |  | 260000
0552200 | Miscellaneous Metals | 800000 |  | 750000
0505200 | Metal Stud Framing | 550000 |  | 550000
| Subtotal |  | 7000000 |  | 6950000 | 50000
Division 7
0701100 | Metal Panels | 800000
0741000 | Specialty Metals | 300000 |  | 300000
0751000 | Roofing | 45000
0781000 | Applied Fireproofing | 300000 |  | 300000
0792000 | Caulking | 50000 |  | 50000
0792100 | Fire Caulking | 15000 |  | 15000
0796100 | Joint Sealants and Coatings (Expansion Joints) | 200000 |  | 200000
| Subtotal |  | 1710000 |  | 865000 | 845000
Division 8
0811000 | Doors, Frames, and Hardware | 500000 |  | 500000
0880000 | Curtain Wall | 1300000
| Subtotal |  | 1800000 |  | 500000 | 1300000
Division 9
0903200 | Ceramic Tile | 50000 |  | 50000
0904100 | Painting | 300000 |  | 300000
0905100 | Polished Concrete | 11000 |  | 11000
0905110 | Epoxy Flooring | 55000 |  | 55000
0905200 | Acoustical Ceiling Systems | 200000 |  | 175000
0905300 | RCC Terrazzo | 500000 |  | 550000
| Subtotal |  | 1116000 |  | 1141000 | -25000
Division 10
1003100 | Partitions and Accessories | 25000 |  | 25000
1010100 | Building Signage | 400000 |  | 400000
| Subtotal |  | 425000 |  | 425000 | 0
Division 12
1248100 | Entrance Floor Mats & Frames | 10000 |  | 10000
| Subtotal |  | 10000 |  | 10000 | 0
Division 13
1305101 | SCADA | 400000 |  | 400000
| Subtotal |  | 400000 |  | 400000 | 0
Division 15
1500100 | Mechanical Systems | 1200000 |  | 1200000
1500500 | Plumbing | 500000 |  | 500000
1530000 | Fire Protection | 300000 |  | 300000
| Subtotal |  | 2000000 |  | 2000000 | 0
Division 16
1600200 | Fiber Duct Bank | 650000 |  | 650000
1600100 | Electrical | 5000000 |  | 5000000
1604100 | Primary Power | 3000000 |  | 3000000
| Subtotal |  | 8650000 |  | 8650000 | 0
Misc. Items
1800100 | Mock Ups | 500000 |  | 500000
| Subtotal |  | 500000 |  | 500000 | 0
COW | Cost of the Work
| Subtotal |  | 44741000 |  | 35141000
Allowances
1 | Site Concrete Material Escalation | 75000 |  | 75000
2 | IT Systems Allowance | 1650000 |  | 1650000
3 | Building Specialties and Millwork | 15000 |  | 15000
4 | Paving Rehabilition at West Economy Lot | 150000 |  | 150000
5 | Rental Car Center Art Wall | 1575000
| Subtotal |  | 3465000 |  | 1890000 | 1575000
General Requirements
GR | General Requirements | 600000 |  | 600000
| Subtotal |  | 600000 |  | 600000 | 0
Contingency & Reserves
CCONT | Contractor Contingency | 2000000
OCONT | Owner Contingency | 1500000 |  | 1000000
| Subtotal |  | 3500000 |  | 1000000 | 2500000
General Conditions
GC | General Conditions | 7000000
| Subtotal |  | 7000000 |  | 0 | --
[5 empty] | Percent Purchased: | #REF!
[5 empty] | Percent Gain/(Loss): | #REF!

## Tab B (2)
Contingency Report
School / Project Manager:
|  |  |  | Date: | 2022-02-10
|  | CMAR Contingency |  | Design Completion |  | Escalation Contingency
| Cost of Work | % | Value | % | Value | % | Value
Demo Earthwork | 260000 |  | 0 | 0% | - | 0% | -
Micropiles | 110000 |  | 0 | 0% | - | 0% | -
RCC Select Demolition | 200000 |  | 0 | 0% | - | 0% | -
Site Concrete and Paving | 280000 |  | 0 | 0% | - | 0% | -
Asphalt and Striping | 200000 |  | 0 | 0% | - | 0% | -
RCC Sitework | 1100000 |  | 0 | 0% | - | 0% | -
Drilled Shafts | 750000 |  | 0 | 0% | - | 0% | -
Site Concrete | 300000 |  | 0 | 0% | - | 0% | -
Landscaping | 2500000 |  | 0 | 0% | - | 0% | -
Fiber Duct Bank | 700000 |  | 0 | 0% | - | 0% | -
Hensel Phelps Self Perform Concrete |  |  | 0 | 0% | - | 0% | -
Structural Concrete & Formwork | 3800000 |  | 0 | 0% | - | 0% | -
Reinforcing | 2400000 |  | 0 | 0% | - | 0% | -
Masonry | 1100000 |  | 0 | 0% | - | 0% | -
Miscellaneous Steel | 390000 |  | 0 | 0% | - | 0% | -
Structural Steel | 5000000 |  | 0 | 0% | - | 0% | -
Cranes for Steel | 260000 |  | 0 | 0% | - | 0% | -
Miscellaneous Metals | 750000 |  | 0 | 0% | - | 0% | -
Metal Stud Framing | 550000 |  | 0 | 0% | - | 0% | -
Metal Panels |  |  | 0 | 0% | - | 0% | -
Specialty Metals | 300000 |  | 0 | 0% | - | 0% | -
Roofing |  |  | 0 | 0% | - | 0% | -
Applied Fireproofing | 300000 |  | 0 | 0% | - | 0% | -
Caulking | 50000 |  | 0 | 0% | - | 0% | -
Fire Caulking | 15000 |  | 0 | 0% | - | 0% | -
Joint Sealants and Coatings (Expansion Joints) | 200000 |  | 0 | 0% | - | 0% | -
Doors, Frames, and Hardware | 500000 |  | 0 | 0% | - | 0% | -
Curtain Wall |  |  | 0 | 0% | - | 0% | -
Ceramic Tile | 50000 |  | 0 | 0% | - | 0% | -
Painting | 300000 |  | 0 | 0% | - | 0% | -
Polished Concrete | 11000 |  | 0 | 0% | - | 0% | -
Epoxy Flooring | 55000 |  | 0 | 0% | - | 0% | -
Acoustical Ceiling Systems | 175000 |  | 0 | 0% | - | 0% | -
RCC Terrazzo | 550000 |  | 0 | 0% | - | 0% | -
Partitions and Accessories | 25000 |  | 0 | 0% | - | 0% | -
Building Signage | 400000 |  | 0 | 0% | - | 0% | -
Entrance Floor Mats & Frames | 10000 |  | 0 | 0% | - | 0% | -
SCADA | 400000 |  | 0 | 0% | - | 0% | -
Mechanical Systems | 1200000 |  | 0 | 0% | - | 0% | -
Plumbing | 500000 |  | 0 | 0% | - | 0% | -
Fire Protection | 300000 |  | 0 | 0% | - | 0% | -
Electrical | 5000000 |  | 0 | 0% | - | 0% | -
Primary Power | 3000000 |  | 0 | 0% | - | 0% | -
Mock Ups | 500000 |  | 0 | 0% | - | 0% | -
| 34491000 |  | 0
|  | 0% |  | 0% |  | 0%

## Tab C (2)
GMP Summary
School / Project Manager:
|  | Date: | 2022-02-10
Project Number: |  | AV101 |  | Date: | 2022-02-10
Project Title: |  | Sky Train Stage 2
CONSTRUCTION SERVICES |  |  |  |  | AMOUNT
DIRECT COSTS
A. | Cost of Construction (Labor, Materials, Equipment)
B. | Allowances
C. | CMAR's Contingency
D. |  | SUBTOTAL DIRECT COSTS |  |  | 0
INDIRECT COSTS |  |  |  | CALCULATED RATE
E. | General Conditions (Excluding General Requirements, Bonds, and Insurance) |  |  | #DIV/0!
F. | General Requirements |  |  | #DIV/0! | 600000
G. | Payment and Performance Bond |  |  | 1% | 0
H. | Insurance |  |  | 0.5% | 0
I. |  | SUBTOTAL GENERAL CONDITIONS COSTS |  | #DIV/0! | 600000
J. |  | SUBTOTAL DIRECT AND INDIRECT COSTS |  |  | 600000
K. | Construction Fee (Overhead & Profit) |  |  | 5%
L. |  | SUBTOTAL DIRECT AND INDIRECT COSTS (INCLUDING FEE) |  |  | 600000
M. | Transaction Privilege Tax |  |  | 6%
|  |  | N. GMP (Minus Owner's Contingency) |  | 600000
|  |  | O. Owner's Contingency |  | 1000000
|  |  | P. Contract Price |  | 1600000