## NBCU-G Scheme 1 (hidden)
NBCU Lot G Pour Cycle - Scheme 1: 7 Form Sets
Alternating 2 Pours and 3 Pours / Week (Average 45,000 SF/week)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65
Form Set 1 | F1 | F | F | F | r | r | r | r | r | P | c | c | s1
Form Set 2 |  |  | F2 | F | F | F | r | r | r | r | r | P | c | c | s2
Form Set 3 |  |  |  |  | F3 | F | F | F | r | r | r | r | r | P | c | c | s3
Form Set 4 | [6 empty] | F4 | F | F | F | r | r | r | r | r | P | c | c | s4
Form Set 5 | [8 empty] | F5 | F | F | F | r | r | r | r | r | P | c | c | s5
Form Set 6 | [10 empty] | F6 | F | F | F | r | r | r | r | r | P | c | c | s6
Form Set 7 | [12 empty] | F7 | F | F | F | r | r | r | r | r | P | c | c | s7
Form Set 1 | [14 empty] | F1 | F | F | F | r | r | r | r | r | P | c | c | s1
Form Set 2 | [16 empty] | F2 | F | F | F | r | r | r | r | r | P | c | c | s2
Form Set 3 | [18 empty] | F3 | F | F | F | r | r | r | r | r | P | c | c | s3
Form Set 4 | [20 empty] | F4 | F | F | F | r | r | r | r | r | P | c | c | s4
Form Set 5 | [22 empty] | F5 | F | F | F | r | r | r | r | r | P | c | c | s5
Form Set 6 | [24 empty] | F6 | F | F | F | r | r | r | r | r | P | c | c | s6
Form Set 7 | [26 empty] | F7 | F | F | F | r | r | r | r | r | P | c | c | s7
Form Set 1 | [28 empty] | F1 | F | F | F | r | r | r | r | r | P | c | c | s1
Form Set 2 | [30 empty] | F2 | F | F | F | r | r | r | r | r | P | c | c | s2
Form Set 3 | [32 empty] | F3 | F | F | F | r | r | r | r | r | P | c | c | s3
Form Set 4 | [34 empty] | F4 | F | F | F | r | r | r | r | r | P | c | c | s4
Form Set 5 | [36 empty] | F5 | F | F | F | r | r | r | r | r | P | c | c | s5
Form Set 6 | [38 empty] | F6 | F | F | F | r | r | r | r | r | P | c | c | s6 | r
Form Set 7 | [40 empty] | F7 | F | F | F | r | r | r | r | r | P | c | c | s7
Form Set 1 | [42 empty] | F1 | F | F | F | r | r | r | r | r | P | c | c | s1
Form Set 2 | [44 empty] | F2 | F | F | F | r | r | r | r | r | P | c | c | s2
Set 1
Set 2
Set 3
Set 4
Set 5
Set 6
Set 7
Set 1
Set 4
Set 5
Set 2
Set 3 10

## Cost Analysis
[5 empty] | TMI Service Fees | 13625.58
710 Wilshire |  |  |  |  | Wilshire Blvd Ped Canopy | 26189.24
Job # 15-602 |  |  |  |  | 7th Court Alley Acess (not full closure) | 4301.15
Street Closure & Permit Analysis |  |  |  |  | 7th street closure (obtaining additional lane) | 5149.4
[5 empty] | 7th street closure (baseline @ sidewalk and parking lane) | 470965.06
925815.73
DESCRIPTION | QUANTITY | PRICE | TOTAL | NOTES
7th Court Alley use during mass Ex. | 15 | 4301.15 | 64517.25 | Assuming 5 days @ 3 different times during mass-ex due to flipping dive ramp | 562-308-0311 - Joeseph Woodward
7th Court Alley use during install and dismantle of placing boom hard pipe. | 6 | 4301.15 | 25806.9 | Demo & install, remove and replace for burried hard pipe at concrete system
7th Court Alley during install of exterior skin | 15 | 4301.15 | 64517.25 | Install and dismantle of scaffold, overhead picks at Alley. 15 days total assumed.
7th Court Alley during install utilities & B-permit work | 15 | 4301.15 | 64517.25 | Closure of alley for utilities and replacing of alley. Cost is NOT ran for full closure
Wilshire Closure @ B-permit work | 10 | 5149.4 | 51494 | Closure of parking and single lane during sidewalk work infront of Landmark.
Wilshir Blvd Pedestrian Canopy @ 12 months (incl closures for up & down) | 12 | 2182.4367 | 26189.24 | Includes closure of wilshire sidewalk for install and breakdown. Includes sidewalk use for canopy @ 12 months.
7th street closure @ tower crane up & down | 8 | 5149.4 | 41195.2 | Closure of additional lane on 7th street for up & down of tower crane (4 days each).
7th street closure @ Concrete pours prior to placing boom | 10 | 5149.4 | 51494 | Closure of additional lane on 7th street for 47M outrigger spread and acess for 1 truck going north. 10 Pours prior to PB erection
7th street closure @ B-permit work | 10 | 5149.4 | 51494 | Closure of additional lane on 7th street for removal and replace of sidewalk (10 days total).
7th street closure (baseline @ 27 months) | 27 | 17443.1504 | 470965.06 | Baseline closure for duration of project on 7th street. 26 month schedule + 1 month. Closure is all inclusive of sidewalk and parking lane (city fees, permit cost, equipment rental, install, etc.)
TMI service fees (plans, permits, etc.) | 1 | 13625.58 | 13625.58 | See Back-up. Service fees for TMI
0
0

## Back-up
710 Wilshire
Job # 15-602
Cost Back-up
DESCRIPTION | Incl # | QUANTITY | PRICE | TOTAL | NOTES
TMI Service Fees | # E-45399 |  |  | 13625.58
TMI Engineering Fee | 1 | 1 | 2900 | 2900 | Cost includes traffic control plan
TMI Plan Check Fee | 2 | 3 | 241.86 | 725.58 | Plan Check Fee for 3 phases of approvals
TMI Service Fee | NA | 10 | 1000 | 10000 | Add'L service fees as req'd
Wilshire Blvd Ped Canopy | # E-45399 |  |  | 26189.24
Encroachment Permit Service Fee | 4 | 2 | 350 | 700 | TMI Cost for submission to city
Encroachment Permit | 5 | 12 | 1808.77 | 21705.24 | Cost of permit from SM (can vary). Monthly Rate, assuming 12 months
Post No parking signs for up & down | 6 | 4 | 390 | 1560 | Posting no parking signs for erection and dismantlre of Ped canopy.
Wilshire single lane and sidewalk closure for up & down | 7 | 4 | 556 | 2224 | Labor, equip & material for wilshire lane and parking closure. $/day
7th Court Alley Acess (not full closure) | # E-45399 |  |  | 4301.15
Encroachment Permit Service Fee | 15 | 1 | 350 | 350 | TMI Cost for submission to city
Encroachment Permit | 16 | 1 | 2052.75 | 2052.75 | Cost of permit from SM (can vary). $/Ea permit pulled
Signage & Equipment | 17 | 1 | 420 | 420 | $/day of rental equipment
Flagmen (labor incl. burden) | NA | 24 | 61.6 | 1478.4 | assuming MCC laborers
7th street closure (obtaining additional lane) | # E-45399 |  |  | 5149.4
Encroachment Permit Service Fee | 9 | 2 | 350 | 700 | TMI Cost for submission to city
Encroachment Permit | 10 | 2 | 1032.7 | 2065.4 | Cost of permit from SM (can vary). Each rate (Need revised quote)
Post No parking signs for up & down | 11 & 12 | 4 | 350 | 1400 | Posting no parking signs @ 7th street
Shoulder/parking lane & bike lane closure (equip) | 13 | 2 | 492 | 984 | Traffic control devices, install & removal. $/day assuming 2 day minimum.
7th street closure (baseline W/ sidewalk & parking lane) | # E-41366 |  |  | 470965.06
Traffic Control Planning | 1 | 1 | 650 | 650 | Survey & as-builts
SM Plan Check Fee | 2 | 1 | 241.86 | 241.86 | SM agency plan check review
Encroachment Permit Service Fee | 4 | 7 | 350 | 2450 | TMI Cost for submission to city (7 times at every other month)
Encroachment Permit | 3 | 27 | 6116.85 | 165154.95 | Cost of permit from SM (can vary). Each rate at 27 Months
Bagging and tagging parking meters | 5 | 27 | 10140 | 273780 | Bagging & tagging meters on sidewalk for 27 months ($338/day)
Bagging and tagging parking meters (service Fee) | 6 | 1 | 350 | 350 | Service fee @ Meters (look into pulling meters, not bagged)
Rental equipment for closure | 9 | 27 | 978.75 | 26426.25 | All material and signage for closure
Install of closure & Breakdown of closure | 7 | 4 | 478 | 1912 | TMI set up & breakdown
0